## Tab 1 - Guidance
DRGR QPR Review Guidance
(1) | Log in to DRGR and click on the QPR tab in the navigation bar on the top of the page. Find the grant you want and click Review QPR in the far right column in that row. Under the action column, click on “Review” for the most recently submitted QPR.
(2) | There are three ways to look at a Quarterly Performance Report (QPR) in the Disaster Recovery Grant Reporting System (DRGR): (1) View – official “submitted” version with calculated fields; (2) Download – PDF file of official submitted version; (3) Review – to record your comments and change the status.
(3) | QPRs cannot be reviewed unless the QPR is in Submitted status. Grantees cannot submit QPRs unless the Action Plan is in Approved status when they try to submit the QPR.
(4) | If the QPR is missing required information, reject the QPR and send an email to the grantee requesting a correction within 10 days.
(5) | If the QPR review raises questions, note them in the comments field (with your initials) and discuss with the grantee before the next QPR is due.
(6) | If the review reveals that the Action Plan needs updating, you may accept the QPR with a note to the comment field, or you may reject the QPR and require the plan corrections prior to resubmission of the QPR.
(7) | If there is one late QPR, notify grantee. If there is more than one late QPR or if any QPRs are missing, notify Headquarters to discuss options, including issuance of a finding of noncompliance.
(8) | After completion, save all of your comments and, using the pulldown menu, change the status of the QPR from Submitted-Await for Review to either Approved and Reviewed or Rejected – Await for Modification. Remember to save after changing the status.
(a) Rejected – Await for Modification unlocks the QPR so the grantee can edit it and make corrections.
(b) Reviewed and Approved leaves the QPR locked and stored as the report of record.
(9) | Approved QPRs must be posted on grantee’s website 3 days after submission.

## Tab 2 - Checklist
DRGR QPR Review Guide
|  | Initial Review |  | Subsequent Review |  | Subsequent Review |  | Subsequent Review |  | Subsequent Review |  | Subsequent Review |  | Subsequent Review
Grantee: |  | QPR Date Range: |  | QPR Date Range: |  | QPR Date Range: |  | QPR Date Range: |  | QPR Date Range: |  | QPR Date Range: |  | QPR Date Range:
Grant Amount: |  | Date QPR Submitted: |  | Date QPR Submitted: |  | Date QPR Submitted: |  | Date QPR Submitted: |  | Date QPR Submitted: |  | Date QPR Submitted: |  | Date QPR Submitted:
Grant Number: |  | Date Reviewed: |  | Date Reviewed: |  | Date Reviewed: |  | Date Reviewed: |  | Date Reviewed: |  | Date Reviewed: |  | Date Reviewed:
HUD Office: |  | Reviewer(s): |  | Reviewer(s): |  | Reviewer(s): |  | Reviewer(s): |  | Reviewer(s): |  | Reviewer(s): |  | Reviewer(s):
|  | Review Outcome: |  | Review Outcome: |  | Review Outcome: |  | Review Outcome: |  | Review Outcome: |  | Review Outcome: |  | Review Outcome:
|  | __Approved | __Rejected | __Approved | __Rejected | __Approved | __Rejected | __Approved | __Rejected | __Approved | __Rejected | __Approved | __Rejected | __Approved | __Rejected
Criteria |  | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No | Yes | No
A. | Overall Progress Narrative
Report Narrative and Timeliness
(1) | Does the Overall Progress Narrative explain the progress of this grant during the previous quarter?
(2) | Was the QPR submitted on time?
(3) | Have all previous QPRs been submitted?
(a) If not, how many are missing?
(4) | Have any previous QPRs been submitted late?
(a) If so, how many?
(5) | Have you added and saved your comments in the Overall Comments field?
Comments:
Overall Financial Progress
(6) | Under the "To Date" column, is the "Total Obligated" amount less than the "Total Budget" amount?
(7) | Under the "To Date" column, is the "Total Funds Drawdown" amount less than the "Total Obligated" amount?
(8) | Is there more than a 10% discrepancy (either for this quarter or cumulatively) between the amount of "Total Funds Drawndown" and the amount of "Total Funds Expended"?1
(9) | Does the grantee appear to be budgeting, obligating, drawing, and expending funds at a reasonable pace?2
Comments:
Progress toward required targets
(10) | Does the "Overall Benefit Percentage (Actual)" appear to be on track to meet the "Overall Benefit Percentage (Projected)"?
(11) | Does the amount expended (to date) on admin/planning fall below the "Limit on Admin/Planning"?
(12) | Does the amount expended (to date) on public services fall below the "Limit on Public Services"?
(13) | Does the actual amount of funds expended on Affordable Rental Housing activities (KRW and Ike Grants only) appear to be on track toward meeting the targeted amount?
(14) | Does the actual amount of funds expended on Low/Mod activities appear to be on track toward meeting the targeted amount?
Comments:
Program Income
(15) | Are there any activities that are earning Program Income (e.g. loans, property disposition, etc…)?
(16) | Under the "Overall Narrative", was any Program Income recorded as received under this report period or to date?
(a) If yes, does the amount of Program Income recorded seem reasonable for the activities for which it was received?
(17) | Under the "Overall Narrative", was any Program Income recorded as drawndown under this report period or to date?
(a) If yes, is the amount of Program Income drawndown less than the total amount of Program Income received to date?
(18) | Is there a growing balance of Program Income available that is not being used on other activities before grant funds?
(19) | Do the DRGR activities showing Program Income disbursements adequately demonstrate the eligibility of uses?
Comments:
B. | Individual Activity Progress Review (list activities reviewed on Tab 3)
Review of Financial Progress
(20) | Activity Status
(a) If marked as complete, have all of the activity funds been drawndown and expended?3
(b) If marked as underway, have:
(i) All funds been drawndown and expended?4
(ii)Any funds been drawndown and expended?5
(c) Does the projected end date correlate with the amount of funds remaining?6
(21) | Is the amount to date of "Total Obligated" less than the amount of "Total Budget"?
(22) | Is the amount to date of "Total Funds Drawndown" less than the amount "Total Obligated"?
(23) | Is there more than a 10% discrepancy (either for this quarter or cumulatively) between the amount of "Total Funds Drawdown" and the amount of "Total Funds Expended"?7
Comments:
Review of Performance Accomplishments8
Public Facilities and Infrastructure (area benefit activities)9
(24) | For activities in which funds are fully expended, has the grantee entered the appropriate performance measures such as "Linear Feet of Public Improvement" or "Number of Public Facilities" under "This Report Period Total" column? (This will automatically update the performance measure in the "Cumulative Actual Total" column.)
(25) | For activities in which funds are not fully expended, do the amounts under "This Report Period" and "Cumulative Actual Total" remain at $0?
Housing (Direct Benefit Activities)10
(26) | If the grantee is reporting drawdowns and expenditures for this quarter, have the performance measures (# of housing units, # of MF/SF units, # of households, and # of owner/renter households by income level) been entered under "This Report Period" total?
(a) Are all of the numbers entered for the performance measures equal?
(b) If the units are single family and the activity meets the LMI national objective, are all of the numbers recorded under the Low or Mod columns?11
(27) | Do the performance measures (# of housing units, # of MF/SF units and # of households, # of owner/renter households by income level) under the "Cumulative Actual Total" column appear to reflect the proportion of funds expended to date out of the total amount of funds budgeted?
(a) Are all of the numbers entered for the performance measures equal?
Economic Development Activities
(28) | If the grantee has reported drawdowns and expenditures to date, have the appropriate performances measures (# of businesses, # of jobs created/retained) and/or the appropriate beneficiary measures (jobs created by income level) been reported under "This Report Period" or under the "Cumulative Actual Total" columns?
(29) | For direct benefit activities meeting the Low-Mod national objective, do all of the numbers appear under the Low or Mod columns?
(30) | For area benefit activities in which funds are not fully expended, do the amounts under "This Report Period" and "Cumulative Actual Total" columns remain at $0?
Other Activities (acquisition, relocation payments, debris removal, etc…)
(31) | If the grantee is reporting drawdowns and expenditures for this quarter, have the performance measures (# of housing units, # of MF/SF units, # of households, and # of owner/renter households by income level) been entered under "This Report Period" total?
(32) | Do the performance measures under the "Cumulative Actual Total" column appear to reflect the proportion of funds expended to date out of the total amount of funds budgeted?
All Activities
(33) | Does the Activity Progress Narrative correlate with expenditure levels and any accomplishment updates?12
Comments:
Footnotes:
1: If so, determine whether grantee has a reporting error or is drawing funds in advance of need.
2: While the reviewer has the discretion to determine what is a 'reasonable pace', HUD anticipates annual expenditure rates of about 10-15% for grantees less than $1 billion.
3: An activity should only be marked as complete if a grantee has drawndown and expended all of the activity funds and updated the activity’s performance and beneficiary accomplishments.
4: If all funds have been drawndown and expended, the performance measures should be updated and the activity status should be changed to complete in the action plan.
5: An activity should only be marked as underway if a grantee has begun to drawdown funds.
6: If an activity has not been fully drawndown and expended, the projected end date should be a future date.
7: If so, determine whether grantee has a reporting error or may be drawing funds in advance of need.
8: If an activity does not have any accomplishment performance measures selected, the grantee must re-submit the action plan to include them.
9: Performance measures for infrastructure activities should only be updated with actual accomplishments once the activity is fully expended. At this stage it is assumed the public facility is in use by the community.
10: Performance measures for housing activities should be updated once housing units are complete and households have occupied the unit.
11: Activities must be separated by national objective.
12: As a reminder, direct benefit activities like housing and ED job creation usually create accomplishments as funds are disbursed. Area area benefit activities like infrastructure and public facilities will usually load heavy into the last quarters.
Note on B84: Mary Liz Mann: Not sure how we want to define "reasonable pace". The 10%-15% was based off of an email Scott sent on 6/11/12.

## Tab 3 - Activities Reviewed
Date | Activity Number | Issue | Corrective Action | Status Update (incl. date)