## Start Here
U.S. Department of Housing and Urban Development
Chief Risk Officer's Front-End Risk Assessment (FERA)
2010 NEW Handbook, Attachment C - Risk Indicators and Ranking Guide
Name of Program: | Date:
Name of Preparer: | Job Title:
HUD Office | Division:
Phone Number: | HUD Email:
Purpose:
- Defines risk factors to provide programs with a guide for prioritizing risk areas and begin to develop associated risks for inclusion in the risk register. - Column J marks the alignment to the ERM taxonomy categories to (see Attachment D for the Risk Taxonomy) in helping to identify the types of risks that may be related to these risk factor areas.
Instructions:
- On the FERA Risk Indicators tab, read the guidance columns (E - G) and rank each risk score from 1-5 in Column I based on the high, medium, and low descriptions. Mark Column H as "N" if the sub-risk factor is not applicable to your program. - Ranking of the risk indicators should consider the potential impacts to HUD requirements and objectives from the perspective of both HUD and third parties (such as grantees) where applicable, depending on the program type, roles and responsibilities, and particular high risk areas. You may choose to report rankings from one or both of these perspectives (e.g., in the aggregate of HUD and third party risk). - Column J describes the HUD ERM level 1 taxonomy categories that relate to each risk indicator to promote alignment between this document and Attachment D, the Risk Register. The taxonomy categories (compliance, strategic, reporting, and operational) can be used to guide the risk statements and impacts that will be disclosed in Attachment D.

## FERA Risk Indicators
U.S. Department of Housing and Urban Development
Chief Risk Officer's Front-End Risk Assessment (FERA)
2010 NEW Handbook, Attachment C - Risk Indicators and Ranking Guide
NO. | RISK FACTOR | SUB-RISK FACTOR | SUB-FACTOR RISK RATINGS |  |  |  |  | Mapping to Risk Taxonomy (Level I)
|  |  | Low | Medium | High | Applicable? | Ranking
|  |  | 1 - 2 | 3 | 4 - 5 |  | 1 - 5
1a. | NATURE of PROGRAM or FUNCTION | Type of Award (Formula vs. Competitive) | - Outlays primarily consist of formula awards | - Outlays are comprised of a mix of formula and competitive awards | - Outlays predominantly consist of competitive awards | Y | 5 | Operational
1b. |  | Magnitude of Cash or Cash Equivalents | - Program manages insignificant amounts of cash or cash equivalents | - Program oversees a fairly substantial quantity of cash or cash equivalents | - Program administers large sums of cash or cash equivalents |  |  | Operational
1c. |  | Degree of Automation in Financial Management Business Processes | - Program employs automated or formal manual processes for financial management that are tested and proven to be designed appropriately and operating effectively | - Program employs a combination of automated and manual controls for financial management processing that have documented processes that have not been tested for design and operating effectiveness. | - Program employs manual financial processes lacking a standard policy or operating in an ad hoc environment |  |  | Reporting; Operational
1d. |  | Degree of Automation in Operational Business Processes (e.g., program-specific functions such as performance of grantees or risk monitoring) | - Program utilizes automated or formal manual processes for operational activities that are tested and proven to be designed appropriately and operating effectively | - Program utilizes efficient and effective combination of automated and manual controls for operational processes that have not been tested for design and operating effectiveness. | - Program employs manual operational processes lacking a standard policy or operating in an ad hoc environment |  |  | Operational; Reporting; Compliance
1e. |  | Complexity in Program Structure, Transactions, and Processes | - Straightforward program structure, processes, and transactions | - Moderately complex structure, processes, and/or transactions | - Highly complex program structure, processes, and/or transactions |  |  | Operational; Compliance
1f. |  | Volume of Payments | - Low volume of payments and disbursements | - Moderate volume of payments and disbursements | - High volume of payments and disbursements |  |  | Operational
1g. |  | Scope of Authority | - Few activities involving approval of applications, granting of authority, issuance of licenses, certifications, inspections, or enforcement | - Some activities involve the approval of applications, granting of authority, issuance of licenses, certifications, inspections, or enforcement | - Many activities involving the approval of applications, granting of authority, issuance of licenses, certifications, inspections, or enforcement |  |  | Operational; Strategic; Compliance
1h. |  | Reliance on Procurement | - Program depends on little to no procurement assistance | - Program requires some support from procurement assistance | - Program heavily reliant on procurement assistance, resulting in compliance and oversight requirements |  |  | Operational; Compliance
1i. |  | Program Ownership | - Program is administered, controlled, and managed by a Federal organization | - Program is administered, controlled, and managed by a mix of Federal and non-Federal organizations | - Program is primarily administered by recipients of Federal funding (non-Federal organizations) responsible for project management and control |  |  | Operational
2a. | ORGANIZATIONAL STRUCTURE | Assignment of Roles and Responsibilities | - Lines of accountability, responsibility, authority, and reporting are clearly established, defined, and documented | - Somewhat ambiguous assignments of accountability, responsibility, authority, and/or reporting; lack of documentation | - Does not designate and document accountability, responsibility, authority, and/or reporting roles |  |  | Operational
2b. |  | Separation of Duties | - Employs separation of duties for record-keeping, custody, and authorization functions | - Partial segregation between record-keeping, custody, and authorization functions | - Little to no segregation between record-keeping, custody, and authorization duties |  |  | Operational; Reporting
2c. |  | Monitoring / Oversight Infrastructure | - Oversight and monitoring structure exists and activities are documented | - Some monitoring and oversight in place, but lacks documentation | - Monitoring and oversight is nonexistent or no documentation of activities |  |  | Strategic; Compliance
2d. |  | Degree of Centralization | - Centralized structure or maintains an appropriate degree of decentralization | - Presents some risks due to decentralization, but extent remains suitable | - Wholly decentralized structure |  |  | Operational
3a. | GOALS and OBJECTIVES | Mission and Goals | - Mission and/or goals are documented, well-defined, clear and easily interpreted | - Mission and/or goals are documented, defined somewhat clearly and are relatively easy to understand | - Mission and/or goals are undocumented or broad, vague and difficult to understand |  |  | Strategic
3b. |  | Key Performance Indicators (KPIs) and Key Risk Indicators (KRIs) | - Objectives are measurable, achievable, and consistent as documented by KPIs, KRIs, or other quantitative techniques | - Objectives are fairly inconsistent with each other, rather difficult to measure, and/or marginally unobtainable; key performance indicators may not relate to strategic goals | - Objectives are inconsistent, unattainable, and/or immeasurable; KPIs not identified or do not relate back to strategic objectives |  |  | Operational
4a. | INTERNAL CONTROLS | Quality Assurances for Financial Management Controls | - Quality assurance utilizes existing financial management controls that have been evaluated and proven for design and operating effectiveness | - The program or function uses existing financial management controls, but quality assurances have not been evaluated for design and operating effectiveness | - There are no existing financial management controls in place, or they have been previously assessed and proven ineffective in design and/or operating effectiveness |  |  | Reporting; Operational
4b. |  | Quality Assurances for Operational Controls (e.g., program-specific functions such as performance of grantees or risk monitoring) | - Quality assurance utilizes existing operational controls that have been evaluated and proven in design and operating effectiveness | - The program or function uses incumbent operational controls, but quality assurances have not been evaluated for design and operating effectiveness | - There are no existing operational controls in place or incumbent controls have been assessed and proven ineffective in design and/or operating effectiveness |  |  | Reporting; Operational
4c. |  | Quality Assurances for System Controls | - Quality assurance utilizes existing system controls that have been evaluated and proven for design and operating effectiveness | - The program or function uses incumbent system controls, but quality assurances have not been evaluated for design and operating effectiveness | - There are no existing system controls in place or incumbent controls have been assessed and proven ineffective in design and/or operating effectiveness |  |  | Reporting; Operational
4d. |  | Monitoring of Internal Controls | - Formal process for monitoring and tracking weaknesses in internal control is established | - Process in place for monitoring and tracking internal control weaknesses, but no means for enforcing its use | - No means established for monitoring and tracking internal control weaknesses |  |  | Operational
4e. |  | Risk Assessments (e.g., ERM risk assessments, pre and post-award risk assessments) | - Processes and delegation of responsibility for conducting risk assessments are documented and executed in a timely manner | - Processes and delegation of responsibility for conducting risk assessments are documented, but execution is somewhat delayed | - Processes and delegation of responsibility for conducting risk assessments are not documented, or execution is significantly delayed or does not occur at all |  |  | Operational
4f. |  | Restricting Program Participation | - Prevention method exists for limiting the participation of ineligible (including suspended or debarred) parties | Method for prohibiting participation of ineligible (including suspended or debarred) parties in place, but there is no means of ensuring its use | - No process in place for precluding participation of ineligible (including suspended or debarred) parties |  |  | Operational; Compliance
5a. | FUNDING | Cost Estimates | - Detailed and validated estimate exists | - Detailed estimate but not yet validated | - Conceptual level estimate |  |  | Operational
5b. |  | Identification of Resources | - Resources identified, committed and available for execution | - Resources are identified but may not be committed | - Resources are not identified |  |  | Operational
5c. |  | Budget Justification and Sustainability | - Funding is sufficient to fully fund and fulfill objectives | - Funding may be inadequate to cover program requirements and carry out objectives | - Funding feasibility issues are certain or unknown |  |  | Operational
5d. |  | Contingency Plans | - Existence and completeness of contingency plans | - Contingency plans may be in place, but are incomplete and unsatisfactory | - Contingency plans do not exist |  |  | Operational
6a. | TIME and SCHEDULE | Project Duration (Implementation - Close-out) | - Less than 24 months (< 2 years) | - 24-48 months (2-4 years) | - Greater than 48 months (4 years) |  |  | Operational
6b. |  | Accounting for Delays | - Project plan factors in time for inactivity and routine delays | - Project plan accounts for some slack and routine schedule delays | - Slack and routine timing delays are not scheduled into the project plan |  |  | Operational
6c. |  | Continuity | - Predecessor and successor action plans are simple and clearly identified and understood | - Predecessor and successor action plans are identified, but are incomplete or convoluted | - Predecessor and successor actions are not identified |  |  | Operational
6d. |  | Assumptions | - Analysis with regard to performance identified no need for assumptions | - Analysis with regard to performance identified assumptions which have been validated | - Assumptions are vague, untestable or already proven false |  |  | Operational
7a. | AUDIT FINDINGS | External Findings | - No prior OIG, GAO findings for same or similar issue related to the program; no cross-cutting applicability of previous OIG or GAO findings from other similar programs or offices; no single audit findings related to the program | - Prior OIG, GAO findings for same or similar issue related to the program and/or single audit findings related to the program, but these audit findings have been closed | - Audit recommendations remain open from OIG or GAO findings for same or similar issue related to the program and/or single audit findings related to the program; unknown or certain applicability of open OIG or GAO audit findings from other similar programs or offices related to the program |  |  | Strategic; Reporting
7b. |  | Internal Findings | - No issue/risk related to the program documented from management, ERM or A-123 reviews; no cross-cutting applicability of internal audit findings related to the program from other similar program or office after review of controls has been conducted | - Issues/risk related to the program documented from ERM, A-123, or management reviews, but audit recommendations have been closed | - Open audit recommendations related to the program in ARCATS from ERM, A-123, or management reviews; certain or unknown applicability of internal audit findings related to the program from other similar program or offices |  |  | Strategic; Reporting
8a. | IMPACT OF ERRORS | Impact of External Errors | - HUD has large tolerances for errors committed by external parties, but there is little to no impact to the program's mission or reputation | - HUD has a moderate tolerance for external errors, where deviations could have a somewhat significant impact to the program's mission or reputation | - HUD has such a low tolerance for external errors that it results in slight deviations from the requirement creating a significant impact to the program's mission or reputation |  |  | Operational
8b. |  | Impact of Internal Errors | - HUD has internal quality control (QC) requirements with a wide range for acceptable deviation and/or internal errors. Deviations and errors have little to no impact to the program's mission or reputation | - HUD has average QC requirements for internal errors where errors or deviations can result in a somewhat significant impact to the program's mission or reputation. | - HUD has strict QC requirements for internal errors, where small errors or slight deviations can result in a significant impact to the program's mission or reputation. |  |  | Operational
9a. | TECHNOLOGY | Existence of System | - No new systems or technology needs to implemented | - Existing tool or system needs to be modified to accommodate program | - New system and/or tools need to be implemented to automate the new business process |  |  | Operational
9b. |  | System Interfaces | - Established and mature system interfaces and working relationships used | - Some new system interfaces must be established and managed | - Multiple, new, and/or complex system interfaces required and are manual or planned to be manual; may include competing objectives |  |  | Operational
9c. |  | Security and System Access | - Security measures are in place to limit system access only to authorized personnel | - Some security measures are established, but system access is provided to a number of unauthorized individuals and/or access is not consistently monitored | - Little to no security protocols are in place to restrict system access and/or no continuous monitoring of authorizations |  |  | Operational
9d. |  | Data Center Facility | - Existing Data Center with adequately designed and tested internal controls to house mission critical system(s) | - Existing Data Center will be used to house mission critical system(s); new system(s) hardware and software will need to added to the facility and controls established and tested for those new components | - New data center will need to be stood-up or system to be housed in new third party environment for mission critical systems |  |  | Operational
9e. |  | Maintenance and Monitoring | - Little maintenance or upkeep required | - Some maintenance required | - Complex/highly engineered and extensive maintenance required |  |  | Operational
9f. |  | Staff Competencies | - Incumbent staff members possess the capabilities to operate the technology | - Few existing staff members are skilled in using the technology | - Little to no incumbent employees possess the skills required for maintaining or operating the product |  |  | Operational
9g. |  | Quality of Outputs | - Produces timely, accurate, and useful outputs; fulfills initial intended purpose | - Yields somewhat inaccurate, ineffective, and/or sluggish results or does not fully satisfy intended purpose | - Produces inaccurate, delayed and/or ineffective information; does not fulfill original objectives |  |  | Operational
10a. | LABOR | Project Size | - Small project (fewer than 50 FTEs) | - Moderate sized projects (50-150 FTEs) | - Large projects (more than 150 FTEs) |  |  | Operational
10b. |  | Availability | - Readily available | - Restricted availability | - Severely restricted availability |  |  | Operational
10c. |  | Build-up | - Gradual build-up | - Phased build-up | - Rapid build-up |  |  | Operational
10d. |  | Capabilities | - No gaps exist between skills demanded by the project and capabilities of the workforce | - Some gaps exist between skills demanded by the project and proficiencies of the workforce | - Large disparity between workforce capabilities and project requirements |  |  | Operational
10e. |  | Productivity | - Low productivity requirement | - Moderate productivity required | - High productivity required |  |  | Operational
10f. |  | Contingency Plans | - Robust staffing contingency plans are in place | - Staffing contingency plans are in place, but may not be complete | - No staffing contingency plans in place |  |  | Operational
11a. | TRAINING | Existence | - Training program exists and is available to all intended users for new program requirements and processes | - Training program exists, but is unavailable to all intended users and/or only partially addresses new requirements or processes of the program | - Training program and learning objectives do not exist for new program requirements and processes |  |  | Operational; Compliance
11b. |  | Continuous Learning | - A process is in place to provide periodic ongoing refreshment of training knowledge, and follow-up is enforced | - A process is in place to provide ongoing refreshment of training knowledge, but completion is not enforced | - No process in place to provide ongoing refreshment of training knowledge |  |  | Operational
11c. |  | Completion Status | - Personnel have completed all training requirements | - Personnel have completed all onboarding requirements, but ongoing requirements are outstanding | - Personnel have not completed onboarding training requirements, or completion status is unknown |  |  | Operational
11d. |  | Subject Matter | - Personnel are trained in all appropriate and relevant subject matters | - Personnel are not trained in every relevant subject matter, but are capable enough to carry out job responsibilities | - Personnel are incapable of fulfilling their job responsibilities due to a lack of training |  |  | Operational
12a. | POLITICAL VISIBILITY and EXTERNAL STAKEHOLDER INVOLVEMENT | Stakeholder Identification | - External stakeholders have been analyzed and identified | - External stakeholders have been identified, but not analyzed | - External stakeholders have not been identified or analyzed |  |  | Strategic
12b. |  | Level of Endorsement | - External stakeholders are supportive and advocates of the program or project | - External stakeholders neutral but interested in progress updates | - Sensitive to external stakeholders; may attract considerable media attention |  |  | Strategic
12c. |  | Range of External Visibility and Involvement | - Little to no involvement with other regulatory or federal agencies | - Some involvement with other regulatory or federal agencies | - Involvement/coordination with multiple regulatory or federal agencies |  |  | Strategic
12d. |  | Depth of External Involvement | Little to no independent oversight, information sharing, or outreach/input required | - Some independent oversight, information sharing and communication outreach required | - Significant independent oversight or sizeable outreach/input required |  |  | Strategic; Compliance
13a. | POLITICAL VISIBILITY and INTERNAL STAKEHOLDER INVOLVEMENT | Stakeholder Identification | - Internal stakeholders have been identified and analyzed | - Internal stakeholders have been identified, but not analyzed | - Internal stakeholders have not been identified or analyzed |  |  | Strategic
13b. |  | Level of Endorsement | - Internal stakeholders support and advocate for the program or project | - Internal stakeholders neutral, but interested in progress updates for the program or project | - Internal stakeholders lack interest or are unsupportive of the program or project |  |  | Strategic
14a. | STAKEHOLDER DEPENDENCIES | Impact from Collaboration | - Little or no impact from other site programs operations or contractors | - Potential impact from other site operations, programs or contractors | - Potential MAJOR impact from other site operations, or contractors |  |  | Operational
14b. |  | Stakeholder Credentials | - Partners have prior experience with similar endeavors | - Limited past performance | - Newly acquired capabilities, no past performance, or capacity untested |  |  | Operational
14c. |  | Third-party Availability | - Third-party resources immediately available | - Limited resource availability | - Resources fully committed to other projects with no availability or lack of visibility into third party availability |  |  | Operational
15a. | REGULATORY INVOLVEMENT | Historical Compliance or Litigation Incidents | - No compliance or litigation issues | - Compliance or litigation issues identified, but have precedent or defined path forward | - No precedent set for compliance or litigation issues |  |  | Compliance
15b. |  | Fair Housing or Civil Rights Violations | - No historical fair housing or civil rights violations | - Historical fair housing or civil rights violations identified, but have precedent or defined path forward | '- No precedent set for fair housing or civil rights violations |  |  | Compliance
16a. | LEGISLATIVE RISK | External Legislation | - Legislation/supplemental issuances are clear, consistent with other directives, and contains strict statutory provisions that present no barriers or gaps to achieve compliance | - Legislation/supplemental guidance are immaterially unclear, inconsistent with other mandates, and/or include moderately open-ended compliance language | - Legislation/supplemental issuances are vague, substantially inconsistent with other directives, and/or include regulatory language that provides potential for non-compliance including possible enforcement challenges |  |  | Compliance
16b. |  | Internal Policy & Procedure | - Policy and operating procedures are feasible, comprehensive, easily understood, and allow for little to no user discretion | - Policy and procedural guidance and contractual agreements are somewhat comprehensive, and/or require some discretion | - Written policy and procedures are unclear, impractical, incomplete, and/or entail significant discretion |  |  | Operational
16c. |  | Binding Agreements (e.g., Contracts, Leases, Grant Agreements, Cooperative Agreements) | - Binding Agreements contain all required clauses, are easily understood, and provide no legal barriers for legal enforcement | - Binding agreements are complete and contain all required provisions, but presents some flexibility in compliance. Identified compliance gaps could not potentially interfere with administrative, criminal or civil pursuits | - Binding agreements are weak, inconsistent, incomplete, and/or incorporate flexibility in compliance that hinders enforcement proceedings |  |  | Operational
16d. |  | Fraud Policy Reference | - Policies written in a manner to address management override of internal controls and minimizing fraud, waste and abuse | - Policies reference fraud, waste and abuse, but are lacking substance | - Policies do not address fraud, waste, and abuse or management override of internal controls |  |  | Operational; Compliance
17a. | SITE CHARACTERISTICS | Number of Facilities | - 1 site or facility | - 2-3 sites or facilities | - 4 or more sites or facilities |  |  | Operational
17b. |  | Ownership | - HUD owned or GSA leased property | - HUD owned, GSA leased, or Government owned property that is not owned by HUD or GSA leased | - Private property |  |  | Operational
17c. |  | Accessibility | - Easily accessible | - Accessible | - Restricted access |  |  | Operational
17d. |  | Floodplains | - Project site does not contain floodplains | - Project site contains a 500-year floodplain (Zone X), and is not a Critical Action | - Project site contains a 100-year floodplain (Zone A) or Coastal High Hazard Area (Zone V) or project is a 500-year floodplain with a Critical Action. |  |  | Operational
17e. |  | Construction Required | - No required changes to site infrastructure | - Minor changes to facility infrastructure needed | - Major infrastructure modifications required |  |  | Operational
18a. | PROJECT IMPLEMENTATION HEALTH and SAFETY | Construction Required | - Little to no construction needed | - Some construction necessary | - Significant construction required |  |  | Operational
18b. |  | Contractor Expertise | - Contractor demonstrates past experience with same type of project | - Contractor has prior experience with similar type of project | - Contractor lacks experience in dealing with same or similar projects |  |  | Operational
18c. |  | Safety Approach | - Worker health and safety "integrated " with job planning | - Worker health and safety included in job planning, but may be incomplete | - Worker health and safety not incorporated into job planning |  |  | Operational
18d. |  | Approach Implementation | - Integrated approach is fully implemented and mature | - Most elements of an "integrated" worker health and safety approach exist but may not be fully mature or complete | - "Integrated" worker health and safety approach not implemented into daily activities |  |  | Operational
18e. |  | Management of Health and Safety Risks | - Health and safety risks are unlikely and well controlled | - Health and safety risks are moderate, but well controlled | - Health and safety risks are high and/or poorly controlled |  |  | Operational
18.f |  | Historical Safety Record | - Facility/contractor has exemplary health and safety record | - Contractor/facility has a reliable health and safety record | - Contractor/facility does not have strong health and safety record or a mature health and safety program |  |  | Operational
19a. | MAGNITUDE AND COMPLEXITY of CONTAMINATION | Knowledge of Hazards | - Existing hazards are known and well understood | - Hazards are known, but not understood | - Hazards are unknown and not understood |  |  | Operational
19b. |  | Distance from Contamination Sites | Property is more than one mile of a site listed in federal, state or tribal government records as described in the All Appropriate Inquiries Rule Section, 40 CFR 312.26 and is not within one mile of a Department of Defense Formerly Used Defense Site | Property is less than one mile of a site listed in federal, state or tribal government records as described in the All Appropriate Inquiries Rule Section, 40 CFR 312.26 and is not within one mile of a Department of Defense Formerly Used Defense Site. | Property is less than one mile from a CERCLA National Priorities List or alternative site or Department of Defense Formerly Used Defense Site designated for removal or remedial action, is less than ½ mile from a State or Tribal Brownfield’s site, has undergone removal action or remedial response, has a deed notice or restriction, activity and use limitation, engineering controls or other land use control related to site contamination, is less than ¼ mile, on or adjacent to any site listed in federal, state, or tribal government records as described in the All Appropriate Inquiries Rule Section, 40 CFR 312.26. |  |  | Operational
19c. |  | Probability of Exposure | - Very remote potential for chronic or acute exposure to chemical or radiological hazards | - Possible potential for chronic or acute exposure to chemical or radiological hazards | - Very likely potential for chronic or acute exposure to chemical or radiological hazards |  |  | Strategic
19d. |  | Degree of Confidence | - High confidence in the characterization of industrial, chemical and radiological hazards | - Industrial, chemical, and/or radiological hazards are characterized and defined, however incomplete | - No confidence in in characterization and severity of industrial, chemical and radiological hazards |  |  | Strategic
19e. |  | Past Performance | - Exemplary past record for hazardous conditions and industrial health and safety program performance | - Satisfactory past record for hazardous condition and industrial health and safety program performance | - Unsatisfactory past record for hazardous condition and industrial health and safety program performance |  |  | Strategic
20a. | EXTRAORDINARY EVENTS and TRANSACTIONS | Impact of Events (such as natural disasters, major changes in regulation, economic instability, significant budget cuts) | - Possible unforeseen or atypical external events or transactions have little to no impact on the program or function | - Achieving the program or function's mission could be somewhat disrupted by unforeseen or atypical external events or transactions | - Potential extraordinary events or transactions could have a significant or severe impact to the program or function's mission and operations |  |  | Strategic; Operational

## Sheet2 (hidden)
Y
N

## Sheet1 (hidden)
Scoring Ranking
N/A
1
2
3
4
5