## Instructions
Project Tailoring Agreement PPM V2.0
Column | Instructions For Completing This Document
Complete the Project Name, Project Phase, Project Type fields
B | Artifact: This is a pre-populated locked field that lists all of the artifacts that could be initiated, updated, or finalized in each phase.
C | Tailoring: This is an unlocked field used by project teams to propose a tailoring agreement for each artifact. Each possible tailoring agreement is defined below. By default, all artifacts are required. «Required: Use this when the artifact is required and must be created and use the comment column in the PTA to describe the level of detail associated with the artifact (e.g. initiative level, project level, sub-project level). «May be Applicable: This is a TEMPORARY selection to denote if the project is not necessarily required for the project type. As the project develops their Project Tailoring Agreement, any artifacts with this designation as the default should be changed to one of the other 5 choices. «Combine: Use this when you will address the requirements associated with the artifact in question as a section within a larger document rather than as a stand-alone artifact. Combining component management plans (e.g. risk, communication, staffing) into a single, comprehensive Project Management Plan is sometimes more efficient than managing several distinct artifacts; however, it’s not desirable to combine so much content into a single document as to make the document difficult to maintain. «Omit: Use this when a project team determines that the requirements associated with a particular artifact are not applicable to the project. A project must justify its choice to omit an artifact. For example, a project may “omit” the Concept of Operations (CONOPS) artifact if the project is small enough that stakeholders can get a clear picture of the solution based on the descriptions of scope and requirements contained in other artifacts. Also, if the Initial Privacy Assessment (IPA) does not identify and privacy concerns, a project may “omit” the System of Records Notice (SORN) .Use the comment column in the PTA to document the rationale for excluding the artifact. «Refer: Use this when a pre-existing document or system record fully satisfies the requirements associated with the artifact in question and the current project does not cause a need for an update. The “refer” option is most frequently used in connection with security artifacts for projects that are modifications to existing systems. For example, a project that is executing a modification to an existing system may “refer” the Certification and Accreditation memo to a pre-existing record in CSAM that is complete and up-to-date. «Defer: Use this when you will address the requirements associated with the artifact during a future PPM Life Cycle phase rather than during the current Life Cycle phase. Deferring artifacts to future phases is most frequently used when the necessary requirements will be unknown until the activities of the current phase are complete. For example, a project might “Defer” the Solution Architecture document from the Definition Phase to the Design Phase as the completed and approved Risk Adjusted Cost Benefit Analysis of Alternatives (CBA) may be needed to develop the solution architecture on the selected alternative.
D | Category: This is an unlocked field that categorizes the project artifact. The following categories are acceptable: Project Business System N/A (Primarily for Control Gate Reviews)
E | Comments: This is an unlocked field that is used by different groups for different purposes: The IPT uses the comment column to qualify proposed tailoring agreements to refer, combine, or omit artifacts. The PMO uses the comment column to provide additional context and descriptions for ratings given to artifact completeness.
Column | Instructions For Changing the Contents of Drop-Down Menus
Any | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## PTA - Custom Development
PPM V 2.0 |  | Proposed Process Tailoring for Agile Approach
PPM V2.0 Artifact | Tailoring | Equivalent Agile Artifact | Comments
Initiation - Project Validation Review |  | Initiation - Project Validation Review
Project Initiation Form (PIF) | Required | Project Initiation Form (PIF) (same as PPM V2.0) | The PIF is required for all projects. This document references original funding approval and alerts OCIO that the business is ready to begin the approved project. Revise to include team roles (Sponsor, Project Manager, Product Owner, Scrum Master, Team Members)
Planning Phase: Project Tailoring Agreement (PTA) | Required | Project Tailoring Agreement (PTA) (tailored for agile) | Documents the artifacts that will be completed during system development
Planning Phase: Security/Privacy Artifacts |  | Security / Privacy Initial Assessment (PPM V2.0) | Security Assessments http://hudatwork.hud.gov/HUD/cio/po/i/it/security/templates Initial Privacy Assessment is designed to assess whether a Privacy Impact Assessment (PIA) or System of Records Notice (SORN) is required.
|  | Service Layered Architecture Profile (SLAP) | The Project Service Layered Architecture Profile (SLAP) is delivered with specific design constraints and design recommendations for each project. The SLAP is intended to be included in the acquisition package (if applicable).
Project Charter | Required | Program / Project Oversight Plan (POP) | A Project Oversight Plan (POP) applies to the entire program or project and is not specific to a particular release. A POP is only written once for a program or project. The purpose of a POP is to provide transparency to the governing body and other stakeholders, and to specify the management structures that will exist to govern the work to be done. (Addresses Requirements, Communications, and Risk Management, Quality Assurance, Procurement Management, IV&V, etc.)
Project Schedule (WBS) | Required | N/A | Addressed in Critical Task Schedule (See Release Planning)
Procurement Management Plan | May be Applicable | N/A | If applicable, can be addressed in Program / Project Oversight Plan
|  | PVR Briefing Deck | Use the template to capture Program-level content for PVR Gate Review
TRC Control Gate Decision | Required | TRC Program Validation Review | Present Program Validation Review Briefing Deck and associated artifacts
Planning - Project Baseline Review |  | Release Planning
Project Tailoring Agreement (PTA) | Required |  | Moved to Program Validation Phase
Project Management Plan (PMP) | Required | N/A | Addressed in Program Oversight Plan (POP)
Concept of Operations (CONOPS) | Required | N/A | Incorporate key objectives of CONOPS into the Release Planning Review Briefing Deck
Requirements Definition Document | Required | Initial Product / Release Backlog/Stack & User Stories | This will be continuously managed during the release and resubmitted to the TRC at the end of the release, prior to the Release Readiness Review
Requirements Traceability Matrix | Required | N/A | Release Backlog / User Stories and Burn Charts will be maintained throughout Release Readiness
Requirements Management Plan | Required | N/A | Addressed in Program Oversight Plan (POP)
Risk Management Plan (RMP) | May be Applicable | N/A | Addressed in Program Oversight Plan (POP)
Risk Management Log | Required | Risk Management Log (PPM V2.0) | Managed for entire Program and updated during Release Planning & Release Readiness
Quality Assurance Plan | Required | N/A | Addressed in Program Oversight Plan (POP)
Communications Plan |  | N/A | Addressed in Program Oversight Plan (POP) Identified as "Information Radiators"
Independent Verification & Validation Plan (IV&V) |  | N/A | Included in POP.
Solution Architecture |  | N/A | Merged into Architecture and System Design Document in Release Readiness
Security and Privacy Artifacts |  | Security and Privacy Artifacts (PPM V2.0) | These documents are started in Program Validation Phase, and evolve during Release Planning and Release Readiness.
|  | Team Process Agreement | Roles, responsibilities, and accepted practices as well as Definition of Done (criteria which will determine that all development requirements have been satisfied.) Updated during Release Planning based upon Iteration Retrospectives and any new team agreements that have been established since the previous Release.
|  | Critical Task Schedule | Includes high level milestones, critical tasks, Release Planning Review, Release Readiness Review, Deployments, Retrospective, etc.
|  | Capabilities and Constraints | updated during Release Planning
|  | Test and Evaluation Master Plan (TEMP) | The TEMP is at the solution-level and presents the test types, activities, and roles/responsibilities. Specific release-level test plans and the actual results of tests for each Release are recorded in the Test Execution Plan and Results document during Release Readiness.
TRC Control Gate Decision | Required | Release Planning Review (RPR) | Present Release Planning Briefing Deck
Execution & Control - Operational Readiness Review |  | Release Readiness
Technical Design Document (TDD) | Required | Architecture and System Design Document | Includes Descriptions for each Version/Release, - Logical Data Model (ERWin) - Physical Data Model (ERWin) - Business Process Models (As-Is / To-Be) (BPMN 2.0 compliant) - Interface Control Document(s) are included in appendix
Interface Control Document (ICD) | Required | N/A
Change Management Log | Required | N/A | Addressed in management of Release Backlog / User Stories and Burn Chart, maintained throughout Release Readiness
Implementation Plan | Required | Release Deployment Package
Test Pland and Reports | Required | Test Execution Results | Release-specific test plans and actual results of each test conducted during release development.
Data Conversion Plan | Required | Data Conversion Plan (PPM V2.0)
Training Plan | May be Applicable | Training Plan
User Manual | Required | User Manual
Operations and Maintenance (O&M) Manual | Required | Operations and Maintenance (O&M) Manual (PPM V2.0)
Security Artifacts and Privacy Artifacts | Required | Security Artifacts and Privacy Artifacts (PPM V2.0) | These documents begin in Program Validation Phase and evolve during Release Planning and Release Readiness.
Section 508 Compliance / Remediation Plan
|  | Release Addendum (updates to POP) | Successive releases may modify the POP if necessary or may add a Release Addendum for the release. If nothing changes, a Release Addendum is not required. (The Release Addendum is a descritpion of the Version / Release)
|  | HARTS Software Release Request | Deployment Notification
|  | Release Addendum (updates to POP) | An addendum to the POP – This is a summary of the features and controls for the software build. It identifies and describes the version of the software being delivered, including the major changes since the last Release Addendum was issued.
|  | Release Retrospective | See Release Characteristics - what did we learn from this release?
Release Readiness Review Briefing Deck
TRC Control Gate Decision | Required | TRC Release Readiness Review (RRR) | Release Readiness Decisions for each major release, Present Release Readiness Briefing Deck
Close Out - Project Close Out Review |  | Close Out - Project Close Out Review
Project Completion Report | Required | Project Completion Report
TRC Control Gate Decision | Required | TRC Control Gate Decision