## Sheet1
Performance Benchmarks
Grant Number: |  |  | Grantee Organization: | [5 empty] | Period of Performance:
ACTIVITY | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar | Apr - Jun | Jul - Sep | Oct - Dec | Jan - Mar
| 2009 | 2009 | 2009 | 2010 | 2010 | 2010 | 2010 | 2011 | 2011 | 2011 | 2011 | 2012 | 2012 | 2013
Getting Started (0-90 days)
Staff Hired | 60 Days after Award Date
Written Work Plan and Policies and Procedures | 60 Days after Award Date
Approved Environmental Review and Release of Funds | 120 Days after Award Date
Units Made Lead Safe = #
Paint Inspections/Risk Assessments:
Performance Standard |  |  | 5% | 15% | 30% | 45% | 55% | 65% | 75% | 85% | 95% | 100%
Work Plan Milestone
Actual # Completed
Actual % Completed
** Units in Progress
Units Cleared of Hazards:
Performance Standard |  |  | 2% | 5% | 15% | 30% | 45% | 55% | 65% | 85% | 95% | 100%
Work Plan Milestone
Actual # Completed
Actual % Completed
Grant Award Amount Spent (LOCCS) = $
Performance Standard |  | 2% | 5% | 10% | 20% | 30% | 45% | 55% | 65% | 80% | 95% | 100%
LOCCS Drawdown Work Plan Milestone
Actual LOCCS Drawdown
Actual Cumulative LOCCS Drawdown %
Outreach & Education / Training
Community Outreach and Education Goals
Community Outreach and Education Achieved
Training Goals
Training Achieved
LHC/LHRD version
You determine the milestone % to achieve according to your work plan (delete this box)