CHAPTER 10.  MONITORING AND EVALUATION

Section 1.  General

10-1.   INTRODUCTION.  This Chapter sets forth the responsibilities

of the PHA and the Field Office in the monitoring and

evaluation of approved modernization programs.  The

monitoring and evaluation system is comprised of four basic

elements:  (1) fund requisitions; (2) quarterly progress

reports; (3) budget revisions; and (4) on-site inspections.

Its purpose is to provide the PHA and HUD with the means

for determining whether the modernization is progressing in

an efficient and effective manner and, if not, what

corrective actions must be taken.

10-2.   PHA RESPONSIBILITIES.  THE PHA HAS THE PRIMARY MONITORING

AND EVALUATION RESPONSIBILITIES.  THE PHA MUST BE CONCERNED

WITH THE QUALITY OF THE PHYSICAL AND MANAGEMENT IMPROVEMENT

WORK, AS WELL AS WITH MEETING PLANNED FUND

OBLIGATION/EXPENDITURE AND WORK PROGRESS SCHEDULES.  IF

PROPERLY ESTABLISHED AND MAINTAINED, THE SYSTEM WILL ENABLE

THE PHA TO HAVE CURRENT INFORMATION ABOUT THE PROGRESS OF

ITS MODERNIZATION PROGRAM, TEST THE EFFECTIVENESS OF

PARTICULAR ACTIVITIES, TAKE PROMPT ACTION TO REMEDY

DEFICIENCIES, AND CONDUCT ITS OWN EVALUATION OF

*         PROGRAM PERFORMANCE.  FAILURE TO MEET THE DEADLINES

ESTABLISHED BY THE PHA AND APPROVED BY HUD IN THE PROJECT

IMPLEMENTATION SCHEDULE(S) MAY RESULT IN THE RECAPTURE OF

UNOBLIGATED FUNDS AND/OR HUD DETERMINATION THAT THE PHA

LACKS MODERNIZATION CAPABILITY WHICH WILL ADVERSELY AFFECT

FUTURE FUNDING.  SEE PARAGRAPH 9-14 REGARDING PHA         *

RESPONSIBILITIES FOR CONSTRUCTION CONTRACT ADMINISTRATION.

10-3.   HUD RESPONSIBILITIES.  The Field Office shall ensure that

PHAs are carrying out their modernization programs in

accordance with HUD-approved plans and schedules and

applicable laws and regulations.  The Field Office is

responsible for monitoring, but not inspecting approved

programs.  See paragraph 9-15 regarding Field Office

responsibilities for construction contract administration.

The Field Office shall help PHAs to identify problems or

potential problems in program implementation, as well as

their causes, and to correct them.  The Field Office shall

determine whether PHAs have a continuing capacity to carry

out approved modernization programs and to implement

additional modernization programs for which they may apply.

The Modernization Coordinator is responsible for developing

an overall plan and timetable for monitoring and evaluating

modernization programs.  In

10-1                            12/89

_____________________________________________________________________

*         addition, the FHEO Division is responsible for monitoring

on matters related to civil rights and equal opportunity.

The CPD Division is responsible for monitoring relocation

and acquisition requirements in accordance with paragraph

6-7.  The Labor Relations staff is responsible for

monitoring on labor standards compliance.

Section 2.  Fund Requisitions

10-4.   GENERAL.  The PHA shall submit and the Field Office shall

review fund requisitions in accordance with the

requirements of the Rapid Housing Payment System (RHPS), as

set forth in various HUD Notices.                         *

Section 3.  Quarterly Progress Reports

10-5.   PHA SUBMISSION.

a.   Form HUD-52826, Schedule/Report of Modernization

Expenditures.

(1)  Purpose.  The purpose of Form HUD-52826,

Schedule/Report of Modernization Expenditures, is

to provide the PHA with a systematic method for

recording and reporting its actual expenditures

and for determining the current status of its

program.

(2)  PHA Preparation.  Complete instructions for the

preparation of Form HUD-52826 are contained in

*                   Appendix 17.  The PHA shall enter the type of

modernization (emergency, nondiscrimination,

comprehensive, special purpose or homeownership)*

for each project listed in Column (A) of Part I.

The PHA shall report its progress against the

Project Implementation Schedule for each project

in Column (H), "Comments", of Part I.

(3)  PHA Submission.  The PHA shall submit Form

HUD-52826 to the Field Office, Attention:  Chief,

AHMB, in an original and two copies (or any

lesser number of copies as specified by the Field

*                   Office), no later than 45 calendar days after the

end of a quarter.  The first report is due 45

calendar days after the end of the quarter in

which the ACC amendment was executed.  The PHA  *

shall continue to submit the report until the

modernization program has been completed.  When

no further CIAP funds will be expended for a

particular project included in

12/89                                10-2

_____________________________________________________________________

the Modernization Project, the PHA shall enter

the letter "C" on the appropriate line of Part I

of the form, indicating that it will be the last

quarterly progress report submitted for that

project.

b.   Narrative Report on Management Improvement Progress.

Where management improvements are included in the

comprehensive modernization of a project, the PHA

shall submit a quarterly narrative report, describing

the current status of each management work item set

forth on Form HUD-52825, Comprehensive

Assessment/Program Budget, including the numerical

status where the performance goal was quantified.  The

PHA also shall describe any actions taken during the

quarter toward accomplishment of the goal and explain

any lack of progress or actions.

10-6.   HUD REVIEW AND ACTION.  The Field Office shall take the

following actions:

a.   Follow-up for Timely Receipt.  The AHMB shall maintain

a log of quarterly progress reports received.  The HMS

shall routinely telephone delinquent PHAs to remind

them that their quarterly reports are overdue.  No PHA

fund requisitions shall be processed until the latest

required progress reports have been received and

reviewed, unless the first required reports are not

yet due.

*         b.   Review.  Within 65 calendar days after the end of the

quarter, the HMS and the General Engineer shall

promptly review the quarterly progress reports for

completeness and accuracy, and against the latest

approved Project Implementation Schedule(s), the

latest approved budget and prior approved fund       *

requisitions.  The HMS and the General Engineer shall

review the adequacy of the PHA's explanation of any

lack of progress and the appropriateness of the PHA's

planned or actual corrective action.  The HMS also

shall determine if Form HUD-52826 has been correctly

*              filled out.  Such reviews shall be documented.  The

HMS shall request FHEO review and written comment

where there are physical and management improvements

relating to equal opportunity.                       *

c.   Action.  If the HMS or the General Engineer finds the

quarterly progress reports to be satisfactory, the HMS

or the General Engineer shall so indicate on the

documentation.  If the HMS or the General Engineer

10-3                            12/89

_____________________________________________________________________

finds the quarterly progress reports to be incomplete,

inaccurate or inadequate, the HMS or the General

Engineer shall take all necessary steps, in writing,

by telephone, or by personal visit, to reach mutual

agreement with the PHA on corrective action.  The HMS

or the General Engineer shall document any follow-up

actions taken, as well as the PHA responses, on the

documentation.  The HMS shall consult with the General

Engineer on the need for additional on-site

inspections if the progress reports indicate serious

problems.

* 10-7.   MODERNIZATION QUARTERLY REPORTING SYSTEM (MQRS).  MQRS is a

HUD microcomputer system, which provides information on PHA

progress in implementing approved modernization programs

and can be summarized at the Field, Regional and National

levels.

a.   Field Office Summary and Exception Reports.

(1)  The Field Office shall consolidate all Forms

HUD-52826 into a Field Office Summary Report on

the status of all CIAP funds approved after FFY

1974.  Where a PHA does not submit its report(s),

the Field Office shall use the PHA's report(s)

from the previous quarter and shall not approve

any fund requisitions.  The Field Office shall

include all funds reserved in a particular FFY;

i.e., funds for incomplete as well as completed

programs.

(2)  The Field Office also shall prepare a Field

Office Exception Report showing, for each project

with unobligated funds after the original fund

obligation deadline date in the approved Project

Implementation Schedule, the approved time

extension date for fund obligation, if any, or

the funds identified for recapture, and comments.

(3)  The Field Office shall forward its Summary and

Exception Reports to the Regional Public Housing

Director, within 65 calendar days after the end

of each quarter.

b.   Field Office Fiscal Closeout Report.  This

MQRS-generated report tracks the fiscal closeout steps

as required in Chapter 12.  The Field Office also

shall forward this report to the Region.             *

12/89                                10-4

_____________________________________________________________________

c.   Regional Office Summary Report.

(1)  The Regional Office shall consolidate the Field

Office Summary Reports into a Regional Office

Summary Report on the status of all CIAP funds

approved after FFY 1974.

(2)  The Regional Office shall forward its Summary

Report, along with the Field Office Summary and

Exception Reports, to Headquarters, Director,

Office of Public Housing, Attention:  Project

*                   Management Division, within 75 calendar days

after the end of each quarter.

10-8.   TIME EXTENSIONS AND USE OF LEFTOVER FUNDS.

a.   Funds Obligated.  "Funds obligated" means the

cumulative amount of modernization commitments entered

into by the PHA; i.e., contract execution for contract

labor, materials or services; start and continuation

of work for force account labor; and appropriate

charging of administrative costs.  Contract execution

means execution of the contract by both the

contractor and the PHA.  For force account work, all

funds for a group of sequentially-related work items

are considered obligated when the first work item is

started, such as roof insulation followed by roof

replacement, but only where funds continue to be

expended at a reasonable rate (see paragraph 10-9).

However, when one work item is started and is not

sequentially related to other work items, such as

window replacement and kitchen remodeling, then only

the funds for the one work item started are considered

obligated.

b.   Original HUD-Approved Project Implementation

Schedules.  Following CIAP Application approval, the

Field Office approves in the Schedule a

PHA-established fund obligation deadline for each

project (see paragraph 7-2).  The PHA may continue to

obligate funds up to the deadline approved in the

original Schedule, without requesting a time

extension.

c.   Valid Requests and Approval Authority.  The PHA may

request, and HUD may approve, a time extension of the

fund obligation deadline, as set forth in its

originally approved Project Implementation Schedule,

based on a valid reason.  These valid reasons and the

level of HUD approval authority are summarized       *

below:

10-5                            12/89

_____________________________________________________________________

*                                                     HUD Approval

Valid Reason                           Authority

Delay related to lead-based paint      Field Office/

testing and abatement                  OIP Manager

Need to use leftover funds from

completed modernization program to

fund emergency, special purpose,

or homeownership modernization,

supplement comprehensive

modernization in progress, or          Field Office/

fund comprehensive completed           OIP Manager

Unforeseen delays in contracting       Field Manager

or contract administration             OIP Manager

Litigation                             Field Office/

OIP Manager

HUD or other institutional delay       Regional

Administrator

d.   Troubled PHAs.  All time extension requests from large

non-Indian PHAs, which have been designated as

Troubled under Handbook 7460.7 REV-1 and which the

Field Office recommends for approval, shall be

forwarded to the Regional Office for review and

decision.

e.   Right to Review.  Headquarters reserves the right to

require Headquarters review and decision on any PHA

which, due to special circumstances, warrants

Headquarters' level of attention.

f.   PHA Requests.  Before the fund obligation deadline for

a project, the PHA may submit to the Field Office a

time extension request based on any of the valid

reasons set forth in subparagraph c.  The request

shall include the following information:

Modernization Project Number and individual project

number; FFY in which the funds were reserved; type of

modernization; total funds reserved by HUD for the

project; total funds obligated and unobligated for the

project to date; requested extension date (date by

which all funds will be obligated) and why the

specific length of time is necessary; and            *

12/89                                10-6

_____________________________________________________________________

*              narrative statement explaining why the project should

be granted a time extension, based on the one of the

following valid reasons:

(1)  For delay related to lead-based paint, explain

how fund obligation was delayed by the random

testing results which indicated the need for 100

percent testing or other testing or abatement

delays.

(2)  For need to use leftover (unobligated) funds,

justify the work item(s) (under the appropriate

type of modernization.

(3)  For unforeseen delays in contracting or contract

administration, explain if there is a need to

issue a change order which will increase the

contract price; if so, explain why the change

order and its cost.  When this situation occurs,

the funds for the contract have been obligated on

or before the fund obligation deadline, but there

are leftover funds which are unobligated and,

therefore, identified for recapture.  Such

leftover funds may be used to pay for a necessary

change order.  Alternatively, explain if there is

a need to rebid the contract, such as all bids

received were over budget or only a single bid

was received; if so, explain how long it will

take to revise the plans and specifications and

why.

(4)  For litigation, explain what the litigation

involved, how it delayed fund obligation, when it

was initiated, and when it ended or is

anticipated to end.  If the litigation has not

yet ended, the extension date requested shall be

in terms of days or months after settlement, such

as "30 calendar days after settlement."  Any time

extension based on litigation must reflect actual

legal proceedings in court, not the threat of

such proceedings.

(5)  For HUD or other institutional delay, such as the

local utility company or local government,

explain the nature and length of the delay.  Any

time extension based on HUD or other

institutional delay must be in direct proportion

to the delayed response.  Delay by              *

10-7                            12/89

_____________________________________________________________________

*                   the PHA Board of Commissioners does not

constitute a valid other institutional delay.

g.   HUD Review and Action.  The PHA's time extension

request will be reviewed by the Field Office.  Where

the Field Office has approval authority, it also has

disapproval authority.  Where the Field Office does

not have approval authority, it shall forward the

request, with its recommendation, to the Regional

Office for decision.

(1)  Where the time extension request is approved, the

PHA shall submit a revised Project Implementation

Schedule showing the extension date as the date

when all funds will be obligated for the project.

If leftover funds are to be used at a new

project, the requirements of paragraph 10-14b

shall be met and the PHA shall submit any

documents required under paragraph 3-6 for the

CIAP Application.

(2)  Where the time extension request is disapproved

or the PHA fails to request a time extension and

there are unobligated funds after the fund

obligation deadline, the PHA is in Substantial

Breach of its ACC since it has failed to

prosecute diligently or proceed with the timely

modernization of the project, as provided in

Section 507(5) of the ACC.  Accordingly, the PHA

shall not obligate any additional funds since the

unobligated funds will be recaptured after audit

and fiscal closeout of the Modernization Project.

The Field Office shall not process fund

requisitions for obligations which are incurred

after the original fund obligation deadline or

the revised deadline where the PHA had an

approved time extension.

10-9.   FUND EXPENDITURES.  Although the time extension policy does

not address a deadline for fund expenditure, HUD is

concerned that, in some cases after fund obligation, funds

are not being expended in a timely manner.  See paragraph

3-7a(1)(a) regarding, beginning in FFY 1991, PHAs with

prior approved, unexpended funds (unless                  *

12/89                                10-8

_____________________________________________________________________

*         leftover from completed modernization) after the deadline

date for program completion, as set forth in the latest

HUD-approved Project Implementation Schedule, being

eligible only for modernization under Group 1.

a.   Contract Labor.  Where funds have been obligated

through execution of a contract and partial payments

are necessary, the PHA shall require the contractor to

prepare a construction progress schedule and a

schedule of amounts for contract payments.  These

documents should be consistent with the approved

Project Implementation Schedule.  The PHA is

responsible for making progress payments to the

contractor based on the PHA-approved payment schedule.

If the quarterly progress reports show that funds

expended are not increasing from quarter to quarter at

a rate that would allow completion within the time

frame set forth in the Project Implementation

Schedule, the Field Office shall review the PHA to

determine that payments are being made on the basis of

the payment schedule and that the payment schedule and

construction progress schedule are reasonable.  Where

deficiencies are found, future funding will be

adversely affected.

b.   Force Account Labor.  Where funds have been obligated

through start of force account labor work, the PHA is

expected to show reasonable progress through

increasing fund expenditures each quarter at a rate

which would allow completion within the time frame set

forth in the Project Implementation Schedule.  Where

this is not the case, the Field Office shall review

the force account work to determine the facts,

including whether the previously reported fund

obligation was overstated.  Where deficiencies are

found, future funding will be adversely affected.

Section 4.  Budget Revisions

10-10.  TOTAL FUNDING LIMITATION.  The PHA shall not incur any CIAP

cost in excess of the total approved program budget.  HUD

will not approve additional funds to cover any excess cost.

10-11.  HUD-ESTABLISHED THRESHOLD.  Based on an assessment of the

PHA's past performance in preparing budget revisions and

in-house technical capability, the Field Office may

establish a dollar threshold over which the               *

10-9                            12/89

_____________________________________________________________________

*         PHA shall submit budget revisions for prior Field Office

review and approval.

a.   Criteria.  In determining the appropriate dollar

threshold for PHA submission, the HMS, in coordination

with the General Engineer, shall consider the

following criteria:

(1)  Past Performance in Preparing Revisions.  In the

past the budget revisions were necessary to carry

out the approved work.

(2)  In-House Technical Capability.  The PHA has

experienced staff who are capable of reviewing

budget revisions and ensuring that the approved

budget amount for any project is not exceeded.

b.   Notification to PHA.  After completing the assessment,

the HMS shall notify the PHA of the established dollar

threshold over which budget revisions are required to

be submitted for prior Field Office approval and the

reasons.  This notification shall be included in the

letter to the PHA approving the CIAP application.

10-12.  PHA CERTIFICATION.

a.   PHAs with Thresholds.  The PHA shall revise the budget

to delete or substantially revise approved work items,

add new work items, or incur CIAP costs in excess of

the approved budget amount for any work item without

prior Field Office review and approval, unless the

budget revision (1) exceeds the dollar threshold that

has been established by the Field Office (see

paragraphs 7-1 and 10-11), (2) incurs costs in excess

of the approved budget amount for any project, or (3)

changes the method of accomplishment from contract to

force account labor.  Where HUD approval is not

required, the designated PHA official shall certify in

writing to the following and send a copy of the

certification and the informal or formal budget

revision to the Field Office:

(1)  The revision is necessary to carry out the

approved work;

(2)  The revision does not result in the approved

budget amount for any project being exceeded;

and                                             *

12/89                                10-10

_____________________________________________________________________

*              (3)  The revision does not change the method of

accomplishment from contract to force account

labor.

b.   Recognized Performers.  For alternative requirements

for recognized non-Indian performers, as defined in

Chapter 11 of the Field Office Monitoring of PHAs

Handbook 7460.7 REV-1, refer to that Handbook.       *

10-13.  HUD REVIEW AND APPROVAL.

a.   Type of Revision.

(1)  Informal Revision.  If the proposed revision will

have little effect on the overall modernization

program, the PHA may submit a written request for

an informal budget revision to the Field Office

without revising the entire budget.

(2)  Formal Revision.  If the proposed revision is

major or when a combination of several approved

informal revisions has resulted in substantial

differences between the budget and actual

implementation, the PHA shall submit a formal

revision of the entire budget.  Also, the PHA

shall submit a Board Resolution, approving a

major revision, where appropriate.

b.   Review and Approval.  Where submitted by the PHA, the

HMS shall coordinate the prompt review of all informal

and formal budget revisions.  Such review shall be

documented and shall include the General Engineer and

other Field Office staff, as appropriate.  Within 10

working days of receipt, the HMS shall prepare a

letter to the PHA for the signature of the Director,

Housing Management Division or designee, indicating

approval, with or without modification, or

disapproval.

*         c.   Monitoring.  The HMS shall periodically review PHA

budget revisions not approved by HUD to ensure that

the PHA is meeting the criteria set forth in paragraph

10-11a.  If deficiencies are found, the Field Office

monitoring letter (see paragraph 10-17a(3)) may

require the PHA to submit budget revisions over a

reduced threshold to the Field Office for review and

approval before adoption.                            *

10-11                           12/89

_____________________________________________________________________

10-14.  OFFSETS BETWEEN WORK ITEMS OR PROJECTS.  If the PHA plans

to offset any increase in CIAP cost for one or more other

work items, the following conditions shall apply to

modernization programs approved after implementation of

modernization as a separate project (on or after July 1,

1978 and under CIAP):

a.   If the offset involves work items in the same project

or different projects that were included in the

original Modernization Project ACC amendment, the

budget shall be revised.  No revised Form HUD-52540 or

HUD-52541, Project Accounting Data, or ACC amendment

is required.

b.   If the offset involves the addition of a project that

was not included in the original Modernization

*              Project ACC amendment or deletion of a project that

was originally included, the budget shall be revised,

regardless of the PHA's threshold.  The Field Office

shall prepare a revised ACC amendment (Forms HUD-53009

or 53008 for loans or Forms HUD-53009A, B, C, or D   *

for grants).  No revised Form HUD-52540 or HUD-52541

is required.

c.   The project being added must be under the same

consolidated ACC as the other projects originally

included the Modernization Project, with the following

exception.  Only Section 23 Leased Housing

Bond-Financed Projects (BFPs) may be added to a

Modernization Project composed exclusively of BFPs and

only non-BFP projects may be added to a Modernization

Project composed exclusively of non-BFPs.  If a BFP is

being added to a 985 Modernization Project, the BFP

must meet the requirements of paragraph 4-9.

d.   For the project being added to a Modernization Project

approved after FFY 1980, the PHA shall submit any

document required under paragraph 3-6 for the CIAP

Application.

Section 5.  On-Site Inspections

10-15.  INSPECTIONS BY PHA.  The PHA shall provide, by contract or

otherwise, adequate and competent supervisory and

inspection personnel during modernization, whether the work

is performed by contract or force account labor and with or

without the services of an architect/engineer.  Whether

inspections are performed by an architect/engineer or an

independent contractor, THE PHA SHALL HAVE THE FINAL

RESPONSIBILITY FOR ENSURING

12/89                                10-12

_____________________________________________________________________

*         WORK QUALITY AND PROGRESS.  PHA failure to provide adequate

inspections is evidence of lack of modernization capability

and will adversely affect future funding.  The PHA shall  *

state its plans for periodic inspections of the

modernization work in the Modernization Organization and

Staffing Plan, submitted as part of the CIAP Application.

Before HUD approval of the CIAP Application, the Field

Office and the PHA shall mutually determine in writing the

number, type, qualifications and salaries of inspection

personnel required.

10-16.  INSPECTIONS BY ARCHITECT/ENGINEER.  If the PHA is planning

to hire an architect/engineer for certain modernization

work, the PHA may modify the standard provisions of Form

HUD-51915, concerning the services to be rendered during

modernization (see paragraph 8-3).

10-17.  MONITORING BY HUD.  The Field Office shall periodically

visit the PHA to examine records and review implementation

of physical and management improvements.  In addition, the

Regional FHEO Compliance Division shall conduct compliance

reviews and complaint investigations related to civil

rights statutes, executive orders and regulations.

a.   Work in Progress.

*              (1)  Frequency.  After construction has started, the

General Engineer shall visit the PHA and project

site(s) at least four times a year for

comprehensive modernization and at least twice a

year for other modernization types.  The HMS

shall visit the PHA at least twice a year where

there are management improvements.  These

frequencies are management goals, for which

Headquarters may grant relief due to inadequate

staff and travel resources.  The FHEO staff shall

visit the PHA at least once a year where there

are equal opportunity-related physical or

management improvements.  More frequent

monitoring visits shall be made if the scope of

the rehabilitation is substantial (exceeds

$10,000 per unit) or if serious problems or

deficiencies are identified in previous

inspections or from review of the quarterly

progress reports, budget revisions or fund

requisitions.

(2)  Checklist.  The General Engineer and the HMS

shall review the PHA's program during           *

10-13                           12/89

_____________________________________________________________________

implementation, using the Monitoring Checklist in

Appendix 18.  The General Engineer and the HMS

may add data elements, as appropriate.  The

General Engineer and the HMS shall discuss any

adverse findings with the PHA and include them in

the monitoring letter.

(3)  Monitoring Letter.  After each on-site

inspection, the Field Office representative shall

prepare a monitoring letter to the PHA, setting

forth the modernization program(s) monitored,

Field Office staff who monitored and date of

visit, scope of monitoring, monitoring

conclusions (both positive and negative),

specific corrective action required, if any, due

date of corrective action, and offer of technical

assistance, if appropriate.  When the monitoring

visit is a team visit, a single letter should be

sent to the PHA.  In no case should the time

*                   between the visit and the date of the letter

exceed 30 calendar days.  The non-Indian Field

Office shall send a copy of the monitoring letter

to the Regional Public Housing Director.  Where

appropriate, the Field Office representative also

shall prepare a trip report for AHMB files to

record additional background information which

was not included in the monitoring letter.      *

b.   Construction Contract Completion.  Under Section 5 of

Chapter 9, the PHA is required to notify the Field

Office of the scheduled final inspection.  The General

Engineer shall participate in the final inspection

cost exceeds $10,000 to ensure that all physical work

has been completed in accordance with contract

requirements and is of acceptable quality (see

paragraph 9-29).  As appropriate, the HMS and other

staff also shall participate.  In addition, the review

shall evaluate the following program aspects:  (1) the

success of the PHA in implementing the management

improvements; (2) the PHA's administration of the

modernization program; (3) the success and adequacy of

the physical work as outlined by the

architect/engineer; and (4) the adequacy of any work

performed by force account labor.  The Field Office

representatives shall prepare a final monitoring

letter under subparagraph a(3).

12/89                                10-14

_____________________________________________________________________

Section 6.  Corrective Action

10-18.  HUD FOLLOW-UP.  The Field Office AHMB shall take the

following appropriate action to follow-up with the PHA on

any corrective action required by the Field Office's

monitoring letter (see paragraph 10-17a(3)):

a.   If the PHA fails to meet a target date for corrective

action, the General Engineer or the HMS shall

follow-up with a telephone call or written reminder.

b.   If the PHA has not responded within 30 calendar days

after the date the PHA was required to take corrective

action, the General Engineer or the HMS shall prepare

*              a letter to the PHA for the signature of the Field

Office Manager or designee.  Where the corrective

action involves equal opportunity-related physical or

management improvements, the FHEO Division shall     *

concur in the letter.  The letter shall request the

status of the required action and warn the PHA of the

consequences of failure to comply, as set forth in

paragraph 10-19.

*         c.   The General Engineer or the HMS, and the FHEO

representative, as appropriate, shall review the     *

PHA's proposed corrective action.  If the reviews

indicate that the action is less than satisfactory,

the General Engineer or the HMS shall prepare a letter

to the PHA for the signature of the Field Office

Manager or designee.  The letter shall specify needed

additional action and the due date.

d.   The Field Office may establish a new due date, subject

to good faith efforts by the PHA to correct the

deficiency.  The Field Office may conduct a follow-up

visit to verify corrective action taken or to provide

technical assistance where the PHA has been unable to

correct the deficiency.

e.   Where the PHA fails to make good faith efforts to

correct the deficiencies, the Field Office shall

notify the PHA Board of Commissioners and request a

meeting.

10-19.  HUD ACTION.  Where the PHA is unable to correct an

identified deficiency, such as lack of progress,

noncompliance with applicable laws and regulations, and

lack of continuing capacity, the Field Office shall

10-15                           12/89

_____________________________________________________________________

notify the PHA in writing of its intent to take one or more

of the following actions:

a.   Impose additional requirements for PHA submission of

contracting documents for prior HUD review and

approval under Chapter 9.

b.   Disapprove any new application for CIAP funds or limit

any new application to emergency modernization.

c.   Terminate all or part of the approved modernization

program.  In such case, the letter shall direct the

PHA not to incur additional cost for the terminated

program unless the Field Office specifically approves

the additional cost.  In terminating a partially

completed program, the Field Office shall consider

what physical work is already underway, the amount of

funds previously provided for that work, and the

amount of additional funds needed to complete that

work, including the PHA's outstanding contractual

obligations.  In such case, the Field Office shall

reduce all HUD-established thresholds to zero, thereby

requiring prior HUD approval.  Termination of an

approved program that is under ACC must be based on a

declaration of substantial breach of default.  See

Chapter 11 regarding the recapture of modernization

funds and Chapter 12 regarding the fiscal closeout of

modernization programs.

d.   Initiate action to find the PHA in substantial default

or breach of the terms and conditions of the ACC in

order to invoke the remedies under the ACC, including

notification to the Depositary Bank not to honor any

further withdrawals from the General Fund bank account

without prior HUD authorization.

12/89                                10-16

_____________________________________________________________________