CHAPTER 11.  CANCELLATION/RECAPTURE OF CIAP FUNDS

11-1.   INTRODUCTION.  This Chapter provides instructions to the

Field Office on the cancellation or recapture of CIAP

funds.  These instructions are consistent with those

contained in Chapter VI of Handbook 1970.41, Low-Income

Housing Program: Procedures for Accounting, Recording, and

Reporting Budget Authority.

11-2.   DEFINITIONS.

a.   Cancellation.  The deobligation of all or part of the

budget authority approved during the current FFY.

b.   Recapture.  The deobligation of all or part of the

contract, loan and budget authority approved in FFY

1986 or prior years for modernization loans or all or

part of the grant budget authority approved during any

previous FFY, beginning with FFY 1987.

c.   Reuse.  The reobligation of budget authority

previously cancelled or recaptured, where the budget

authority was approved after modernization as a

separate project (on or after July 1, 1978).

11-3.   CURRENT FISCAL YEAR CANCELLATIONS.  The Field Office may

cancel and reuse any current FFY budget authority, as

follows:

a.   ACC Not Amended.  If Form HUD-52541, Project

Accounting Data (PAD), has been approved and the fund

reservation has been recorded in the Program

Accounting System (PAS) by the Regional Accounting

Division (RAD), but the ACC has not yet been amended,

the Field Office may cancel the budget authority

reserved by preparing and signing a revised PAD and

the PHA disapproval letter.  The Housing Management

Specialist (HMS) shall immediately notify Regional or

Chief Counsel to stop processing the ACC amendment for

the original PAD.  The Field Office shall distribute

the revised PAD and the PHA disapproval letter in

accordance with paragraph 4-6.  As soon as the RAD

records the cancellation, the Field Office may reuse

the cancelled budget authority.  The Field Office must

reuse the cancelled budget authority by the end of the

current FFY or the cancelled budget authority will be

returned to RAD and treated as recaptured funds in the

subsequent FFY.

11-1                            12/89

_____________________________________________________________________

b.   ACC Amended, No Funds Advanced.  If, during a current

FFY, the PAD has been approved, the fund reservation

has been recorded in PAS by the RAD, and the ACC has

been amended, but no funds have been advanced, the

Field Office shall prepare and sign a revised PAD, the

disapproval letter to the PHA, and Form HUD-53001,

Actual Modernization Cost Certificate (AMCC),

indicating that no funds were advanced by HUD.  The

Field Office then shall distribute the revised PAD,

the PHA disapproval letter, and the AMCC at the same

time in accordance with paragraphs 4-6 and 12-6.  The

AMCC shall be attached to the ACC amendment and shall

be deemed to further amend the ACC.  Upon receipt of

the documents, the RAD will record the cancellation

and treat the budget authority as recaptured funds in

the subsequent FFY.

11-4.   PRIOR FISCAL YEAR RECAPTURES.  Prior FFY recaptures will

occur when the Field Office is terminating all or part of

the PHA's modernization program before completion or is

recapturing unobligated funds after completion of the PHA's

modernization program.  See Chapter 12 for procedures for

fiscal closeout, including recapture, where the ACC has

been amended and funds have been advanced.

a.   ACC Not Amended.  If the PAD has been approved and the

fund reservation has been recorded in PAS (FFY 1987

and subsequent year funds) or the Assisted Housing

Accounting System (AHAS) (FFY 1986 and prior year

funds), but the ACC has not yet been amended, the

Field Office shall prepare and sign a revised PAD and

the PHA disapproval letter.  For funds reserved in FFY

1987 and subsequent years, the Field Office shall use

the 2/87 version of the PAD (Form HUD-52541); for

funds reserved in FFY 1986 and prior years, the Field

Office shall use the 11/85 version of the PAD (Form

HUD-52540).  The HMS shall immediately notify Counsel

to stop processing the ACC amendment for the original

PAD.  The Field Office shall distribute the revised

PAD and the PHA disapproval letter in accordance with

paragraph 4-6.  Upon receipt of the documents, the RAD

will record the recapture in PAS or AHAS.

b.   ACC Amended, No Funds Advanced.  If the ACC has been

amended, but no funds have been advanced, the Field

Office shall prepare and sign a revised PAD, the PHA

*              disapproval letter, and Form HUD-53001, Actual

Modernization Cost Certificate (AMCC), indicating    *

that no funds were advanced by HUD.  The Field Office

then shall distribute the revised PAD, the PHA

disapproval

12/89                                11-2

_____________________________________________________________________

letter, and the AMCC at the same time in accordance

with paragraphs 4-6 and 12-6.  The AMCC shall be

attached to the ACC amendment and shall be deemed to

further amend the ACC.  Upon receipt of the documents,

the RAD will record the recapture in PAS or AHAS.

c.   ACC Amended, Funds Advanced.  See Chapter 12.

11-3                            12/89

_____________________________________________________________________