CHAPTER 9.  PROCUREMENT AND CONTRACT ADMINISTRATION

Section 1.  General

* 9-1.   INTRODUCTION.  This Chapter sets forth the requirements for

CIAP-funded procurement, which includes small purchases,

construction and equipment contracts, and professional

services other than architectural/engineering.  These

requirements are consistent with the Uniform Administrative

Requirements for Grants and Cooperative Agreements to State

and Local Governments, as set forth in 24 CFR 85.36, except

as specified in 24 CFR 968.240.  See Appendix 15 for 24 CFR

85.36, Procurement, and 85.37, Subgrants.

9-2.   METHODS OF PROCUREMENT.  There are five types of allowable

procurement, as follows:

a.  Small Purchase Procedures.  Small purchase procedures

are those relatively simple and informal procurement

methods for securing services, supplies, or other

property that do not cost more than $25,000 in the

aggregate.  The PHA shall obtain either oral or written

price or rate quotations from an adequate number (at

least three) of qualified sources, keep a written record

of the quotations, make a documented selection based on

price and other factors, and issue a purchase order to

bind the agreement.  The PHA shall not break down larger

contracts into smaller amounts to circumvent sealed bid

procurement.  If small purchase procedures are used for

construction contracts with dollar values exceeding the

following thresholds, the PHA shall use Form HUD-5370,

General Conditions, and the appropriate wage rate form:

(1)   For construction work over $2,000 and subject to

Davis-Bacon wage rates, use Form HUD-52554,

Supplement to the General Conditions of the

Contract for Construction; or

(2)   For construction work over $10,000 and subject to

HUD-determined wage rates, use Form HUD-5370A,

Supplementary Conditions of the Contract for

Construction (Nonroutine Maintenance).

b.  Sealed Bids (Formal Advertising).  Bids are publicly

solicited and a firm-fixed-price contract (lump sum or

unit price) is awarded to the responsible bidder whose

bid, conforming with all the material terms and

conditions of the invitation for bids, is the lowest in

price.  See Sections 2 through 5 of this Chapter.      *

9-1                            12/89

_____________________________________________________________________

*            Sealed bids are required for construction and equipment

contracts over $25,000, except for procurement under

noncompetitive proposals or the Consolidated Supply

Program (CSP), unless a lower threshold is required by

by State or local law or the PHA's own procurement

policy.

c.  Competitive Proposals.  This procurement is generally

used when conditions are not appropriate for sealed

bids; i.e., there is not a complete, adequate and

realistic specification or purchase description

available and selection of the successful bidder cannot

be made principally on the basis of price.  See Section

6 of this Chapter.

d.  Noncompetitive Proposals.  This procurement may be used

only when the award of a contract is infeasible under

small purchase procedures, sealed bids or competitive

proposals and one of the following circumstances

applies:  (1) the item is available only from a single

source; (2) the public exigency or emergency for the

requirement will not permit a delay resulting from

competitive solicitation; (3) the Field Office

authorizes the noncompetitive proposals; or (4) after

solicitation of a number of sources, competition is

determined inadequate.

e.  CSP.  Refer to the CSP Handbook 7460.9.

9-3.     PROCUREMENT REQUIREMENTS.

a.  Procurement Standards.  See 24 CFR 85.36(b) in Appendix

15.

b.  Competition.  See 24 CFR 85.36(c) in Appendix 15.

c.  Contract Cost and Price.  See 24 CFR 85.36(f) in

Appendix 15.

Section 2.  Bid Advertisement

9-4.     PHA PREPARATION.  The PHA shall prepare the construction and

bid documents as follows:

a.  General.  The PHA and its architect shall ensure that

the construction and bid documents comply with State,

tribal or local laws governing the public solicitation

of bids.  Any modifications required to comply with such

laws should be discussed with Regional or Chief Counsel

to ensure that such changes are not in conflict        *

12/89                                 9-2

_____________________________________________________________________

*            with Federal requirements.  Where there is a conflict

between State or tribal and Federal prevailing wage

laws, the PHA shall follow the procedures set forth in

paragraph 6-9f.

b.  Invitation for Bids.  The invitation for bids shall be

prepared in the form prescribed by the Field Office,

include any specifications and pertinent attachments,

and define the items or services for the bidder to

properly respond.  The bid acceptance period shall be

specified and the bidders shall be informed that the PHA

reserves the right to reject any or all bids received.

c.  Instructions to Bidders.  Form HUD-5369, Instructions to

Bidders, shall be used to inform interested bidders of

the general bidding requirements, the responsibilities

of each party, and the factors to be considered in

determining the successful bidder.  The $25,000

threshold is a Federal requirement and may be lower as

required by State or local law or the PHA's own

procurement policy.  Form HUD-5369 shall be modified to

include the requirement that any contractor awarded a

contract for modernization shall comply with 24 CFR Part

35 prohibiting the use of lead-based paint.            *

d.  Previous Participation Certificate.  For all

construction contracts (excluding CSP contracts) over

$50,000, the bidder shall be required to submit with the

bid, Form HUD-2530, Previous Participation Certificate.

If the Certificate is not submitted by the low bidder

with the bid, the PHA shall require submission within 3

working days.  If the Certificate is submitted after

that date, the bid shall be considered non-responsive

and rejected, and the contract may be awarded to the

second low bidder.  No contract award shall be made

without a properly executed Certificate.

e.  Bid Guarantee.  For all construction and equipment

contracts (excluding CSP contracts) over $25,000, the

bidder shall be required to submit with the bid a

negotiable bid guarantee not less than 5 percent of the

amount of the bid.  The bid guarantee is to assure that

the bidder will, upon acceptance of his/her bid, execute

the contractual documents as required within the time

specified.  The bid guarantee shall he a certified

check, bank draft, U. S. Government Bonds at par value

or a bid bond secured by a surety company.  The surety

company must be authorized to do business in

9-3                            12/89

_____________________________________________________________________

the State where the project is located and must be

acceptable to the Government (see subparagraph g(1)).

If the bid guarantee is not submitted with the

*            bid, the PHA shall reject the bid.                     *

f.  Non-Collusive Affidavit.  For all construction and

equipment contracts (excluding CSP contracts) over

$25,000, the bidder shall be required to submit with the

bid a non-collusive affidavit.  If the affidavit is not

submitted by the low bidder with the bid, the PHA shall

require submission within 3 working days.  If the

affidavit is submitted after that date, the bid shall be

considered non-responsive and and rejected and the

contract may be awarded to the second low bidder.  No

contract award shall be made without a properly executed

non-collusive affidavit.

g.  Assurance of Completion.  For all construction and

equipment contracts (including CSP contracts) over

$25,000, the contractor shall be required to furnish a

performance and payment bond for 100 percent of the

contract price or, as may be required by law, separate

performance and payment bonds, each for 50 percent or

more of the contract price, or a 20 percent cash escrow

or a 25 percent irrevocable letter of credit.  To the

extent permitted under State law, all three options

shall be set forth in the bid documents.

(1)   The surety must be a guarantee or surety company

acceptable to the Government.  Individual sureties

shall not be considered.  U. S. Treasury Circular

No. 570, published annually in the Federal

Register, lists companies approved to act as

surety on bonds securing Government contracts, the

maximum underwriting limits on each contract

bonded, and the States in which each company is

licensed to do business.  Use of this Circular is

mandatory.  The PHA may obtain a free copy of this

Circular by writing directly to the Audit Staff,

Bureau of Government Financial Operations, U. S.

Treasury Department, Washington, D. C. 20226.

(2)   Section 911 of the HUD Act of 1970 authorizes the

Small Business Administration to provide a 90

percent guarantee on contracts of $1,000,000 or

below to any surety company that will provide bid

or performance and payment bonds to the small

construction contractor.

12/89                            9-4

_____________________________________________________________________

h.  Construction Contract.  The construction contract shall

be prepared in the form prescribed by the Field Office

and shall include Form HUD-5370, General Conditions.  In

preparing the construction contract, consideration shall

be given to the following:

(1)   Changes.  Any changes in the General Conditions

shall be made by appropriate amendment written

into the Special Conditions.  Since some

provisions of the General Conditions reflect

Federal statutes, Executive Orders or established

HUD policy and must be incorporated verbatim and

without qualifications, proposed modifications

shall be discussed with the Regional or Chief

Counsel before they are drafted.  The PHA is

responsible for recognizing a need for

modification of the printed General Conditions and

also for conforming the contract documents with

State, tribal and local laws.

(2)   Separate Construction Contracts.  Main

construction work should be performed under a

single construction contract.  The PHA may obtain

separate bids for portions of the work where

required by State law, necessitated by varying

wage rate requirements (see paragraph 6-9c), or in

the best interest of the modernization of the

project.  Where separate bidding is used, it is

critical that the scope of work under each

contract be clearly defined without gaps or

overlapping of work specified in related contracts

and that the PHA have the capability to administer

separate contracts.

(3)   Project Completion Time.  A realistic construction

period shall be established for the contract.

Such things as type of construction, project size

and location, season and prospective weather

conditions, and availability of skilled labor and

materials should be considered.

(4)   Liquidated Damages.  A liquidated damage rate

shall be established which will reasonably

approximate the loss which might be sustained by

the PHA through failure of the contractor to

complete the project on time.  This includes loss

of rental income, increased administrative costs

and inspection fees, interest and carrying

charges, and other expenses related to the period

of delay in modernization of the project.  An

9-5                            12/89

_____________________________________________________________________

unreasonably high rate of liquidated damages may

discourage bidders, result in higher bids, and be

construed as a penalty.  An unreasonably low rate

may encourage late completions.

(5)   Wage Requirements.  Davis-Bacon wage rates

determined by the Department of Labor and provided

by the Regional or Field Office or HUD-determined

wage rates shall be incorporated in the Special

Conditions without modification (see paragraphs

6-9 and 9-5g).  All documentation shall be

prepared so as to permit inclusion of the wage

rates as soon as they are received.

(6)   Equipment.  Equipment, such as ranges, water

heaters and refrigerators, may be acquired through

the CSP, through separate contracts, or included

in the main construction contract.  Use of either

of the first two cost saving methods is

recommended.  If the main construction contract is

to include the installation, but not the purchase,

of dwelling equipment, the contract shall include

proper provision for reception of the items and

appropriate coordination clauses.  If the

equipment is purchased by methods other than the

CSP, the PHA should ensure that price and warranty

are equivalent to or better than that available

through the CSP.

(7)   Demolition.  Whenever feasible, demolition work

should be included in the main construction

contract.  If this is not done, the standard

bidding documents may be used with minor

modifications for demolition work.  Since there

may be salvage value, the form of bid should allow

for the possibility of a sum being deducted (equal

to the salvage value) from the amount to be paid

to the contractor.

*            (8)   Specifications.  See 24 CFR 85.36(c)(1) in

Appendix 15 for examples of specifications which

restrict competition and therefore are expressly

prohibited.                                      *

i.  CSP Contract.  For work to be performed under CSP, the

PHA shall issue a purchase order, which shall include

the assurance of completion, correct wage rates,

completion date, liquidated damage rate, insurance,

general and supplemental conditions, and contract

administration and completion provisions.  The purchase

12/89                                 9-6

_____________________________________________________________________

order shall not include work other than that listed in

the HUD CSP catalogs and shall not be modified through

change orders.

* 9-5.   BID PACKAGE.  The PHA shall prepare a standard bid package,

consisting of the following, as appropriate:

a.  Cover sheet identifying the PHA, project number, job

number, and general scope of work;

b.  PHA invitation for bids, including the day, time and

place that bids will be opened;

c.  Form HUD-5369, Instructions to Bidders;

d.  Form HUD-5370, General Conditions, and Special

Conditions.  Until the General Conditions can be

revised, the PHA shall insert into the General

Conditions the sentence, "The contractor or

subcontractor is prohibited from placing a lien on the

PHA's property."

e.  For contracts over $50,000, Form HUD-2530, Previous

Participation Certificate, marked "Modernization," to be

submitted to the PHA;

f.  Bound construction specifications and bound working

drawings or other description of supplies/services; the

drawings shall be scaled and signed by the person who

prepared them;                                         *

g.  Correct wage rates, including either Form HUD-52554,

Supplement to the General Conditions of the Contract for

Construction, where Davis-Bacon wage rates apply, or

Form HUD-5370A, Supplementary Conditions of the Contract

for Construction (Nonroutine Maintenance), where

HUD-determined wage rates apply;

h.  Bid form to be submitted to the PHA;

i.  Bid guarantee form to be submitted to the PHA;

j.  Non-collusive affidavit to be submitted to the PHA;

k.  Contract form; and

l.  Assurance of completion (see paragraph 9-4g).

9-6.   HUD-ESTABLISHED THRESHOLD.  Based on an assessment of the

PHA's past performance in modernization contracting and

9-7                            12/89

_____________________________________________________________________

in-house technical capability, the Field Office may

establish a dollar threshold over which the PHA shall submit

construction and bid documents for prior Field Office review

and approval.

a.  Criteria.  In determining the appropriate dollar

threshold for PHA submission, the General Engineer shall

consider the following criteria:

(1)   Past Performance in Modernization Contracting.  In

the past:

(a)   Construction documents (working drawings and

construction specifications) have accurately

reflected HUD-approved work and have met the

Modernization Standards;

(b)   Bid documents have been complete and have

included all mandatory provisions, including

the correct wage rates; and

(c)   Bid advertisement has been conducted in

compliance with State, tribal or local laws

and Federal requirements governing public

solicitation of bids.

(2)   In-House Technical Capability.  The PHA has a

staff architect/engineer who is capable of

preparing the construction and bid documents or

experienced staff who are capable of reviewing the

documents prepared by an outside

architect/engineer.

b.  Notification to PHA.  After completing the assessment,

the General Engineer shall notify the PHA of the

established dollar threshold over which construction and

bid documents are required to be submitted for prior

Field Office approval and the reasons.  Where prior

Field Office approval is required, the PHA shall be

informed as to whether HUD review pertains to only the

preliminary or to both the preliminary and final plans

and specifications.  This notification shall be included

in the letter to the PHA approving the CIAP Application.

c.  Submission.  Where required, the PHA shall submit

complete construction (working drawings and construction

specifications) and bid documents for each proposed

modernization contract to the Field Office, Attention:

Chief, Assisted Housing Management Branch

12/89                                 9-8

_____________________________________________________________________

(AHMB), for review and approval before soliciting bids.

9-7.   PHA CERTIFICATION.

a.  PHAs with Thresholds.  The PHA shall solicit bids

without prior Field Office review and approval, unless

the estimated contract exceeds the dollar threshold that

has been established by the Field Office (see paragraphs

7-1 and 9-6).  Where HUD approval is not required, the

designated PHA official shall certify in writing to the

following and send a copy of the certification to the

Field Office:

(1)   The PHA has obtained the required certification

from the architect/engineer (see paragraph 8-3);

(2)   The construction documents accurately reflect

HUD-approved work and meet the Modernization

Standards;

(3)   The bid documents are complete and include all

mandatory provisions, including correct wage rates

*                  and labor standards contract provisions and Indian

preference requirements, where applicable; and   *

(4)   The bid documents include all necessary

requirements related to lead-based paint abatement

and physical accessibility.

*        b.  Recognized Performers.  For alternative requirements for

recognized non-Indian performers, as defined in Chapter

11 of the Field Office Monitoring of PHAs Handbook

7460.7 REV-1, refer to that Handbook.                  *

9-8.   HUD REVIEW AND APPROVAL.

a.  Review.  Where submitted by the PHA, the General

Engineer shall promptly review the construction and bid

documents to ensure that they have been completed in

accordance with prior approvals, meet the Modernization

Standards, include all mandatory provisions, and are

ready for issuance.  As necessary, the General Engineer

shall solicit technical advice from other Field Office

specialists, such as the Labor Relations staff on the

wage rates and the Fair Housing and Equal Opportunity

(FHEO) Division on requirements related to Executive

Order 11246, as amended, and Section 3 of the HUD Act of

1968, as amended, including the appropriate Appendix A

for Bid Condition Areas (see Handbook

9-9                            12/89

_____________________________________________________________________

8020.1, Chapter 5).  The General Engineer also shall

work with the PHA and its architect to reach agreement

on any points in question.

b.  Action.  The Field Office review shall be completed and

the PHA advised of the results within 10 working days of

receipt of the construction and bid documents.  When the

documents are in proper order, the General Engineer

shall prepare a letter to the PHA for the signature of

the Director, Housing Management Division or designee,

indicating approval of the documents, with or without

modification, and authorizing the PHA to issue the

invitation for bids.  Where appropriate, the Regional or

Chief Counsel shall concur in the letter.

c.  Monitoring.  The General Engineer shall periodically

review copies of the construction and bid documents

through on-site review of PHA files.  The review shall

determine whether the documents met the criteria set

forth in paragraph 9-6a(1) and did not result from

splitting bids to avoid prior HUD review and approval.

The Maintenance Engineer also shall periodically review

the PHA's in-house technical capability to determine

whether there has been a change in capability which

would warrant a higher or lower threshold.  If

deficiencies or evidences of abuse of the established

threshold are found, the Field Office monitoring letter

(see paragraph 10-17a(3)) may require the PHA to submit

construction and bid documents for each proposed

modernization contract over a reduced threshold to the

Field Office for review and approval before solicting

bids.

9-9.   INVITATION FOR BIDS.  Where prior Field Office approval is

required, the PHA shall immediately publish an invitation

for bids upon receipt of the Field Office approval letter,

but only if it has the current, correct wage rates.  Where

prior Field Office approval is not required, the PHA shall

publish the invitation immedately upon receipt of the wage

rates from the Labor Relations staff.  The PHA shall number

sequentially each copy of the bid package for control

purposes.  The PHA shall provide a copy of the complete bid

package to each bidder whether or not bids are being invited

for a single construction contract or separate trade (e.g.,

plumbing, electrical, mechanical) contracts.

a.  Publication.  The PHA shall give full opportunity for

open and competitive bidding by publishing the

invitation for bids at least once a week for two

consecutive weeks in local newspapers and trade

12/89                                9-10

_____________________________________________________________________

journals.  See paragraph 6-2c regarding publicizing

invitations for bids to Minority Business Enterprises

(MBEs).  The PHA also shall extend an invitation to

contractors who have previously expressed an interest to

participate in modernization to the PHA or Field Office.

b.  Bid Period.  The PHA shall establish a deadline date for

acceptance of bids which allows sufficient time for

bidders to evaluate the bid package, estimate costs, and

submit their bids to the PHA.  The bid period shall be

for at least the number of days required by State or

*            local law.  However, if an addendum is issued, the PHA

shall consider the magnitude of change in determining

whether the bid opening should be postponed and for how

long.                                                  *

c.  Deposit.  The PHA shall require a deposit for each bid

package in an amount that is based on local practice,

but at least sufficient to offset the cost of

reproducing the bid package.  A deposit is not required

for bid packages issued to a builder's exchange or

similar building service organization.  All deposit

checks or drafts shall be made payable to the PHA.

*        d.  Alternate Bids.  The PHA shall not request alternate

bids (e.g., two different structural systems).  Instead,

the PHA shall specify the most expensive system as the

base bid and list deductive alternates in inverse

priority order so that in the case of a budget overrun,

they may be taken in numerical order as listed until the

award can be made within available funds.              *

e.  Addendum to Bid Package.  The PHA shall issue changes to

the standard bid package in the form of an addendum.

The PHA shall not interpret the meaning of bid documents

except by addendum.  Each addendum shall be numbered

sequentially and a copy provided to each bidder of

record, to each place where bidding documents are on

file and to the Field Office, only where the PHA is

required to submit construction and bid documents before

advertisement.  The addendum also shall specify, if

applicable, the revised deadline date for submission of

bids.

f.  Control Record.  The PHA shall maintain, or authorize

its architect to maintain, a record of all bidding

documents.  This record shall identify the following for

each individual or firm that requested a bid package:

the bid package control number; name and

9-11                            12/89

_____________________________________________________________________

address of the individual or firm; if applicable, number

of the addendum and date sent; amount of deposit and

date received, including the return or forfeiture of the

deposit; date and time the bid was received; and date

the individual or firm was notified as to the successful

low bidder.

Section 3.  Contract Award

9-10.  BID OPENING AND EVALUATION.

a.  Bid Opening.  Upon receipt of each bid, the PHA shall

mark the date and time on the envelope and keep it

unopened in a secure place.  At the date and time

specified in the invitation for bids, the bids shall be

opened in public and read aloud.

*        b.  Late Bids.  Any bids received after the date and time  *

specified in the invitation for bids shall not be opened

and shall be returned unopened to the bidder, with a

letter indicating that the bid was not received by the

specified deadline.

c.  Bid Rejection or Withdrawal.  After the public opening,

the PHA may allow any bidder to withdraw a bid only if

it is apparent that the bidder has made a mistake or the

PHA may reject or disqualify the lowest bidder.

(1)   Withdrawal.  If a bidder seeks to withdraw a bid

before the end of the bid acceptance period or the

execution date of the contract, whichever is

earlier, the PHA shall secure the following before

approving or disapproving the withdrawal request:

a notarized statement from the bidder indicating

that an error was made with an explanation of how

it occurred; a copy of the bidder's cost

estimating worksheets or other evidence provided

by the bidder in support of the withdrawal

request; and a legal opinion prepared by the PHA's

attorney indicating whether the bidder is bound by

the bid.

(2)   Rejection.  The PHA shall reject any bid that is

incomplete, such as where the bid guarantee is not

submitted with the bid, or that fails to conform

to the essential items of the Invitation for Bids.

(For the exceptions on the Previous Participation

Certificate and the non-collusive affidavit, see

paragraphs 9-4d and f, respectively.) If the PHA

proposes to reject the lowest bidder for reasons

other than an incomplete bid, the PHA shall give

12/89                                 9-12

_____________________________________________________________________

the bidder an opportunity, within a specified

time, to delete objectionable conditions from a

bid only if the conditions do not concern the

substance of the bid, such as price, quantity,

quality, or delivery of items offered.  After the

specified time, the PHA shall make a final

decision.

(3)   Bidder Notification.  The PHA shall notify the

bidder, not later than the specified bid holding

period, as to whether the withdrawal request has

been approved or disapproved or whether the bid

has been rejected.  If appropriate, the PHA also

shall return the bid guarantee to the bidder.

d.  Rejection of All Bids.  The PHA may decide, because of

the high bids received or other justifiable cause, to

reject all bids.

(1)   Reasons for Rejection.  The PHA and its architect

shall review the bids received to determine the

reason that the contract cannot be awarded.  The

purpose of this review is to ascertain that: the

bid amount exceeds the approved budget amount; the

bids are unreasonably high due to unusual

circumstances affecting construction in the

housing market area; the project is overdesigned;

or the award cannot be made for other identified

causes.

(2)   Overdesign.  If it is determined that the high

bids are due to project overdesign, the PHA and

its architect shall identify design modifications

that would likely result in lower bids.  Where

required under paragraph 9-6, the PHA shall submit

revised construction documents for prior Field

Office review and approval.  The PHA architect

shall be held responsible for making any design

modifications under the terms of the architect's

contract.

(3)   Invitation for Bids.  Upon Field Office approval

of the revised construction documents, where

required, the PHA shall be authorized to issue a

subsequent invitation for bids.

*        e.  Bid Protests.  The PHA alone is responsible, in

accordance with good administrative practice and sound

business judgment, for the settlement of all contractual

and administrative issues arising out of procurements,

including protests.  The PHA shall have                *

9-13                            12/89

_____________________________________________________________________

*            procedures to handle and resolve protests and shall in

all instances disclose information regarding protests to

the Field Office.  The Field Office will not substitute

its judgment for that of the PHA unless the matter is

primarily a Federal concern.  The bidder must exhaust

all administrative remedies with the PHA before pursuing

a protest with the Field Office.                       *

9-11.  PHA SUBMISSION AND CERTIFICATION.

a.  General Requirements.  After bid opening, the PHA shall:

(1)   In all cases, clear the lowest responsible bidder

with the Field Office for check against the Lists

of Parties Excluded from Federal Procurement or

Nonprocurement Programs;

(2)   For contracts over $50,000, regardless of whether

prior HUD approval was required of the bid

documents or is required of the contract award,

submit Form HUD-2530, prepared by the lowest

responsible bidder, to the Field Office for

previous participation review; and

*            (3)   Where prior HUD review and approval are required

before contract award (see subparagraph b), submit

the following documents to the Field Office,     *

Attention:  Chief, AHMB:

(a)   Bid tabulation, certified to completeness by

the PHA and identifying the following for

each bid received: name and address of the

*                        bidder; amount of the bid; amounts of any

deductive alternates; and amount and type  *

of bid guarantee; and

(b)   Bid, including a copy of the bid guaranty

and non-collusive affidavit, that the PHA

proposes to accept.

*        b.  Prior Field Office Approval.  Prior Field Office review

and approval before contract award are required when:

(1)   The proposed award exceeds the approved budget

amount;

(2)   The PHA's procurement procedures or operation

fails to comply the the procurement standards in

24 CFR 85.36(b) in Appendix 15;                  *

12/89                                 9-14

_____________________________________________________________________

*            (3)   The proposed award exceeds $25,000 and is to be

awarded without competition or on the basis of a

single bid;

(4)   The proposed award exceeds $25,000 and specifies a

"brand name" product; or

(5)   The proposed award exceeds $25,000 and is to be

made to other than the apparent low bidder.

c.  Award Without Prior Field Office Approval.  Except as

required in subparagraphs a and b, the PHA may award the

contract without prior Field Office approval if the

designated PHA official has certified in writing that:

(1)   The bid advertisement and contract award were

conducted in compliance with State, tribal or

local laws and Federal requirements, including 24

CFR 905.204, Indian preference in contracting for

IHAs;

(2)   The award has been cleared with the Field Office

to determine that the contractor is not on the

Lists of Parties Excluded from Federal Procurement

or Nonprocurement Programs;

(3)   Where the award exceeds $50,000, the award has

been cleared by the Field Office under the

previous participation review process; and

(4)   The award does not meet the conditions of        *

subparagraph b.

9-12.  HUD REVIEW AND APPROVAL.

a.  Technical Review.  Where submitted by the PHA, the

General Engineer shall consult with the HMS regarding

any required budget revisions and review contract award

documents to determine that the proposed award is in

proper order.  The Maintenance Engineer shall check the

Lists of Parties Excluded from Federal Procurement or

Nonprocurement Programs to ensure that the contractor is

not on the List.

*        b.  Previous Participation Review.  Upon receipt of Form

HUD-2530, designated responsible staff (DRS) shall enter

the principal's name into the automated system in

accordance with the User's Guide.                      *

9-15                            12/89

_____________________________________________________________________

*            (1)   When the system reports that the principal may be

granted 2530 approval, the DRS shall take the hard

copy printout from the system and attach it to

Form HUD-2530.  The Chief, AHMB, shall sign Part

II of the form and place a check in Block A.  The

DRS then shall forward the form to the Field

Office Manager or, in co-located offices, the

Regional Public Housing Director, for approval.

The Field Office Manager or Regional Public

Housing Director shall write "Approved" next to

the names of the principals in Block 7, Page 1 of

Form HUD-2530, and then date and sign the form.

After approval, the DRS shall notify the PHA.  The

Field Office shall process Form HUD-2530 within

three working days of receipt.

(2)   When the system reports that the principal has to

be referred to Headquarters due to a history of

adverse or unsatisfactory performance, as

indicated by either Form HUD-2530 or results of

inquiries to the Farmers Home Administration or

the State Finance Agency, the DRS shall request

review by Chief or Regional Counsel.  Counsel

shall review the sufficiency of evidence to

support a Departmental hearing, as described in

the Previous Participation Handbook 4065.1.  The

DRS shall forward Form HUD-2530, along with

Counsel's review and the hard copy printout, to

the Field Office Manager or Regional Public

Housing Director for signature and then to the

Participation and Compliance Division in

Headquarters for either final action or referral

to the Multifamily Participation Review Committee.

The DRS shall alert Headquarters that Form

HUD-2530 will be submitted and to provide

information on when the bid acceptance period

expires.  In addition, the DRS shall notify the

PHA of the status of the 2530 clearance.

c.  Action.  The Field Office review shall be completed and

the PHA advised of the results within 10 working days of

receipt of the proposed contract award documents, unless

Headquarters approval of Form HUD-2530 is required.

When the contract award documents are in proper order,

the General Engineer shall prepare a letter to the PHA

for the signature of the Director, Housing Management

Division or designee, authorizing the PHA to award the

contract and requiring the PHA to submit any budget

revisions.                                             *

12/89                                 9-16

_____________________________________________________________________

d.  Monitoring.  The General Engineer shall periodically

evaluate the bids opened and the contracts awarded by

the PHA, including the PHA certification where prior

Field Office approval was not required, through on-site

review of PHA files.  If deficiencies are found, the

Field Office monitoring letter (see paragraph 10-17a

(3)) may require the PHA to submit proposed contract

award documents in all or specified instances to the

Field Office for review and approval before contract

award.

9-13.  PHA CONTRACT AWARD.  Upon receipt of the Field Office letter

authorizing contract award or the Field Office approval

under the previous participation review process, including

the excluded parties check, the PHA shall contact the

successful bidder (if separate trade contracts are to be

executed, the PHA shall contact each successful bidder) to

schedule a date for contract execution.  For CSP contracts,

the PHA shall comply with subparagraphs d, e and f.

a.  Contractor Notification.  The PHA shall send a

registered letter to the successful bidder indicating:

the date, time, and place scheduled for PHA and

contractor execution of the contract; the contractor

must provide the assurance of completion in the amount

identified in Form HUD-5369, Instructions to Bidders;

and if a performance and payment bond, the bond shall

bear the same date or a date after the date of execution

of the contract and shall be accompanied by a properly

*            executed power of attorney by the bonding company to its

authorized agent, which does not precede the date of the

performance and payment bond.                          *

b.  Contract Execution.  Before executing the contract, the

PHA shall ensure that the assurance of completion meets

the requirements of the Instructions to Bidders.  The

PHA shall prepare three original sets of the contract

documents; i.e., construction contract, bound

construction specifications, bound working drawings, and

addenda.  The PHA and contractor (including trade

contractors if separate construction contracts are to be

executed) shall sign the first and last page of the

three sets of construction specifications, working

drawings and any applicable addenda.  If separate trade

contracts are to be executed, each trade contractor also

shall sign the first and last page of the applicable

trade division of the construction specifications.

9-17                            12/89

_____________________________________________________________________

c.  Distribution of Executed Documents.  The PHA shall

retain one original copy of the performance and payment

bond (or other assurance), power of attorney, and a

signed set of the contract documents for its files.  The

PHA shall send one copy to the Field Office, Attention:

Chief, AHMB, and retain the contractor's copy for

attachment to the PHA's notice to proceed.  For CSP

contracts, the PHA shall send one copy of the signed

purchase order to the Field Office.

d.  Department of Labor Notification.  Within 10 calendar

days of contract award (including subcontracts) for each

contract of $10,000 or more, the PHA shall send a notice

of contract award to the Regional Office of Federal

Contract Compliance Programs of the Department of Labor.

This notification is required by Executive Order 11246,

as amended, and shall include: the name, address, and

telephone number of the contractor; employer

identification number; dollar amount of the contract;

estimated construction start and completion dates; and

project number(s) and community in which the project(s)

is located.

e.  Preconstruction Conference.  The PHA shall schedule date

for a preconstruction conference to be held at the PHA.

The conference date may be the same, or within 10

calendar days from the date of contract execution.  The

purpose of the preconstruction conference is to provide

for the timely modernization of the project by

eliminating any misunderstanding of HUD regulations and

procedures, contract and safety requirements, and

responsibilities of the PHA, its architect, the

contractor and the Field Office.  In scheduling the

preconstruction conference, the PHA shall consult with

its architect, the contractor, and the General Engineer,

if appropriate, to arrange a date that is acceptable to

all parties.

f.  Notice to Proceed.  The PHA shall prepare two original

copies of the notice to proceed to be issued to the

contractor, together with the contractor's set of the

executed contract documents.  The notice to proceed is

the official PHA order directing the contractor to start

work.  The date of completion is counted from the date

of the notice to proceed.  The contractor shall be

requested to sign the notice to proceed, designating

receipt and acceptance, and return one signed original

to the PHA.

Section 4.  Contract Administration Responsibilities

12/89                                9-18

_____________________________________________________________________

9-14.  PHA RESPONSIBILITIES.  The PHA is responsible for enforcing

the architect's and the construction contracts and for

ensuring retention of all contractual rights.  PHA staff

assigned these responsibilities shall be included in the

Modernization Organization and Staffing Plan, required in

paragraph 3-6e.

a.  Contracting Officer.  The PHA shall designate an

*            employee as its contracting officer, identify the scope

and limitation of his/her responsibility in writing   *

and provide copies to its architect and the contractor.

b.  Contract Administrator.  The PHA shall designate a

qualified professional, such as its architect, to

administer the contract.

c.  Insurance.  The PHA shall comply with the insurance

requirements set forth in paragraph 6-10.

d.  Reports.  The PHA shall obtain the reports and

construction documents required by the contract and the

Field Office from its architect and the contractor.  The

PHA shall retain these reports and, as required, send a

copy to the Field Office.

e.  Inspections.  See paragraphs 10-15 and 10-16.

f.  Construction Progress Meetings.  The PHA shall meet with

its architect and the contractor on a regular basis to

discuss work progress, any problems or deficiencies

noted during inspection visits, overdue reports and the

construction schedule.  The PHA shall prepare a written

record of the items discussed at each meeting and place

a copy in its construction file.

g.  Correction of Deficiencies.  Upon being notified by its

architect or the General Engineer of construction

deficiencies, the PHA shall promptly notify the

contractor in writing of the deficiencies observed.

This notification also shall advise the contractor that

failure to make timely corrections would be an

infraction of the contract and that the contractor is

liable for any resulting losses or delays.

*        h.  Timeliness of Construction Progress.  The PHA shall

notify the Field Office if the contractor falls more

than 30 days behind the PHA-approved Construction

Progress Schedule (see paragraphs 9-18 and 9-20).      *

9-19                            12/89

_____________________________________________________________________

9-15.  HUD RESPONSIBILITIES.  The Field Office is responsible for

ensuring that the PHA, in accordance with the terms of the

ACC, is enforcing the architect's contract and the

construction contract, including the construction documents.

See paragraph 10-17 regarding inspections by the Field

Office.  The Field Office shall provide technical assistance

and guidance to the PHA concerning contract administration

*        and enforcement, reporting, interpretation of construction

documents and other related matters.  The Field Office shall

maintain a control log on the status of modernization

contracts.  A sample Modernization Contract Status Control

Log is attached as Appendix 16.                            *

9-16.  SUBCONTRACTORS.  All contracts between the contractor and

any subcontractors shall contain the equal opportunity

employment requirements and the prevailing wage rate

requirements.  The contractor (including the CSP contractor)

*        is responsible for determining that potential subcontractors

are not on the Lists of Parties Excluded from Federal

Procurement or Nonprocurement Programs.  See 24 CFR 85.37(b)

in Appendix 15 for other subcontractor requirements.       *

9-17.  CONTRACTOR PAYROLL.  The contractor is responsible for

paying not less than the applicable wage rates to all

employees engaged in work under the contract and ensuring

that any subcontractors also pay not less than the

applicable wage rates (see paragraph 6-9).

a.  Payroll Report.  The contractor shall submit a certified

payroll report and compliance statement to the PHA each

week during the contract period; i.e., from execution of

the contract to contract completion and acceptance by

the PHA.  A separate payroll report shall be submitted

for the contractor and each subcontractor.

b.  Payroll Forms.  The contractor's report may be submitted

on the Payroll Form (WH-347), which includes on its

reverse side the required Statement of Compliance.  Such

forms may be obtained from the Government Printing

Office, Washington, D.C. 20402.  The contractor may

substitute other forms including computer-generated

forms, instead of the Payroll Form (WH-347), provided

that all of the required information is included.

*        c.  Monitoring.  The PHA is responsible for reviewing the

contractor's reports to ensure that the correct wage

rates are being paid and for resolving any             *

12/89                                 9-20

_____________________________________________________________________

*            discrepancies.  Refer to the Labor Standards Handbook

1344.1 REV-1 for guidance.                             *

d.  Retention.  The PHA shall retain all payroll reports and

certifications for three years from the date of contract

completion and acceptance by the PHA.

9-18.  CONSTRUCTION PROGRESS SCHEDULE.

a.  Contractor Schedule.  Where progress payments are

necessary, the PHA shall require the contractor to

prepare a construction progress schedule, for each

project immediately after PHA issuance of the notice to

proceed.  The PHA may require use of Form HUD-5372,

Construction Progress Schedule, or other appropriate

forms from various professional organizations.  The

information shall be realistic and consistent with the

information provided by the contractor on the

*            PHA-approved schedule of amounts for contract payments

and the HUD-approved Project Implementation Schedule.  *

b.  PHA Review and Approval.  The PHA or its architect shall

review the contractor's construction progress schedule

to determine that the scheduled dates and amount of work

to be completed are reasonable and consistent with the

contract.  If acceptable, the PHA architect shall sign

the schedule and forward it to the PHA for approval.

Upon approval by the PHA, the approved construction

progress schedule shall be returned to the contractor.

c.  Field Office Monitoring.  The General Engineer shall

periodically review PHA-approved construction progress

schedules through on-site review of PHA files.  If

deficiencies are found, the Field Office monitoring

letter (see paragraph 10-17a (3)) may require the PHA to

submit future schedules to the Field Office for prior

review and approval.

9-19.  SCHEDULE OF AMOUNTS FOR CONTRACT PAYMENTS.

a.  Contractor Schedule.  Where progress payments are

necessary, the PHA shall require the contractor to

prepare a schedule of amounts for contract payments

immediately after execution of the contract.  The PHA

may use Form HUD-51000, Schedule of Amounts for Contract

Payments, or other appropriate forms from various

professional organizations.

b.  PHA Review and Approval.  The PHA and its architect

9-21                            12/89

_____________________________________________________________________

shall review the schedule to determine that the

scheduled work to be completed by the specified dates

and the amount of payment for such work are reasonable.

If acceptable, the PHA shall approve and return the

schedule to the contractor.  Field Office review is not

required.

c.  Field Office Monitoring.  The General Engineer shall

periodically review PHA-approved payment schedules

through on-site review of PHA files.  If deficiencies

are found, the Field Office monitoring letter (see

paragraph 10-17a(3)) may require the PHA to submit

future payment schedules in all or specified instances

to the Field Office for prior review and approval.

9-20.  CONTRACT PAYMENTS.  The PHA is responsible for making

progress payments to the contractor based on the

PHA-approved schedule of amounts for contract payments.

Generally, progress payments for acceptable work and

materials delivered and stored on the site are made at

30-day intervals.  Field Office authorization of progress

payments, based on the approved payment schedule, is not

required.

a.  Contractor Request for Payment.  The contractor shall

submit a request for payment for each project on Form

HUD-51001, Periodical Estimate for Partial Payment.  The

request shall be accompanied by the contractor's written

designation of a certifying officer.  In addition, the

contractor shall submit the following HUD forms or other

appropriate forms, if applicable, with each periodical

estimate for partial payment: Form HUD-51002, Schedule

of Change Orders; Form HUD-51003, Schedule of Materials

Stored; and Form HUD-51004, Summary of Materials Stored.

b.  PHA Review and Approval.  The PHA shall review each

Contractor request and shall approve the payment if the

following conditions have been met.  If the contractor

requests payment for items which have not been

acceptably completed, the PHA shall delete those items

and adjust the payment accordingly.

(1)   the contractor request is consistent with the

PHA-approved schedule of amounts for contract

payments;

(2)   the request does not include the amount to be

retained by the PHA under the contract;

12/89                                9-22

_____________________________________________________________________

(3)   the work covered by the payment has been performed

in accordance with the construction documents;

(4)   the periodical estimate for partial payment has

been properly executed and all applicable

supporting documentation submitted; and

(5)   the contractor has submitted all required reports,

such as payroll reports.

c.  Distribution of Documents.  The PHA shall retain the

original periodical estimate for partial payment and any

applicable supporting documentation for its file and

return a copy of the PHA-approved forms to the

contractor.

9-21.  AS-BUILT DRAWINGS.  The general contractor is responsible

for providing all necessary information to the PHA architect

in order that the PHA architect may prepare the as-built

drawings.  The PHA architect shall provide the PHA with a

copy of the as-built drawings for its file upon contract

completion.  These drawings shall include all significant

deviations from the working drawings approved by the PHA or

the Field Office.

9-22.  SHOP DRAWINGS AND MATERIALS.  Where appropriate to the

particular type of modernization being undertaken, the

contractor shall prepare and submit shop drawings and

material samples in accordance with the agreements reached

at the preconstruction conference.

a.  Contractor Submission.  The contractor is responsible

for preparing and submitting shop drawings to the PHA or

its architect.  The contractor's letter shall list the

shop drawings being submitted and state whether the shop

drawings deviate from the approved construction

documents.  Each shop drawing shall include: a

descriptive title and drawing number; a brief

description of the work involved; the project number and

name; the contractor's and any subcontractor's name; and

evidence of the contractor's approval.

b.  PHA Architect's Approval.  The PHA architect shall

review the shop drawings to determine whether they are

consistent with the construction documents.  The

architect shall require that any corrections be made

before approval.  Upon approval, the architect shall:

(1)   sign and date each shop drawing and include the

following statement:  "This shop drawing is

9-23                            12/89

_____________________________________________________________________

approved, but the contractor shall verify and

shall be responsible for all related documents and

job conditions on the work."

(2)   send a letter to the contractor indicating that

the shop drawing was approved and advising the

contractor that:

(a)   "This approval of the enclosed shop drawing

is general and does not relieve the

contractor of the responsibility for

adherence to the contract, nor is the

contractor relieved of the responsibility

for any error which may exist;" and

(b)   if applicable, "The modification shown on

the enclosed shop drawing is approved in the

interest of the PHA to effect an improvement

for the project and is ordered with the

understanding that it does not involve any

change in the contract price or time; it is

subject to all contract stipulations and

covenants; and it is without prejudice to

any and all rights of the PHA under the

contract and bond."

c.  Distribution of Documents.  The PHA architect shall

retain a copy of the approved shop drawing and forward a

copy to the contractor and the PHA.

d.  Samples.  The contractor shall submit certificates,

material samples, and test results to the PHA architect

for approval.  The PHA architect shall advise the

contractor of the reasons for any disapproval and

request that another sample be submitted.  Approved

samples and data shall be retained at both the PHA

office and the project office for comparison during

construction.

9-23.  CONTRACT MODIFICATIONS.

a.  Content.  Modifications to contract work shall be

documented by a written agreement, executed by all

parties to the contract, describing the work

modifications to be performed.  Contract modifications

shall be prepared in the form prescribed by the Field

Office and shall include the following:

(1)   a detailed description of the proposed

12/89                                9-24

_____________________________________________________________________

modification;

(2)   a reference to the applicable working drawings and

specifications;

(3)   a fixed price (credit, debit or no change) for the

change in contract work;

(4)   an estimate of any additional time required to

complete the work;

(5)   the contractor's itemized breakdown of the cost of

materials and labor and an itemized breakdown for

any applicable subcontractors;

(6)   the change indicated on the architectural

drawings, if applicable; and

*            (7)   the latest approved budget amount and the

cumulative amount expended to date.              *

b.  PHA Register.  The PHA shall maintain a separate

contract modifications register for each contract.  This

is required to provide a permanent record of all actions

taken in connection with each contract.  The register

shall identify:

(1)   the number of the modifications;

(2)   a brief description of the modification;

(3)   the cost of the proposed modification;

(4)   the date submitted to the Field Office, if

applicable;

(5)   any critical deadline dates that must be met by

the Field Office;

(6)   if applicable, the date of Field Office approval

or disapproval and the action taken; and

(7)   the amount of any additional time required by the

contractor.

c.  HUD-Established Threshold.  Based on an assessment of

the PHA's past performance and in-house technical

capability, the Field Office may establish a dollar

percentage threshold over which the PHA shall submit

contract modifications for prior Field Office review

9-25                            12/89

_____________________________________________________________________

and approval.

(1)   Criteria.  In determining the appropriate dollar

or percentage threshold for PHA submission, the

General Engineer shall consider the following

criteria:

(a)   Past Performance in Reviewing Contract

Modifications.  In the past:

1    Proposed work was included in the

general scope of the contract;

2    Proposed work was a necessity and in

the PHA's interest;

3    Proposed work was consistent with the

Modernization Standards;

4    Proposed work could not practicably be

performed under a separate contract

after completion of the contract;

5    Any additional time required for the

proposed work was reasonable; and

6    Any additional costs were within the

latest approved budget.

(b)   In-House Technical Capability.  The PHA has

a staff architect/engineer or experienced

staff who are capable of reviewing and

approving/disapproving contract

modifications.

(2)   Notification to PHA.  After completing the

assessment, the General Engineer shall notify the

PHA of the established dollar or percentage

threshold over which change orders are required to

be submitted for prior Field Office approval and

the reasons.  This notification shall be included

in the letter to the PHA approving the CIAP

Application.

d.  PHA Certification.  The PHA may order or agree to a

contract modification without prior Field Office review

and approval, unless the modification, when added to

previously approved modifications, would exceed the

latest HUD-approved budget amount or the dollar

threshold that has been established by the Field Office

(see paragraph 7-1).  Where HUD approval is not

12/89                                9-26

_____________________________________________________________________

required, the designated PHA offical shall certify in

writing to the following and send a copy of the

certification and approved contract modification to the

Field Office:

(1)   The proposed work is included in the general scope

of the contract;

(2)   The proposed work is necessary and economical;

(3)   The proposed work is consistent with the

Modernization Standards;

(4)   The proposed work cannot practicably be performed

under a separate contract after completion of the

contract;

(5)   Any additional time required for the proposed work

is reasonable; and

(6)   Any additional costs are within the latest

approved budget and do not, when added to other

contract modifications previously approved by the

PHA, exceed the HUD-established threshold.

e.  Recognized Performers.  For alternative requirements

*            for recognized non-Indian performers, as defined in

Chapter 11 of the Field Office Monitoring of PHAs

Handbook 7460.7 REV-1, refer to that Handbook.         *

f.  PHA Submission.  Where required, except in an emergency

endangering life or property, the PHA shall submit

contract modifications to the Field Office, Attention:

Chief, AHMB, for review and approval before ordering or

agreeing to any changes in the contract work.

9-24.  HUD REVIEW AND APPROVAL OF CONTRACT MODIFICATIONS.

a.  Review.  Where submitted by the PHA, the General

Engineer shall conduct a prompt review because

modifications often affect work progress.  If the review

indicates that the modification is due to an act by the

contractor contrary to, or failure to act in accordance

with, the terms of the contract, or a mistake by the PHA

architect in preparation of the construction documents

not to be expected under professional standards or other

laxity in carrying out the terms of the contract causing

monetary damage to the PHA, the General Engineer shall

consult the Regional or Chief Counsel for legal advice

as to where

9-27                            12/89

_____________________________________________________________________

responsibility lies.  The General Engineer shall

recommend action that is consistent with this legal

advice.  The General Engineer shall consult with the HMS

regarding any required revisions to the program budget.

To recommend approval, the General Engineer shall

determine that the proposed modification meets the

criteria in paragraph 9-23d.

b.  Action.  The Field Office review shall be completed and

the PHA advised of the results within 10 working days of

receipt of the contract modification.  If the

modification is approvable, with or without revision,

the Director, Housing Management Division or designee

shall approve the modification.  If the modification is

not approvable, the General Engineer shall prepare a

letter to the PHA for the signature of the Director,

Housing Management Division or designee, advising the

PHA of the reasons for disapproval.

c.  Monitoring.  The General Engineer shall periodically

review contract modifications approved by the PHA and

the PHA register through on-site review of PHA files.

If deficiencies are found, the Field Office monitoring

letter (see paragraph 10-17a(3)) may require the PHA to

submit proposed change orders over a reduced threshold

to the Field Office for review and approval before

issuance.

9-25.  TIME EXTENSIONS.  The contractor is responsible for

completing the work within the time established in the

contract.  However, the PHA may authorize any justifiable

time extensions without prior Field Office review and

approval.

a.  PHA Records.  Upon contract completion, the PHA shall

determine the number of calendar days and reasons for

any delays beyond the date established in the contract.

The PHA shall maintain a construction log to record

potential causes for delays which may be used as the

basis for granting time extensions or for determining

the amount of liquidated damages to be assessed against

the contractor.  The PHA shall maintain a record of the

following:

(1)   the daily temperature;

(2)   the daily amount of precipitation;

(3)   delays in obtaining labor and materials, including

the duration and reason;

12/89                                 9-28

_____________________________________________________________________

(4)   labor disputes or strikes, including the duration

and the applicable construction trade;

(5)   delays experienced by others in completing

non-contract public improvements (whether on-site

or off-site); and

(6)   other causes for delays, such as fires, floods,

vandalism or court orders.

b.  Basis for Time Extensions.  In order to be considered

for approval by the PHA, requests for time extensions

must meet the following criteria:

(1)   the contractor must have submitted a written

notice to the PHA within 10 calendar days of the

start of any delay; and

(2)   the severity and extent of adverse weather could

not have been reasonably foreseen by the

contractor (normal seasonal levels of rain, snow,

cold or heat should have been considered by the

contractor) or the cause of the delay was beyond

the contractor's control.

c.  Contractor Request.  Immediately upon receipt of the

contractor's notification of delay or request for time

extension, the PHA shall send a letter of

acknowledgement to the contractor.  The letter shall

indicate that: immediate consideration will be given to

the contractor's request; or the actual delay in work is

difficult to determine and consideration will be given

to the contractor's request upon completion of work.

d.  PHA Finding of Fact.  The PHA shall review its records

to ensure that the information provided by the

contractor is accurate, to determine the cause of the

delay and the extent that it was within the contractor's

control, and to ascertain if the request meets the

criteria established in subparagraph b.  Based on its

review, the PHA shall prepare a "finding of fact" with

the assistance of its architect and attorney and, in

order to approve, determine that:

(1)   the contractor's request, as documented by the PHA

"finding of fact," meets the requirements of

subparagraph b;

(2)   the additional time and cost requested by the

contractor is reasonable based on the nature and

9-29                            12/89

_____________________________________________________________________

duration of the delay; and

(3)   if there is some question of the contractor's

liability for the delay, the PHA "finding of fact"

shall be reviewed in accordance with paragraph

9-26.

* 9-26.  DISPUTES AND CLAIMS.  The PHA alone is responsible, in

accordance with good administrative practice and sound

business judgment, for the settlement of all contractual and

administrative issues arising out of procurements.  The PHA

shall have procedures to handle and resolve disputes.

a.  PHA Notification.  The PHA shall promptly notify the

Field Office of any problems or disputes experienced

during modernization which could result in a claim by

its architect or the contractor.  This may include

claims for extra costs due to delays, claims for time

extensions or extra costs based on PHA actions, or

claims resulting from contract modifications.          *

b.  PHA Records.  It is imperative that the PHA maintain a

complete written and dated record of any actions that

may result in a dispute or claim for damages.  This is

required to protect the PHA interest during any

litigation proceedings that may subsequently arise.  In

such instances, the PHA shall, at a minimum, maintain

the following: a complete and detailed job record;

disputes and claims file, cross-referencing other

pertinent files, for each dispute or claim; and any

correspondence relating to the dispute, including

written minutes of any meetings, which identify actions

taken by the PHA, its architect or contractor, and

decisions or agreements made concerning the dispute.

c.  Contractor Notice.  The contractor must submit a written

notice of claim to the PHA within the time period set

forth in the contract from the date of the incident on

which the claim is based.  The contractor's initial

notice must identify the nature and scope of the claim,

including extra costs sought by the contractor.  The

contractor will subsequently be required to submit a

detailed description and supporting evidence for the

claim.

d.  PHA Acknowledgement.  Immediately upon receipt of the

contractor's notice, the PHA shall date stamp the notice

and shall send a letter to the contractor acknowledging

receipt of the claim.  The PHA's letter also shall

indicate that: if the claim was filed within

12/89                                9-30

_____________________________________________________________________

*            the required time period, the contractor is required to

submit a detailed justification for the claim; or if the

claim was not filed within the required time period, the

contractor's claim is not eligible for consideration.  *

e.  PHA Finding of Fact.  The PHA shall review its records

to ensure that the information provided by the

contractor is accurate.  Based on its review of the

contractor's claim and its knowledge of the

circumstances, the PHA shall prepare a "finding of fact"

with the assistance of its architect and attorney.

*        f.  Field Office Responsibility.  The Field Office will not

substitute its judgment for that of the PHA unless the

matter is primarily a Federal concern.  Violations of

law will be referred to the local, State or Federal

authority having proper jurisdiction.  The contractor

must exhaust all administrative remedies with the PHA

before pursuing a claim with the Field Office.         *

9-27.  LIQUIDATED DAMAGES.  The contractor is responsible for

completing the project within the time established in the

construction contract unless time extensions are authorized

in accordance with paragraph 9-25.  If the work is not

completed by the contract date, the contractor shall be

liable for liquidated damages resulting from such unexcused

delays.

a.  PHA Finding of Fact.  The PHA shall prepare a "finding

*            of fact" under paragraph 9-25, which identifies the

amount of liquidated damages to be assessed against the

contractor and the basis used in determining the amount.

Liquidated damages shall be assessed at the rate

established in the contract and shall be withheld from

any payment due the contractor.

b.  Field Office Responsibility.  The Field Office will not

substitute its judgment for that of the PHA unless the

matter is primarily a Federal concern.  Violations of

law will be referred to the local, State or Federal

authority having proper jurisdiction.  The contractor

must exhaust all administrative remedies with the PHA

before pursuing a protest with the Field Office.       *

Section 5.  Contract Completion and Settlement

9-28.  EARLY OCCUPANCY.  The PHA may accept part of project for

occupancy before contract settlement where the following

9-31                            12/89

_____________________________________________________________________

conditions are met:

a.  The dwelling units to be accepted (except items approved

for delayed completion) have been completed and are

ready for occupancy;

b.  The general contractor agrees to early occupancy and

completion of items approved for delayed completion;

c.  Early occupancy will not unduly inconvenience or

represent a safety risk to tenants while the unfinished

work is being completed;

d.  The PHA has obtained occupancy permits from the

responsible local agency for each unit to be accepted;

and

e.  The PHA has executed an occupancy agreement with the

general contractor indicating that the PHA partially

accepts specified work provided that the contractor

accepts the responsibility to complete the project by

the established completion date.

9-29.  FINAL INSPECTION.  The contractor shall provide prompt

written notification to the PHA when all work is completed.

A final project inspection shall be made when all work is

completed.  Until the final inspection has been made, the

PHA shall not advance any of the retainage or make the final

payment to the contractor.

a.  Inspection Date.  Upon receipt of the contractor's

notification of the date when the work has been

completed, the PHA shall conduct a final inspection

within 10 calendar days.  The PHA shall notify the

General Engineer of the scheduled inspection date.

b.  Inspection Participants.  The final inspection shall be

conducted by: a PHA representative; the PHA architect,

*            where applicable; the General Engineer, where required

by the magnitude of work or other conditions; and a

contractor representative.  The General Engineer is

required to participate in the final inspection where

the per unit modernization cost exceeds $10,000.       *

c.  Inspection Conference.  The inspection team shall meet

after completing the final inspection to determine

whether; the work has been completed in accordance with

the construction documents; there are any minor items of

incomplete or unsatisfactory work (or seasonal work such

as planting of shrubs and lawns) and reach agreement

12/89                                9-32

_____________________________________________________________________

on the items to be included on the PHA's or its

architect's final punch list; or there are any major

deficiencies which must be corrected by the contractor

so that another final inspection can be made before

contract settlement.

9-30.  SETTLEMENT DOCUMENTS.  Following final inspection, the PHA

shall notify the contractor (including the CSP contractor)

to submit the following documentation to the PHA:

a.  Where appropriate, a certificate of occupancy issued by

the responsible local agency for each building;

b.  One notarized original and two copies of the

contractor's release and certification which indicates:

(1)   the work was completed in accordance with the

construction documents, including change orders,

except any minor items identified on the PHA's or

its architect's proposed certificate of

completion;

(2)   the total amount due the contractor and a

separately stated amount for each unsettled claim

against the PHA;

(3)   the PHA is released of all claims, other than

those stated in the contractor's release; and

(4)   wages paid to laborers or mechanics were

consistent with the wage rate requirements of the

contract and there are no outstanding claims for

unpaid wages.

c.  Assignment of all guarantees and warranties to the PHA;

and

d.  "Final" periodical estimate for partial payment.

9-31.  PHA SUBMISSION AND HUD APPROVAL.

a.  PHA Submission.  The PHA shall submit the following to

HUD:

*            (1)   For contracts over $50,000, submit to the AHMB, a

copy of all settlement documents identified in

paragraph 9-30, and the original and one copy of

the proposed certificate of completion.

(2)   For construction contracts over $2,000, but not  *

9-33                            12/89

_____________________________________________________________________

*                  more than $50,000, which are subject to

Davis-Bacon wage rates, or for construction

contracts over $10,000, but not more than

$50,000, which are subject to HUD-determined wage

rates, submit to the Labor Relations staff, a copy

of the proposed certificate of completion.

b.  Review by AHMB.  Upon receipt of the contract settlement

documents for contracts over $50,000, the General

Engineer shall conduct a prompt review.  To recommend

approval, the General Engineer shall determine that

according to his/her best knowledge: all work has been

completed in accordance with the construction documents;

the proposed certificate of completion is acceptable;

and the amount to be withheld from the contractor is

sufficient to complete any items on the PHA's or its

architect's punch list, including seasonal work.  After

review, the General Engineer shall notify by form letter

the Labor Relations staff that the contract settlement

documents are in and request sign-off on the form letter

if there are no known labor relations problems.  If

there are problems, the Labor Relations staff shall

indicate what they are and when they may be resolved.

c.  Review by Labor Relations Staff.  Upon receipt of the

proposed certificate of completion for contracts under

subparagraph a(2), the Labor Relations staff shall

determine whether there are any known labor relations

problems.  If there are none, the Labor Relations staff

shall so notify the PHA.  If there are any known

problems, the Labor Relations staff shall so notify the

PHA and the AHMB.

d.  HUD Action.  AHMB and/or Labor Relations review shall be

completed and the PHA advised of the results within 15

working days of receipt of the contract settlement

documents.  If the documents are in order, the General

Engineer shall forward the certificate of completion to

the Director, Housing Management Division or designee

for signature and shall promptly return the original to

the PHA.

9-32.  PAYMENT TO CONTRACTOR.  Upon receipt of the approved

certificate of completion from the AHMB or notification from

the Labor Relations staff that there are no known labor    *

problems, the PHA is authorized to make payment to the

contractor.

a.  Contract Payment.  The PHA payment to the contractor

12/89                                9-34

_____________________________________________________________________

shall be the amount specified in the certificate of

completion and shall not include any amount to be

retained for disputed items and incomplete work, such as

punch list or seasonal items.

b.  Final Payment.  The PHA is not authorized to make final

payment of any amounts withheld for contracts over

*            $50,000 without prior Field Office approval.  When     *

punch list or seasonal work items are completed, the PHA

shall prepare a revised certificate of completion for

Field Office approval.

9-33.  WARRANTY INSPECTIONS.  The PHA is responsible for performing

required warranty inspections, including the 11-month

inspection, during the warranty period and promptly

notifying the contractor in writing to remedy any defects

relating to manufacturer or contractor warranties on

equipment and systems and contractor warranties on materials

and workmanship.

a.  Contractor Responsibility.  Upon receipt of PHA written

notice, the contractor shall promptly remedy any defects

due to the use of faulty equipment or materials, or poor

workmanship.  The contractor also is responsible for

paying for any damage to other work resulting from such

defects.

b.  Warranty Period.  The warranty period for all

construction work shall be at least 365 calendar days

from the date specified on the final certificate of

completion that is applicable to the work in question or

such longer period as otherwise specified in the

contract.

Section 6.  Contracts for Management Improvements and Other

Professional Services

9-34.  DETERMINATION OF NEED.  During Joint Review, the PHA and the

Field Office shall reach agreement upon the PHA's need for

professional consulting services.  Such services may be

required, for example, to identify management problems and

their causes and/or to develop and implement appropriate

solutions.

9-35.  SELECTION PROCESS.  The PHA shall obtain professional

consulting services by issuing an RFP, establishing a

*        competitive range based on technical qualifications and

cost, holding discussions with those consultants within the

competitive range and giving them an opportunity to submit

revised proposals, holding final discussions, and then

making an award to the responsible firm whose proposal is  *

9-35                            12/89

_____________________________________________________________________

*        most advantageous, with price and other factors considered.

a.  PHA Preparation of RFP.  The PHA shall prepare the RFP

which shall contain: a brief description of the PHA and

the project(s) to be modernized; specific consultant

services required; time frame for provision of the

services; all evaluation factors and their relative    *

importance; submission deadline; and name of the PHA

contact person.  The RFP shall request the consultant,

if interested, to respond with a proposal that

demonstrates an understanding of the required services,

provides evidence of the firm's ability to perform the

services and profiles of the firm's principles, staff

and facilities, provides a cost estimate, and includes a

completed Form HUD-2530, Previous Participation

Certificate, marked "Modernization."

*        b.  PHA Advertisement of RFP.  The PHA shall advertise the

RFP through: public announcement in local newspapers

and, if appropriate, in national publications; direct

requests to qualified consultants in the PHA's files

which the PHA or other PHAs have previously retained;

and direct requests to local associations of minority

consultants.  The PHA shall furnish all interested

parties with a copy of the RFP.

c.  PHA Evaluation of Proposals.  The PHA shall evaluate all

responses to the RFP against the technical evaluation

factors and eliminate those that are obviously

unqualified to provide the required services.  The PHA

shall hold discussions with those consultants which are

within the established competitive range and give them

an opportunity to revised their proposals.  The PHA then

shall hold final discussions and make an award.

d.  Previous Participation Review.  Upon selecting and

reaching agreement with the consultant, the PHA shall

immediately transmit Form HUD-2530 to the Field Office

(see paragraph 9-38b).

e.  PHA Contract Execution.  Upon receipt of previous

participation clearance and Field Office approval where

required, the PHA shall immediately execute the

contract, which must be either a fixed-price or

cost-reimbursement with established ceiling type.

f.  Contract Modifications.  The PHA shall not order agree

to any modifications in the contract work where        *

12/89                                 9-36

_____________________________________________________________________

prior Field Office approval is required.  Contract

modifications shall include a description of the

proposed modification in work, the fixed cost (credit,

debit or no change) of the modification, and an estimate

of any additional time required to complete the work.

* 9-36.  HUD-ESTABLISHED THRESHOLD.  Based on an assessment of the

PHA's past performance in obtaining professional consulting

services and administering such contracts, the Field Office

may establish dollar thresholds over which the PHA shall

submit RFPs, contracts and contract modifications for prior

Field Office review and approval.

a.  Criteria.  In determining the appropriate dollar

thresholds, one for RFPs and contracts and one for

contract modifications, the HMS shall consider the

following criteria:

(1)   Past Performance in Preparing and Administering

Contracts.  In the past:

(a)   RFPs have contained clear statements of

required services and contained all

mandatory information;

(b)   Procurement has been conducted in compliance

with Federal requirements;

(c)   Contracts have been cleared with the Field

Office under the previous participation

review process;

(d)   Contracts and contract modifications have

accurately reflected HUD-approved work and

have been within the latest approved budget;

and

(e)   Contract modifications have been within the

general scope of the contract.

(2)   In-House Technical Capability.  The PHA has

experienced staff who are capable of preparing the

RFP and reviewing proposals and contract

modifications.

b.  Notification to PHA.  After completing the assessment,

the HMS shall notify the PHA of the established dollar

thresholds (for RFPs/contracts and for contract

modifications) over which such documents are required to

be                                                     *

9-37                            12/89

_____________________________________________________________________

*            submitted for prior Field Office approval and the

reasons.  This notification shall be included in the

letter to the PHA approving the CIAP application.

c.  Submission.  Where required, the PHA shall submit the

RFP before advertisement, the contract before award, and

any contract modifications before issue for each

professional consulting service contract to the Field

Office, Attention:  AHMB, for prior review and approval.

9-37.  PHA CERTIFICATION.

a.  PHAs with Thresholds.  The PHA may advertise RFPs, award

professional service contracts, and issue contract

modifications without prior Field Office review and

approval, unless the estimated contract or contract

modification amount exceeds the dollar thresholds that

have been established by the Field Office (see

paragraphs 7-1 and 9-36).  Where HUD approval is not

required, the designated PHA official shall certify in

writing to the following and send a copy of the

certification, executed contract, and approved contract

modification to the Field Office:

(1)   The contract (or modification) accurately reflects

HUD-approved work and does not exceed the latest

approved budget amount; and

(2)   The contract has been cleared with the Field

Office under the previous participation review

process; or

(3)   The contract modification is within the general

scope of the contract.

b.  Recognized Performers.  For alternative requirements for

recognized non-Indian performers, as defined in Chapter

11 of the Field Office Monitoring of PHAs Handbook

7460.7 REV-1, refer to that Handbook.

9-38.  PHA SUBMISSION AND HUD APPROVAL.

a.  RFP Review and Approval.  Where submitted by the PHA,

the HMS shall review the RFP and advise the PHA of the *

results within 10 working days of receipt.  The HMS

shall prepare a letter to the PHA for the signature of

the Director, Housing Management Division or designee,

indicating approval, with or without modification, and

authorizing the PHA to advertise the RFP, or

12/89                                 9-38

_____________________________________________________________________

*            indicating disapproval.

b.  Previous Participation Review.  Upon receipt of Form

HUD-2530, designated responsible staff (DRS) shall enter

the principal's name into the automated system in

accordance with the User's Guide.

(1)   When the system reports that the principal may be

granted 2530 approval, the DRS shall take the hard

copy printout from the system and attach it to

Form HUD-2530.  The Chief, AHMB, shall sign Part

II of the form and place a check in Block A.  The

DRS then shall forward the form to the Field

Office Manager or, in co-located offices, the

Regional Public Housing Director, for approval.

The Field Office Manager or Regional Public

Housing Director shall write "Approved" next to

the names of the principals in Block 7, Page 1 of

Form HUD-2530, and then date and sign the form.

After approval, the DRS shall notify the PHA.  The

Field Office shall process Form HUD-2530 within

three working days of receipt.

(2)   When the system reports that the principal has to

referred to Headquarters due to a history of

adverse or unsatisfactory performance, as

indicated by either Form HUD-2530 or results of

inquiries to the Farmers Home Administration or

the State Finance Agency, the DRS shall request

review by Regional or Chief Counsel.  Counsel

shall review the sufficiency of evidence to

support a Departmental hearing, as described in

the Previous Participation Handbook 4065.1, The

DRS shall submit the case, along with Counsel's

review, to the Participation Control Officer (PCO)

in Headquarters for either final action or

referral to the Multifamily Participation Review

Committee.  The DRS shall alert the PCO that Form

HUD-2530 will be submitted.  In addition, the DRS

shall notify the PHA of the status of the 2530

clearance.

c.  Contract Review and Approval.  Where submitted by the

PHA, within 10 working days of receipt, the HMS shall

review the proposed contract and prepare a letter to the

PHA for the signature of the Director, Housing

Management Division or designee, advising the PHA of any

required changes or authorizing the PHA to proceed with

execution.  To recommend approval, the HMS shall

determine that the consultant is approved under the    *

9-39                            12/89

_____________________________________________________________________

previous participation review process and and that the

proposed contract contains:

(1)   a clear statement of the specific services,

including tasks, to be performed;

(2)   a description of the methodology to be used in

carrying out the services;

(3)   an identification of the type and frequency of

written reports to be provided to the PHA;

(4)   a time frame for completion of all services that

is related to and coordinated with the physical

improvements;

(5)   a payment schedule that is related to the

successful completion of specific tasks; and

(6)   a total cost that is fair and reasonable.  Where

the total cost exceeds the approved budget amount

and adjustments can be made within the existing

budget, the PHA shall be required to submit a

budget revision.

*        d.  Contract Modification Review and Approval.  Where

submitted by the PHA, within 10 working days of receipt,

the HMS shall review the proposed modification and

prepare a letter to the PHA for the signature of the

Director, Housing Management Division or designee,

advising the PHA of approval, with or without revision,

or disapproval.

e.  Monitoring.  At least twice a year, the HMS shall

monitor management and other professional service

contracts and contract modifications awarded by the PHA

through on-site review of PHA files.  If deficiencies

are found, the Field Office monitoring letter (see

paragraph 10-17a(3)) may require the PHA to submit

proposed contracts and modifications over a reduced

threshold to the Field Office for review and approval

before award.                                          *

9-39.  ABANDONMENT OR TERMINATION.  In the event of abandonment of

the project or termination of the contract for any cause,

under the respective sections of the contract, the terms of

any settlement between the PHA and the consultant shall be

subject to Field Office approval.  The PHA shall not

disburse any monies to the consultant after the giving of

notice of abandonment or termination until the Field Office

has approved the settlement agreement.

12/89                                 9-40