APPENDIX 22

APPENDIX 22. COMPREHENSIVE PLAN FOR MODERNIZATION (CPM)

Purpose

The CPM is the most important source document for PHA planning for

physical and management improvements under CIAP.  The CPM is intended

to be a flexible, dynamic document that serves as the master planning

document for the PHA to upgrade its projects.  The CPM is required

for non-Indian PHAs With 500 units or more in management.

Components of an Approvable CPM

At a minimum, the CPM includes, but is not limited to, the following

major elements:

1.   Description of Basic Project Characteristics

The CPM contains a brief description of each project in the

PHA's inventory so that baseline information on each project is

readily available to PHA and HUD staff.  Depending on the style

or requested format by each Field Office, this information may

be included as a cover to the general project physical and

management needs assessment.

2.   General Project Physical and Management Needs Assessment

The CPM contains a general physical and management needs

assessment for each project in the PHA's inventory, regardless

of whether the PHA plans to request CIAP funding within the next

five years.  The general needs assessment provides the basic

information for the five-year funding request plan and sets

forth strategies for addressing all identified needs.  Such

strategies may include unit conversion, partial demolition or

disposition.

The general project physical needs assessment includes a

description of the physical work currently needed to bring the

project up to the modernization and life-cycle cost-effective

energy conservation standards.  The general needs assessment

should not be confused with the detailed needs assessment that

the PHA must prepare for Joint Review, using Form HUD-52827, as

set forth in the Modernization Standards Handbook 7485.2 REV-1.

The following items are considered in preparing the assessment:

a.   Potential hazards, including lead-based paint and asbestos;

and

Page 1

_____________________________________________________________________

APPENDIX 22

b.   Section 504 compliance, including incorporating the results

of the Transition Plan, where applicable, into the general

physical needs assessment for each affected project.

The management needs assessment addresses the improvement areas

set forth in paragraph 2-3b of this Handbook for each project in

the PHA's inventory, but may reference PHA-wide needs.

3.   Project Viability Reviews

The CPM contains a PHA-conducted project viability review for

each project in the PHA's inventory in accordance with paragraph

3-9 of this Handbook.  As part of the CIAP Application review

process, the Field Office shall review the PHA's own viability

determination to ensure that it is consistent with the Field

Office's own viability determination for the project.

Based upon the results of the project viability revieW, the PHA

must determine if there is a need for partial demolition or

disposition of any project.  If there is such a need, the PHA

should discuss with the Field Office as to what the requirements

are for a demolition or disposition application and how to

proceed.

4.   Five-Year Funding Request Plan

This portion of the CPM serves as the summary planning document

which should assist the PHA in prioritizing its projects for

funding requests over a five-year period.  This summary is

reflected on Form HUD-52824, Five-Year Funding Request Plan,

reflects a five-year rolling base, and is updated annually.

Each year of the five-year plan shall identify projects for

funding by modernization type and the estimated amounts.  The

PHA is not required to include all projects in the five-year

plan since the plan should reflect only what reasonably can be

expected to be funded over the five-year period.

5.   PHA Board Resolution, approving the CPM.

New CPM Requirement for FFY 1991 - Five-Year Management Improvement

Goals

In addition to conducting the general management needs assessment by

project, the PHA must evaluate the overall condition of its

management operation and compare that evaluation to the Performance

Indicators, currently set forth in Chapter 11 of the

12/89                               Page 2

_____________________________________________________________________

APPENDIX 22

Field Office Monitoring of PHAs Handbook 7460.7 REV-1.  Once the PHA

has evaluated its management operation against the Performance

Indicators, and has identified specific management deficiencies

through the management needs assessment, the PHA then shall establish

annual to improve its overall management.  All management

improvements that will be undertaken by project should clearly relate

to the management needs assessment and the Performance Indicators, as

well as the requested physical improvements.  For each area in which

management improvement funding is requested, the PHA shall establish

baseline data and then an annual target for improvement for the area

to be impacted by the requested management improvement funding.

Progress against these targets will be reviewed in determining the

PHA's management capability.

FFY 1990 will be a transition year for the PHA to evaluate its

operation against the Performance Indicators and develop management

improvement goals.  However, these goals will be a requirement for

the FFY 1991 CIAP Application process.

HUD Review and Approval of Original CPM

1.   Field Office Review

In most cases, Field Office review of the original CPM has been

completed.  In those cases where review is still pending, the

Field Office shall review the original CPM using the CPM Review

Checklist at the end of this Appendix to ensure that the

required major elements are present and that certain areas are

properly addressed.  In carrying out this review, the Field

Office shall take the following steps:

a.   Determine the current approval status of all CPMs that have

been previously submitted.  Where HUD review is not

completed, use the CPM Review Checklist.

b.   For those CPMs that have addressed all of the required

major elements, contact the PHA, regarding any necessary

updates to ensure consistency with its CIAP Application.

c.   Send written notice to PHAs With CPMs that are deficient in

one or more areas and that must be corrected before funding

of any additional modernization other than emergency.  In

addressing the identified deficiencies, the PHA also should

consider any necessary updates to the CPM.

2.   Field Office Recommendation

Based on review of the CPM and the results of Step 1 of the

Page 3

_____________________________________________________________________

APPENDIX 22

viability review conducted on each project, excluding those that

have comprehensive modernization in progress, the Field Office,

in most cases, has recommended approval of the original CPM to

the Regional Office by the appropriate deadline date, except

where the CPM was unsatisfactory or incomplete; i.e., the

strategy developed was inconsistent with known physical or

management problems; the proposed physical improvements would

not bring all the PHA's projects up to the modernization and

energy conservation standards; the proposed management

improvements would not address all of the PHA's identified areas

of deficiencies; the CPM was clearly unrealistic in its proposed

actions; or the PHA has not demonstrated that completion of the

improvements would reasonably ensure the long-term viability of

the projects at a reasonable cost.

Conditional Plan Approval

The Regional Office may have given conditional plan approval where

the CPM appears generally reasonable, but one or more of the above

deficiencies exist in the CPM or there were outstanding viability

reviews on projects required to go to Step 2 or beyond.  In such

cases, the Field Office provided a schedule to the Regional Office

for requiring the PHA to correct any identified deficiencies or for

Field Office completion of the viability reviews.

Annual Updates to the Approved CPM

To use successfully the CPM in conjunction with the CIAP Application,

it is necessary for the PHA to review and update annually the CPM as

the first step in preparing the CIAP Application.  It is strongly

recommended that all updates to the CPM be done by the PHA, not a

consultant, to ensure that the updates represent the PHA's own

funding priorities and opinions.  If the PHA wishes to employ a

consultant to update its CPM, the cost is an eligible CIAP cost;

however, the PHA shall ensure that its Board of Commissioners reviews

and approves the update.

PHA's Responsibilities

At the beginning of each FFY, the PHA shall begin to prepare for the

CIAP Application process by reviewing the CPM.

1.   Five-Year Funding Request Plan

The PHA shall revise the five-year rolling base in the Five-Year

Funding Request Plan component of the CPM to reflect the results

of the previous year's funding approvals and to make adjustments

for the projects affected by those funding

12/89                                Page 4

_____________________________________________________________________

APPENDIX 22

decisions.  For example, if a project was identified in the CPM

as requiring funding and received funding to meet all currently

identified physical and management improvement needs, that

project should be removed from the five-year rolling base.

Similarly, if the project was identified in the CPM, but did not

receive all funds requested, and many work items cannot be

addressed, the unfunded portion of the request should be carried

over into the current year.

Once the update of the five-year rolling base is completed, this

element will serve as the basis for the PHA's current year

funding request and will not need to be revised again until the

conclusion of the current year funding cycle.

2.   Physical and Management Needs for Projects Identified in the

Current Year of the Five-Year Funding Request Plan

Once the PHA has revised the five-year rolling base, based on

previous year funding approvals, the PHA then shall begin to

review the projects listed in the current year and revise the

general physical and management needs assessment in preparation

for the CIAP Application process.

For example, a project has been rolled over from year 2 to year

1 (the current year) of the five-year funding request plan.

However, the initial general physical and management needs

assessment was conducted 4 years prior to the current year.

Continued deterioration, inflation, and additional physical work

items and management concerns necessitate an update of the

general needs assessment before the CIAP Application is

developed to ensure that the needs and associated costs are

current.  This update is only necessary for projects now in the

current year of the five-year rolling base.  However, it also

may be advisable for the PHA to conduct this type of update for

other projects.

3.   Project Viability Review

The PHA shall re-evaluate its original determinations of

viability for the projects now in the current year of the

five-year rolling base to ensure that its original

determinations are still applicable.  If certain projects or

buildings are now determined to be non-viable by the PHA, the

PHA shall consider preparing a demolition or disposition

application meeting the requirements of Section 18 of the Act.

In such case, the PHA should consult with the Field Office on

how to proceed.

Page 5                           12/89

_____________________________________________________________________

APPENDIX 22

4.   Five-Year Management Improvement Goals

The PHA shall revise its five-year management improvement goals

to reflect the results of the previous year's funding approvals

and to make adjustments to the projects affected by those

funding decisions, as well as by PHA progress toward its

established goals during the previous year.  This update should

serve as the basis for the PHA's current year funding request.

Field Office's Responsibilities

The Field Office shall review the CPM updates in conjunction with the

CIAP Application.  In accordance with Chapter 3 of the CIAP Handbook

and the processing schedule established in the annual Notice of Fund

Availability, the Field Office Assisted Housing Management Branch

staff, including the General Engineer, Housing Management Specialist,

and Financial Analyst shall review the updates to the CPM to ensure

consistency with the CIAP Application, as follows:

1.   Five-Year Funding Request Plan

The Field Office shall review the current year's five-year

funding request plan and compare it to the previous year's

five-year funding request plan and funding approvals to ensure

consistency of PHA priorities, proposed work and estimated

costs.  Where there are major changes in PHA priorities and

other information, the Field Office shall request an explanation

from the PHA.

2.   Project Viability Review

The Field Office shall review the PHA's own viability

determination for projects for which current year funds are

requested, as well as the Field Office's previously conducted

viability determination for those projects.  The Field Office

shall determine whether, given current circumstances, its prior

determinations are still valid or require updating.

3.   Five-Year Management Improvement Goals

The Field Office shall review the PHA's update of the five-year

management improvement goals and determine whether they are

realistic and consistent with prior year accomplishments.

12/89                               Page 6

_____________________________________________________________________

APPENDIX 22

COMPREHENSIVE PLAN FOR MODERNIZATION (CPM)

AHMB REVIEW CHECKLIST

PHA Name _________________________      No. of PHA Units __________

No. of PHA Projects _______

1.   Does the CPM contain all of the major elements?

a.   Has the PHA included a brief description of each project in

its inventory?

b.   General project physical and management needs assessment

1.    Has the PHA addressed each project in its inventory?

2.    Is there a standardized approach to the general

physical needs assessment by project?

3.    Is the general physical needs assessment complete by

project, addressing work needed to meet mandatory

modernization and energy conservation standards?

4.    Does the general physical needs assessment address

potential hazards, such as lead-based paint and

asbestos?

Page 1                           12/89

_____________________________________________________________________

APPENDIX 22

5.    Does the general physical needs assessment address

Section 504 compliance?

6.    Are the strategies developed by the PHA consistent

with known physical and management problems?

7.    Is the management needs assessment complete by

project?

5.    Are PHA-wide management deficiencies and proposed

solutions properly identified?

c.   Project viability reviews

1.    Is there a clear viability determination for each

project?

2.    If not, which projects have viability issues and what

are the issues?

3.    Is the PHA considerating any demolition or

disposition?

12/89                               Page 2

_____________________________________________________________________

APPENDIX 22

4.    Does each viability review include a determination of

financial feasibility?

5.    Are there any differences between the PHA's and the

Field Office's determinations?  If so, identify the

projects and attach an explanation.

d.   Five-Year Funding Request Plan by Fiscal Year

1.    Do the funds requested by fiscal year reflect what

reasonably can be expected to be received over the

five-year period?

2.    Has the PHA included all of the projects in its

inventory in the five-year rolling base?  If not, how

many projects are outside the current five-year

period?

3.    Is a total need identified for each of the five

years?  If yes, what are the funding levels requested

for:

Year 1:  $ ____________________

Year 2:  $ ____________________

Year 3:  $ ____________________

Year 4:  $ ____________________

Year 5:  $ ____________________

4.    Do the estimated costs include amounts needed for

management improvements?  If yes, how much is

requested for Year 1?

Year 1:  $ ____________________

Page 3

_____________________________________________________________________

APPENDIX 22

e.   Five-Year Management Improvement Goals

1.    Has the PHA conducted an evaluation of its overall

management operation relative to the Performance

Indicators identified in Chapter 11 of the Field

Office Monitoring of PHAs Handbook?

2.    Has the PHA established goals for the improvement of

management deficiencies based on the baseline

comparison to the Performance Indicators?

2.   Does the PHA have the management and modernization capability to

implement the improvements in the CPM in the time period

identified?  Include justification.

OTHER ISSUES RELATED TO HUD REVIEW OF THE CPM

1.   What does the CPM show?

- Level of effort

- Thoroughness

- Completeness of problem analysis

- PHA involvement in the development/update of the CPM

2.   Is the CPM coherent?

- Language

- Organization

3.   Do the solutions presented match the problems?

4.   Do the cost estimates appear reasonable?

5.   Is the implementation plan realistic?

12/89                               Page 4

_____________________________________________________________________

APPENDIX 22

- Does the PHA have the capability to obligate (contract for)

the work identified in the CPM?

- If not, how can the PHA increase its capability?

6.   Does the PHA have a good implementation record from previous

CIAP approvals?

- Timely obligations and expenditures

- Timely and accurate quarterly reports

Page 5                           12/89

_____________________________________________________________________