7485.3 G

CHAPTER 4. HA RESPONSIBILITY: COMPREHENSIVE PLAN

4-1. OBJECTIVE:  The objective of this Chapter is to set forth the

requirements of the Comprehensive Plan, including the Five-Year

Action Plan, and any amendments, and the use of unobligated CIAP

funds for CGP purposes.  Since the requirements for the Annual

Statement, including the HUD review criteria, are statutorily

different from the Comprehensive Plan, the requirements for the

Annual Statement are set forth in Chapter 6.

4-2. POLICY STATEMENT.

A.   In administering the CGP, the Department is required by

Section 14(e)(4)(D)of the Act to respect, to the greatest

extent possible, the professional judgment of the HA's

administrators.  The Department strongly supports this

statutory mandate and has made every effort in the

regulations to provide HAs with maximum discretion and

flexibility in planning and carrying out their modernization

strategies under the CGP, and to ensure accountability for

program funds and activities.  However, the Department is

responsible for ensuring that the HA has identified all of

its physical and management improvement needs, is making

satisfactory progress toward meeting those needs, and is

complying with all statutory and regulatory requirements.

B.   Although the Department believes that the HA is the key

actor in the modernization process, it also believes that

the residents of the public housing and the community's

political leadership share in that responsibility and must

be involved in planning and establishing priorities for the

HA's modernization program.  For this reason, the Department

is requiring, through the public hearing process, that

residents and the local/tribal government be provided with

ample opportunity to participate, not only during the

upfront development of the HAs modernization strategy, but

throughout the ongoing implementation of that strategy.  In

this manner, the Department hopes to foster a local

Partnership among the HA, its residents, and the

local/tribal government, which can jointly develop and

implement the objectives and priorities established in the

HA's modernization strategy.  Refer to Chapter 9 for

specific requirements and guidance on developing this

Partnership.

4-3. PURPOSE OF COMPREHENSIVE PLAN.  The Comprehensive Plan is the

focal point of the HA's modernization strategy.  It identifies

all of the physical and management improvements needed for the HA

and all of its

4-1

7485.3 G

developments that represent eligible costs under Chapter 2,

irrespective of funding availability.  The Comprehensive Plan

sets forth strategies and a plan of action, which will bring the

HA and its developments up to the following standards:

A.   The modernization and energy conservation standards under

Section 14(e)(1)(A)(ii) of the Act, which are prescribed in

'968.115 or '950-610 and set forth in the Modernization

Standards Handbook 7485.2, as revised; a life-cycle cost

analysis, where appropriate; and the lead-based paint (LBP)

testing and abatement requirements in '968-110(k) and

'950.120(i); and

B.   For PHAs, an acceptable level of performance with respect to

the management areas under Section 14(e)(1)(B) of the Act,

the Public Housing Management Assessment Program (PHMAP) at

24 CFR Part 901, and other areas deemed necessary by HUD and

identified through audits or HUD monitoring reviews; or

C.   For IHAs, an acceptable level of performance with respect to

the management areas under Section 14(e)(1)(B) of the Act

and other areas deemed necessary by HUD and identified

through audits or HUD monitoring reviews.  HUD is not using

the PHMAP to assess the IHA's management needs since IHAs

are specifically excluded from PHMAP coverage by Section 527

of the National Affordable Housing Act (NAHA) of 1990; and

D.   For both PHAs and IHAs any additional management needs which

the HAs want to address to ensure the long-term viability of

their developments and to improve the effectiveness and

efficiency of their management operations.

4-4. SUBMISSION AND COMPONENTS OF COMPREHENSIVE PLAN.  In its first

year of participation in the CGP and every sixth year thereafter,

the HA shall develop and submit a Comprehensive Plan.  The HA may

amend any portion of its Comprehensive Plan at any time.  The

Comprehensive Plan is comprised of the following documents: [Sec.

14(e)(1)(A) through (H)]; ['968315 or '950.652]

A.   Executive Summary (see paragraph 4-6);

B.   Physical Needs Assessment (see paragraph 4-7), including the

long-term viability and reasonable cost analysis (see

paragraph 4-8);

4-2

7485.3 G

C.   Management Needs Assessment (see paragraph 4-9);

D.   Five-Year Action Plan (see paragraph 4-10);

E.   Local Government Statement (see paragraph 4-11);

F.   HA Board Resolution, including civil rights statement (see

paragraph 4-12); and

G.   Annual Statement (see Chapter 6).

4-5. RESIDENT AND LOCAL/TRIBAL GOVERNMENT PARTICIPATION.  The HA shall

develop, implement, and monitor the Comprehensive Plan, and

thereafter annually amend portions of the Plan (both for purposes

of adding a new fifth year to the rolling base of the Five-Year

Action Plan, and reflecting any necessary changes to the approved

Physical and Management Needs Assessments), in consultation with

residents of all developments covered by the Comprehensive Plan

and with appropriate local/tribal officials.  Refer to Chapter 9

for specific requirements and guidance. ['968.315(b) and (c)     or

'950.652(b) and (c)]

4-6. EXECUTIVE SUMMARY.  As part of the Comprehensive Plan, the HA

shall prepare the Executive Summary to facilitate review and

comprehension of the other documents in the Comprehensive Plan by

residents, local/tribal government, and the public.  For that

reason, it is important that the Executive Summary be clear and

succinct and allow for easy comparison among developments so that

persons not intimately familiar with the details may assess the

relative needs, overall modernization strategy and funding

priorities of the HA. The Executive Summary shall include the

following items:    ['968315(e)(1) or '950.652(d)(1)]

A.   Summary of Preliminary Estimated Costs.  The HA shall

complete Form HUD-52831, Executive Summary of Preliminary

Estimated Costs, which summarizes for each development in

the HA's inventory which is eligible for CGP funding, the

total preliminary estimated hard cost (physical improvement

cost) to meet the modernization and energy conservation

standards and to comply with other program requirements, the

per unit hard cost, whether the development has long-term

physical and social viability under paragraph 4-8, and the

percentage of vacant units.  The form also provides for, on

a HA-wide basis, the total preliminary estimated cost for

management/operations needs, nondwelling structures and

equipment, administration, and other current needs or future

needs within the next five years.  A sample Form HUD-

4-3

7485.3 G

52831 with instructions is contained in Appendix 4-1.

B.   Description of Resident Partnership and Summary of General

Issues. The HA shall prepare a specific description of its

process for maximizing the level of participation by

residents during the development, implementation and

monitoring of the Comprehensive Plan.  The HA also shall

prepare a summary of the general issues raised by residents,

local/tribal officials, and others during the public comment

process and the HA's response to those general issues.  The

HA is not required to respond to each comment.  The HA shall

maintain records, such as minutes of planning meetings or

resident surveys, in its files and make available such

records to residents, duly elected resident councils, and

other interested parties upon request.  Refer to Chapter 9

for specific requirements and guidance.

4-7. PHYSICAL NEEDS ASSESSMENT.  As part of the Comprehensive Plan,

the HA shall prepare Form HUD-52832, Physical Needs Assessment,

for each development in its inventory which is eligible for CGP

funding, providing a general description of all unfunded physical

improvements that the HA would need to undertake to bring that

development including dwelling and nondwelling structures,

dwelling and nondwelling equipment, and site, to a level at least

equal to the modernization and energy conservation standards and

to comply with other program requirements.  The HA also shall

prepare a separate Physical Needs Assessment for all HA-wide

nondwelling needs and a separate Physical Needs Assessment for

all planned use of modernization funds for development.  The HA

shall develop the Physical Needs Assessment without regard to the

availability of funds. ['968.315(e)(2) or '950.652(d)(2)]

A.   Preparation.  The HA is required to carry out a general, not

a detailed, physical needs survey of each development,

listing major work categories, not every single work item.

The HA is encouraged to analyze its physical needs in light

of its past modernization experience, particularly where

approaches other than straight rehabilitation are required

to ensure long-term viability, and to consult the locality

and residents, including persons with disabilities or

advocacy groups representing persons with disabilities, in

developing alternative strategies.  However, in preparing

the Physical Needs Assessment for each development, the HA

shall consider the following:

1.   Reasons for any vacancies and strategy and work necessary

to return the units to occupied status.

4-4

7485.3 G

2.   Work necessary to ensure long-term viability, such as

conversion from family to elderly, change in bedroom

sizes, partial demolition/disposition to assure the

useful life of the remaining portion of the development

(e.g., reduce density or create open space), or other

physical design changes.

3.   Work necessary to comply with Federal requirements or

State and local/tribal codes, such as elimination of

asbestos.

4.   Replacement needs of equipment, systems and structural

elements that are likely to be needed within the next

five years, assuming routine and timely maintenance is

performed.

5.   Work necessary to meet Housing Quality Standards (HQS)

(see subparagraph C).

6.   LBP testing and abatement requirements in accordance

with the LBP Poisoning Prevention Act and HUD

implementing regulations at 24 CFR Part 35, as well as

the requirements for professional risk assessments and

interim containment.  HUD strongly recommends that the

HA use the Guidelines for the Evaluation and Control of

LBP Hazards in Housing published in July 1995, to

assist with the identification of its LBP needs.

7.   Work necessary to meet physical accessibility

requirements relating to substantial and other

alterations under 24 CFR 8.23.

8.   Physical disparities between buildings occupied

predominantly by minorities and those by non-minorities

and the physical improvements required to correct the

disparities.  Note:  This does not apply to IHAs

established under tribal law or to IHAs established

under State law which have been determined not to be

subject to Title VI of the Civil Rights Act of 1964 or

the Fair Housing Act.

9.   Number of vacant or non-homebuyer-occupied Turnkey III

units that the HA is proposing for substantial

rehabilitation and subsequent sale in accordance with

paragraph 2-4C.

10.  Development deficiencies which require correction and are

eligible for CGP funding in accordance with paragraph 2-5B.

4-5

7485.3 G

11.  Need for nondwelling space and equipment, such as

playgrounds, laundry facilities, and day care centers.

Note:  Since the CGP is intended to fund physical

improvements of a capital nature, the HA shall address

routine and preventive maintenance with operating, not CGP,

funds, except as provided in paragraph 2-18.

B.   Sources of Information.  The HA shall identify on the

Physical Needs Assessment the source(s) of information from

which it derived data to develop the general description of

needed physical improvements.  The HA shall retain such

information in its files (1) as supporting documentation for

the information submitted on the Physical Needs Assessment,

(2) for post-review by the FO, residents or community

members, or (3) for submission to the FO upon request.

Sources of information available to the HA in preparing the

Physical Needs Assessment for each development may include,

but are not limited to:

1.   Previous physical needs assessments undertaken; e.g., to

prepare for Joint Review under the CIAP;

2.   HA annual inspection reports of dwelling units;

3.   HA maintenance records, including work orders;

4.   Resident complaint records;

5.   HA schedule for LBP testing and the results of LBP

testing and professional risk assessments;

6.   HA needs assessment and/or transition plan for physical

accessibility.  The HA shall not submit this assessment

and/or plan to the FO, but shall retain them in its

files;

7.   Energy audit updates; and

8.   Recent HUD review reports, containing recommendations for

improvements.

C.   Housing Quality Standards (HQS).  The HQS does not apply to

IHAS.

1.   Section 14(e)(1)(B) of the Act requires a PHA to

provide an assessment of improvements needed to upgrade

the management and operation of the PHA so that decent,

safe and sanitary living conditions will be provided.

Accordingly, the

4-6

7485.3 G

Department is using the habitability standard

established under the HQS or any equivalent standard

such as local habitability (see '882.109) as a useful,

interim measure of PHA progress toward meeting the

modernization and energy conservation standards.

2.   PHA progress towards bringing its units up to the HQS

will be monitored under the PHMAP.

3.   Each physical work item, such as replacement of hot

water heaters, which is carried out by the PHA under

the CGP shall comply with the modernization and energy

conservation standards.

D.   Completion of Assessment.  After the HA has considered the

items in subparagraphs A through C, the HA shall complete

one Form HUD52832, Physical Needs Assessment, for each

development and, where appropriate, one form for HA-wide

nondwelling needs and one form for any planned use of

modernization funds for development.  Multifamily

developments which are contiguous and treated as one

development for management purposes may be grouped together;

scattered site units which are treated as one entity for

management purposes also may be grouped together.  If the HA

has no physical improvement needs at a particular

development at the time it completes the Comprehensive Plan

and no replacements are likely to be required within the

next five years, the HA shall provide a statement to that

effect on the Physical Needs Assessment for that

development.  Such a statement does not preclude the HA from

amending the Physical Needs Assessment at any time within

the five-year period if unforeseen needs arise or from

identifying new needs which have occurred when the

Assessment is revised every sixth year.  Similarly, if the

HA intends to demolish, partially demolish, convert, or

dispose of a development (or units within a development), it

must so indicate.  A sample Form HUD-52832 with instructions

is contained in Appendix 4-2.

4-8. LONG-TERM VIABILITY AND REASONABLE COST ANALYSIS.  Section

14(e)(1)(C) of the Act requires an analysis on a development-by-

development basis in accordance with standards and criteria

prescribed by HUD, demonstrating that completion of the

identified physical and management improvements will reasonably

ensure the long-term physical and social viability, including

achieving structural/system soundness and fun occupancy, of each

development at a reasonable cost.  For cost reasonableness, the

HA shall determine whether the unfunded hard costs satisfy the

definition of reasonable cost which is: total unfunded

4-7

7485.3 G

hard costs needs for a development do not exceed 90% of the

computed Total Development Cost (TDC) for a new development with

the same structure type and number and size of units in the

market area.  Unfunded hard cost needs exclude any prior year

funding for the development.  For each development, the HA shall

indicate on Form HUD-52832, Physical Needs Assessment, whether

the development has long-term physical and social viability.

['968.315(e)(4) or '950.652(d)(4)]

A.   Determination of CGP Hard Cost Limit.  Where the estimated

per unit unfunded hard cost at a development is equal to or

less than the per unit TDC limit for the smallest bedroom

size at that development for the appropriate structure type,

the HA is not required to compute the TDC limit for the

entire development.  In all other cases, the HA shall

compute the TDC limit, as follows:

1.   Computation of TDC Limit.  To compute the TDC limit,

the HA shall obtain the most recently published TDC

figures for the type and size of units that will be in

the development after modernization; i.e., following

any conversion, demolition or other unit changes.  The

HA shall not adjust the published TDC figures for

inflation or other reasons.  After the HA has computed

the TDC limit for the development, the HA shall

multiply that amount by 90% to determine the CGP hard

cost limit.  The HA shall then compare the estimated

unfunded hard cost needs of the development to the CGP

hard cost limit (90% of the TDC limit).  The following

example illustrates this computation for a walkup

development in the Northeast:

Number of

Size of             Units After         Unit                Total

Bedrooms            Modernization       Cost                TDC Cost

O-BR                     20   x         $26)250   =         $  525,000

1-BR                     20   x         $31,350   =         $  627,000

2-BR                     30   x         $34,700   =         $1,041,000

3-BR                     10   x         $41,400   =         $  414,000

TDC Limit                                                   $2,607,000

CGP Hard Cost limit (90% of TDC)                            $2,346,300

2.   Averaging Not Allowed.  If the development contains

dissimilar types of structures,, such as a mid-rise with

several low-rises, the HA shall separately compute the

TDC limit for

4-8

7485.3 G

each type of structure.  The HA shall not average the

modernization cost for dissimilar structures so that the

less costly modernization on one type of structure

disproportionately carries the more costly modernization

on the other type of structure.

3.   Family High-Rises.  To compute the TDC limit for family

highrises where there are no published figures for units

with three or more bedrooms, the HA shall multiply the

two-bedroom TDC figure for elevator structures for each

additional bedroom by the factor provided below.  The

following example illustrates how to calculate the TDC

limit for a 250-unit family high-rise development:

Number of

Size of        Units After                   Unit           Total

Bedrooms       Modernization                 Cost           TDC

Cost

1-BR                50   x                   $21,000 =      $1,050,000

2-BR                50   x                   $25,000 =      $1,250,000

3-BR                50   x(1.20x$25,000)     $30,000 =      $1,500,000

4-BR                50   x(1.39x$25,000)     $34,750 =      $1,737,500

5-BR                50   x(1.48x$25,000)     $37,000 =      $1,850,000

TDC Limit                                                   $7,387,500

CGP Hard Cost Limit (90% of TDC)                            $6,648,750

4.   Over Six-Bedroom Units.  For detached or semi-detached

units and row dwellings, the TDC limit for a 7-bedroom

unit is derived by multiplying the 6-bedroom TDC figure

by a factor of 1.03. The TDC for a 8-bedroom unit is

calculated by multiplying the 6-bedroom TDC figure by a

factor of 1.05. For example:

$60,250 (6-bedroom) x 1.03 = $62,058 (7-bedroom)

$60,250 (6-bedroom) x 1.05 = $63,263 (8-bedroom)

5.   Scattered Site Units.  The HA shall calculate the TDC

limit for the entire scattered site development.

However, before actually expending funds on other than

emergency work for an individual scattered site unit, the

HA shall determine whether the unfunded hard cost needs

for the individual unit exceed 90% of the TDC limit; if

so, refer to subparagraph C.

4-9

7485.3 G

B.   At or Below the 90% Limit.  Where the preliminary estimate of

unfunded hard cost needs for a development is 90% or less of

the TDC limit, no further action is required unless the HA

determines that the development does not have long-term social

and physical viability, despite its reasonable cost.  The HA

shall not submit evidence of computation of the TDC limit as

part of its Comprehensive Plan, but shall retain such evidence

for each development in its files (1) as supporting

documentation for the information submitted on Form HUD-52832,

Physical Needs Assessment, (2) for post-review by the FO, or

(3) for submission to the FO upon request.

C.   Exceeding the 90% Limit

1.   HA Request.  Except for emergencies and essential

nonroutine maintenance necessary to maintain

habitability, the HA shall not expend any CGP funds on a

development, unless the HA has requested, and HUD has

approved the request to exceed 90% of the TDC limit.

Where the HA wishes to fund such a development, the HA

shall submit, as part of the Comprehensive Plan, a

written justification, including the following

information:

a.   Estimated hard cost by development account and work

item;

b.   Explanation of any special or unusual physical

conditions at the development, including site and

nondwelling structures, such as LBP abatement or

physical accessibility needs;

c.   Justification for all work as necessary to meet the

modernization and energy conservation standards,

and to develop a modest, non-luxury development

that provides for efficient design, durability,

energy conservation, safety, security, economical

maintenance, and healthy family life in a

neighborhood environment;

d.   Description of efforts made to reduce costs;

e.   Explanation of why rehabilitation of the existing

development is more cost-effective in the long-term

than construction or acquisition of replacement

housing;

4-10

7485.3 G

f.   If applicable, explanation of why the HA has no

practical low-income housing alternative; and

g.   Alternative HA strategies which the HA considered,

such as:

(1)  Changes in its occupancy policy;

(2)  Partial demolition of selected buildings to

reduce density or create open space;

(3)  Revision to rehabilitation approach to reduce

costs and make the development feasible to

modernize at a reasonable cost;

(4)  Reconfiguration of unit sizes to accommodate

the applicants on the waiting list or for

other reasons; and

5)   Design changes to enhance development

security.

2.   Timing of HA Request.  If the HA plans to include the

development in the Five-Year Action Plan or Annual

Statement for expenditure of funds for other than

emergencies, the HA shall submit its request to exceed

90% of the TDC limit as part of the Annual Submission in

Chapter 6.

3.   Criteria for HUD Review and Approval of HA Request.  HUD

review and approval criteria are:

a.   HA has provided complete and accurate information

as required by subparagraph C1; and

b.   HA has adequately explained any special or unusual

conditions, justified all work as necessary to meet

the modernization and energy conservation standards

and provide a modest, non-luxury development,

provided reasonable cost estimates, and made every

effort to reduce costs; and

c.   Rehabilitation of the existing development is more

costeffective in the long-term than construction or

acquisition of replacement housing; or

d.   There are no practical alternatives for replacement

housing.

4-11

7485.3 G

4.   FO Action on HA Request.  The FO has disapproval

authority, but not approval authority.  After review of

the HA request against the criteria set forth in

subparagraph C3 and conduct of any on-site review, as

necessary, the FO shall take one of the following steps

within 30 calendar days of receipt of the HA's request:

a.   Where the FO determines that the HA request does

not meet the approval criteria in subparagraph C3,

the FO shall disapprove the request to exceed 90%

of the TDC limit.  The FO shall notify the HA in

writing and explain the reasons for disapproval; or

b.   Where the FO determines that the HA request does

meet the approval criteria in subparagraph C3, the

FO shall submit its recommendation for approval to

Headquarters for review and final action.

4-9. MANAGEMENT NEEDS ASSESSMENT. As part of the Comprehensive Plan, the

HA shall prepare Form HUD-52833, Management Needs Assessment,

identifying all improvements (including those with no cost) needed

to upgrade the management and operation of the HA and of each

viable development so that decent, safe and sanitary living

conditions will be provided.  The Management Needs Assessment shall

include the mandatory improvements in subparagraph B and may

include the optional improvements in subparagraph C. The HA shall

develop the Management Needs Assessment without regard to the

availability of funds.  However, many management improvements may

be made at no cost.  A sample Form HUD-52833 with instructions is

contained in Appendix 4-3. ['968.315(e)(3) or '950.652(d)(3)]

A.   Determination of Needs.  HAs are cautioned that the

identification of management improvements may be difficult in

that the obvious improvement may not be the improvement needed

to correct the deficiency.  For example, the HA may attribute

the large number of vacancies, identified under the PHMAP, to

a lack of modernization funding.  However, closer examination

may reveal that the vacancies also are caused by a lack of

coordination between maintenance and occupancy staff.  The HA

shall attempt to identify the root cause(s) of the problem so

that appropriate improvements may be identified.

B.   Mandatory Improvements.  The Management Needs Assessment shall

identify the most current needs related to the mandatory areas

listed below, indicate the relative urgency of need, and

4-12

7485.3 G

estimate the cost, if any.  To the extent that any of these

needs are addressed in an existing HUD-approved Memorandum of

Agreement (MOA) or Improvement Plan (IP) for PHAs or

Management Improvement Plan (MIP) for the HA may simply

include a cross-reference to that document.

1.   The management, financial, and accounting control systems

of the HA,

2.   The adequacy and qualifications of personnel employed by

the HA in the management and operation of its

developments, for each significant category of

employment;

3.   The adequacy and efficacy of resident programs and

services, resident and development security, resident

selection and eviction, occupancy, maintenance, resident

management and resident capacity-building programs,

resident opportunities for employment and business

development and other self-sufficiency opportunities for

residents, and homeownership opportunities for residents;

4.   Open audit findings; and

5.   For PHAS:

a.   management deficiencies identified in an existing

HUD- approved MOA or IP based on the PHMAP.  Note:

Under PHMAP, a management deficiency exists where

the PHA received a grade of "F" on any indicator or

received a grade of "D" or "E" on any indicator and

was required by the FO to have an MOA or IP;

b.   management deficiencies identified under the PHMAP

(after HUD determination of any PHA appeal of

scores), but for which the PHA has not yet

submitted to HUD the required MOA or IP; in such

case, the PHA may identify submission to HUD of the

MOA or IP which meets the PHMAP requirements, as an

improvement activity; and

c.   management deficiencies not identified under the

PHMAP but through HUD monitoring.

6.   For IHAs, management deficiencies under '950.135,

regardless of whether there is an MIP, or identified

through HUD

4-13

7485.3 G

monitoring and the Risk Assessment and Determination

for Allocation of Resources (RADAR).

C.   Optional Improvements.  The Management Needs Assessment may

identify, at the HA's option, any other management and

operations needs which the HA wants to address at either the

HA-wide or development level, with the relative urgency of

need indicated.  These may include improvements identified

through:

1.   HA self-assessment, such as its administration of equal

opportunity requirements; or

2.   PHMAP for PHAS, RADAR for IHAS, or in other ways not

addressed in subparagraph B, where the HA wishes to

attain a higher level of performance.  For example,

under the PHMAP the grade of "C' is considered to be a

satisfactory level of performance for a graded

indicator.  Where the PHA received a grade of "D" or

"E" on an indicator, but was not required by the FO to

have an MOA or an IP, the PHA may elect to address the

improvement of its performance under the indicator.

This also applies where the PHA received a grade of "B"

or "C" on an indicator, but wishes to improve its

performance, maximize its efficiency or reduce costs.

D.   Cost Estimates.  The Management Needs Assessment shall

include a preliminary cost estimate for each identified need

and a grand total.

E.   Sources of Information.  The HA shall identify on the

Management Needs Assessment the source(s) of information

from which it derived data to develop the general

description of management/operations needs.  The HA shall

retain such information in its files (1) as supporting

documentation for the information submitted on the

Management Needs Assessment, (2) for post-review by the FO,

residents or community members, or (3) for submission to the

FO upon request.

Note:  If there are no current management needs and the HA does

not anticipate any needs within the next five years, the HA shall

provide a statement to that effect on the Management Needs

Assessment.  Such a statement does not preclude the HA from

amending the Management Needs Assessment at any time within the

five-year period if unforeseen needs arise or from identifying

new needs which have occurred when the Assessment is revised

every sixth year.

4-14

7485.3 G

4-10.FIVE-YEAR ACTION PLAN. ['968.315(e)(5) or '950.652(d)(5)]

A.   General.  As part of the Comprehensive Plan, the HA shall

prepare Form HUD-52834, Five-Year Action Plan, to carry out

the improvements and replacements identified in paragraphs

4-7 and 4-9.  The first year of the five-year period is

covered by the Annual Statement.  Years two through five are

covered by the Five-Year Action Plan.  A sample Form HUD-52834

with instructions is contained in Appendix 4-4.

B.   Rolling Base. While it is expected that some HAs will be

able to address all of their current backlog needs in the

initial five-year period, many HAs will need a longer time

period in which to do so.  For this reason and because all

HAs will continue to accrue additional modernization needs

each year, the Five-Year Action Plan has a rolling base.  A

rolling base means that the Five-Year Action Plan must be

annually updated to eliminate the previous year and add an

additional fifth year so that it always covers the present

five-year period, be with the current year.

C.   Funding Estimates.  In developing the Five-Year Action Plan,

the HA shall assume that the current year formula amount

will be available in each year of years two through five,

plus the HA's estimate of the funds that will be available

from other private and public sources, such as State and

local/tribal government funds, operating funds, Community

Development Block Grant funds, unobligated CIAP funds being

reprogrammed for CGP purposes, etc.  All work specified in

the Five-Year Action Plan is contingent upon the

availability of funds.

D.   Setting Priorities.  The HA shall consider the urgency of

need assigned to work on the Physical Needs Assessment.  In

addition, the HA shall give priority to activities required

to:

1.   correct emergency conditions, as defined in paragraph

1-6; and

2.   meet statutory or other legally mandated requirements,

such as compliance with a court-order or voluntary

compliance agreement.

Note:  In setting priorities, the HA is responsible for

determining the appropriate sequencing and coordination of

work to maximize dollars and avoid waste.

4-15

7485.3 G

E.   Annual Revision.  The HA shall maintain a current Five-Year

Action Plan by annually amending its Action Plan, in

conjunction with the Annual Submission (see Chapter 6).

4-11.LOCAL GOVERNMENT STATEMENT.  As part of the Comprehensive Plan, and

with each Annual Submission, the HA shall obtain a signature on

Form HUD-52835, Local Government Statement, from each

jurisdiction in which HA developments covered by the

Comprehensive Plan are located.  For IHAs established pursuant to

tribal ordinance, the IHA shall obtain a statement from each

tribe pursuant to whose ordinance the IHA was established or in

whose jurisdiction its area of operation extends.  For IHAs

established pursuant to State law, the IHA shall obtain a

statement from each tribe that petitioned for the creation and

the development of the IHA or that participates in or is

responsible for the development of policy and oversight of the

IHA.  For Alaska IHAs, consult HUD Counsel.  A sample Form HUD-52835

is contained in Appendix 4-5.  Form HUD-52835 is signed by

the chief executive officer (CEO) or Indian governing tribal

official, as defined in paragraph 1-6, of the unit of general

local government or Indian tribe. ['968.315(e)(6) or

'950.652(d)(6)]

A.   Certification.  The Local Government Statement certifies

that:

1.   The HA developed the Comprehensive Plan/Annual

Statement in consultation with local government

officials/Indian tribal officials and with residents of

the developments covered by the Comprehensive

Plan/Annual Statement, in accordance with the

requirements of the CGP;

2.   The Comprehensive Plan/Annual Statement is consistent

with:

a.   For PHAS, the unit of general local government's

assessment of its low-income housing needs (as

evidenced by its Consolidated Plan under 24 CFR

Part 91, if applicable), and that the unit of

general local government will cooperate in

providing resident programs and services; or

b.   For IHAs, the appropriate governing body's

assessment of its low-income housing needs and

that the appropriate governing body will cooperate

in providing resident programs and services.

3.   The HA's proposed drug and crime elimination activities

are coordinated with and supportive of local strategies

and

4-16

7485.3 G

neighborhood improvement programs, if applicable.

Under the Cooperation Agreement, the local/tribal

government is providing public services and facilities

of the same character and to the same extent to Public

and Indian housing as are furnished to other dwellings

and residents of the locality.  Where additional on-duty

police are being funded under the CGP, such police

will only provide additional security and protective

services over and above those for which the

local/tribal government is contractually obligated to

provide under the Cooperation Agreement.

B.   Consolidated Plan (Not Applicable to IHAs).  The

Consolidated Plan requires a description of the number of

public housing units in the jurisdiction, their physical

condition, and the restoration and revitalization needs of

the public housing developments within the jurisdiction.  In

addition, the Consolidated Plan requires the strategy of the

PHA and the jurisdiction for improving the management and

operation of public housing developments and the living

environments of low- and very low-income families residing

in public housing.  Since the Consolidated Plan,includes

substantial information about public housing modernization

needs, it is recommended that the PHA and local government

work closely together to identify and plan for those needs.

A simple way to coordinate the Consolidated Plan and the CGP

Comprehensive Plan after the first year is for the

Consolidated Plan to be amended to cross-reference the

Reapproved CGP Comprehensive Plan.

C.   Use of Advisory Group.  In the case of the HA with

developments in more than one jurisdiction, the HA may

submit to the FO, with the Comprehensive Plan or Annual

Submission, Form HUD-52835 signed by an advisory group

representative of the participating jurisdictions in lieu of

Form HUD-52835 from the CEO of each participating

jurisdiction.  In such case, the CEO of each jurisdiction

participating in the advisory group shall state in a written

letter to the advisory group that the certifications set

forth in Form HUD-52835 are true for its jurisdiction.

Therefore, the advisory group is only for administrative

convenience and not a means to circumvent local/tribal

government certifications.

D.   Inability to Obtain Form HUD-52835.  Where the HA is unable

to obtain a signed Form HUD-52835 from certain

jurisdictions, the HA shall submit to the FO, with the

Comprehensive Plan or Annual Submission, a statement that

the HA will not expend any funds from the annual grant in

the identified jurisdictions and that the HA consulted with

the local/tribal government officials and residents of the

developments in such jurisdictions regarding the

Comprehensive Plan or Annual Submission.

4-17

7485.3 G

4-12.     HA BOARD RESOLUTION.  As part of the Comprehensive Plan, and

with each Annual Submission, the HA shall submit to the FO

Form HUD-52836, HA Board Resolution Approving Comprehensive

Plan or Annual Statement.  Form HUD-52836 approves the

Comprehensive Plan or Annual Statement or any amendments and

certifies that the HA has complied or will comply with HUD

requirements.  Where the HA is an agency of the local

government and has no legally responsible Board, the mayor

or legal designee shall sign the Resolution.  A sample Form

HUD-52836 is contained in Appendix 4-6. ['968.315(e)(7) and

'950.652(d)(7)]

4-13.     USE OF UNOBLIGATED CIAP FUNDS FOR CGP PURPOSES.  HAs have

the flexibility to use previously approved, but unobligated

CIAP funds for the approved CIAP work items or for different

work items which are consistent with the HA's Physical and

Management Needs Assessments and Five-Year Action Plan under

the CGP. [Sec. 14 (o)]; ['968.101(c) or '950.600(c)]

A.   HA Submission.  If the HA elects to use any previously

approved, but unobligated CIAP funds for work items under the

CGP, the HA shall submit the following items to the FO with

the initial submission of the Comprehensive Plan or at any

subsequent time:

1.   Revised Forms HUD-52825 (CIAP Budget), with brief

narrative explanations of the proposed revisions;

2.   Evidence of consultation with the residents of the

developments affected by the revisions.  Note:  The CGP

advance meeting and public hearing requirements do not

apply; and

3.   HA Board Resolution approving the proposed revisions to

the CIAP Budget(s).

B.   FO Review.  The FO shall review the proposed budget

revisions in accordance with the following criteria.

1.   The HA has submitted all required material under

subparagraph A;

2.   The proposed work items are eligible modernization

costs; and

4-18

7485.3 G

3.   The proposed management and physical improvements are

set forth in the Physical and/or Management Needs

Assessments and the Five-Year Action Plan.

C.   FO Action.

1.   Approval.  Where the proposed budget revisions meet the

criteria in subparagraph B, the FO shall approve the

revisions and notify the HA of approval within 75

calendar days of receipt of the Comprehensive Plan in

accordance with the procedures in paragraph 5-5 or,

where submitted after Comprehensive Plan approval,

within 21 calendar days of receipt.  Where approval

results in adding or deleting developments from the

original CIAP Budget, an ACC amendment is required for

CIAP Budgets approved before 1993.

2.   Disapproval.  Where the proposed budget revisions do

not meet the criteria in subparagraph B, the FO shall

disapprove the revisions and notify the HA of

disapproval, including the reasons, within 75 calendar

days of receipt of the Comprehensive Plan in accordance

with the procedures in paragraph 5-5 or, where

submitted after Comprehensive Plan approval, within 21

calendar days of receipt.

4-14.AMENDMENTS TO COMPREHENSIVE PLAN. The HA shall submit amendments

to the Comprehensive Plan to the FO for review and approval as

required below: [Sec. 14(e)(3)(B)]; ['968315(f) or '950.652(e)]

A.   Annually.  The HA shall submit an annual update of the Five-

Year Action Plan, eliminating the previous year and adding

an additional fifth year, as part of the Annual Submission.

The annual update of the Five-Year Action Plan is required

even when all remaining needs and anticipated replacements

will be funded during the five-year period or even where

there are no current or anticipated needs.  In such cases,

the HA shall indicate the amount of the annual grant which

will be placed into the replacement reserve (see paragraph

2-7).  See paragraph 6-5 for the Annual Submission

requirements.

B.   As Needed.  The HA shall revise its Physical or Management

Needs Assessments whenever it wishes to carry out activities

in its Five-Year Action Plan or Annual Statement that are

not reflected in its current needs assessments, except in

the case of emergencies.  Also, when the needs assessments

have substantially changed, the HA may submit an amendment

to its needs assessments.

4-19

7485.3 G

The HA may submit amendments and a Board Resolution

approving the amendments at the time of the next Annual

Submission or at any other time during the year.  Examples

of revisions include:

1.   A revised Form HUD-52832, Physical Needs Assessment,

for any development whose physical needs have

significantly changed since the last needs assessment

was undertaken, and now need to be reflected in the

Five-Year Action Plan, excluding changes occurring

because of work previously funded and completed under

the CIAP or the CGP or with other funding sources.

Changed needs may be due to such factors as the need

for partial demolition in lieu of total rehabilitation,

a redetermination of long-term viability, HUD

disapproval of the HA's request to exceed 90% of TDC,

the results of LBP testing, or accelerated

deterioration of the property.

2.   A revised Form HUD-52833, Management Needs Assessment,

where the management needs have significantly changed

since the last needs assessment was undertaken, and now

need to be reflected in the Five-Year Action Plan,

excluding changes occurring because of work previously

funded and completed under the CIAP or the CGP or with

other funding sources.  Changed needs may be due to

such factors as a revised assessment of management

performance, resulting in a new or revised MOA or IP

for PHAs or MIP for IHAs, audit or other monitoring

findings, or an HA self-assessment.

C.   Every Six Years.  To ensure that the HA's needs assessments

remain reasonably current, the HA shall submit a complete

revision of its Comprehensive Plan every sixth year from the

initial year of participation.  The revision shall reflect

the deletion of physical and management needs already funded

and the addition of any new needs which have occurred since

the last update, including any replacements likely to be

needed during the second five-year period.  The HA shall

submit the following revisions, with the Annual Statement,

in the sixth year:

1.   Executive Summary, under paragraph 4-6;

2.   Form HUD-52832, Physical Needs Assessment, for each

development under paragraph 4-7;

4-20

7485.3 G

3.   Form HUD-52833, Management Needs Assessment, under

paragraph 4-9;

4.   Form HUD-52834, Five-Year Action Plan, under paragraph

4-10;

5.   Form HUD-52835, Local Government Statement under

paragraph 4-11; and

6.   Form HUD-52836, PHA/IHA Board Resolution Approving

Comprehensive Plan or Annual Statement, under paragraph

4-12.

D.   FO Review and Action.  The FO shall review and act on the

amendments in accordance with Chapter 5.

4-21