U.S. Department of Housing and Urban Development

Originating Organization:  Office of Housing

_______________________________________________________________________

Special Attention of:             Interim Notice H 93-2 I

Regional Directors of Housing

Housing Management Directors      Issued:  1/19/93

Resident Initiative Specialists   Expires: 5/31/93

Resident Initiative Leaders       ________________________________________

Regional Counsel                  Cross References:  24 CFR Part 248,

Regional Accounting Division          Handbook 4350.6, Notice H 92-81

_______________________________________________________________________

///////////////////////////////////////////////////////////////////////////

Subject:    Actions Subsequent to Notification of Funding Approval

for Preservation Technical Assistance Planning Grants

TABLE OF CONTENTS

1.   Purpose

2.   Field Coordination

3.   Clarifications/Changes to H92-81

4.   Acceptance by Applicant

5.   Reservation of Funds

6.   Grant Agreement

7.   Meeting with Grant Recipients

8.   Procedures for Drawing Down Funds

9.   Processing Amendments

10.  Deobligation of Funds

11.  Regional Reallocation of Funds

12.  Reporting Requirements

13.  HUD Quarterly Report

Attachments:

1.   Conflict of Interest Certification

2.   Sample Form HUD-718, Funds Reservation and Contract

Authority

3.   Grant agreement

4.   OMB Circulars A-110, A-122, A-133

5.   Form HUD-27054, LOCCS Voice Response Access Authorization

6.   Direct Deposit Form SF-1199A with instructions

7.   Form HUD-27054A, LOCCS Access Authorization Security Form

8.   Form HUD-9738, LOCCS/VRS Preservation Technical Assistance

Planning Grant Payment Voucher

9.   Part 1 of LOCCS User Guide

___________________________________________________________________________

HMPPA: Distribution: W-3-1,W-2(H),W-3(A)(H)(OGC)(ZAS),W-4(H R-1,R- R-3-1,

R-3-2,R-3-3,R-6,R-6-1,R-6-2,R-7,R-7-1,R-8

_____________________________________________________________________

1.   PURPOSE.

This Notice provides processing instructions for field

office staff and recipients of Preservation Technical

Assistance Planning Grant funds for actions subsequent to

Notification of Funding Approval.  This follows Notice H92-81,

"Processing Applications under the Preservation NOFA for

Technical Assistance Planning Grants for Resident Groups,

Community Groups, Community-Based Nonprofit Organizations

and Resident Councils," issued October 22, 1992.  Notice

H92-81 gives guidance up to and including grant approval and

applicant acceptance.  The Notice for Funding Availability

(NOFA) making these planning grant funds available was

published in the Federal Register on September 3, 1992 at 57

FR 40570.

2.   FIELD COORDINATION.  Notice H92-81 authorized, and this

Notice gives instructions for:

A.   Resident Initiatives Specialists (RIS) to:

(1)  Make recommendations through the Director of

Housing Management (HM) to Regional Offices for

amendments of grants for Regional Office award.

(2)  Provide monitoring functions to ensure successful

grant completion.

(3)  Enter the budget (i.e., line-item activities from

Exhibit 3 of the application) for the grant into

the Line of Credit Control System/Voice Response

System (LOCCS-VRS) payment system.

(3)  Approve line-item requests for funds made by

grantees through LOCCS-VRS.

(4)  Make requests for deobligation of funds through

the Director of HM to the Regional Housing

Director (RHD).

B.   Resident Initiatives Leaders (RIL) to:

(1)  Track the status of Regional grants and submit

quarterly reports on awards.

(2)  Monitor total Regional funds spent through the

LOCCS system and make requests through the RHD for

additional funds, if necessary.

C.   Field Office Managers to execute grant agreements.

2

_____________________________________________________________________

D.   RHDs to approve award amendments and deobligations of

funds.

E.   Regional Counsel to make amendments to grant

agreements, if necessary, or delegate this

responsibility to Field Counsel.

3.   Clarifications/Changes to H92-81

a.   Phase I Eligibility.

A technical amendment was made to the NOFA by

publication in the Federal Register on December 1,

1992.  This amendment covers the eligibility of

applicants applying for Phase I funding in projects

eligible for incentives under the Low Income Housing

Preservation and Resident Homeownership Act of 1990

(LIHPRHA).  The amendment allows an eligible applicant

to apply for Phase I funding if a LIHPRHA owner submits

an Initial Notice of Intent to extend and the owner

subsequently files a letter of intent to work with the

organization towards a resident-supported purchase of

the property.

b.   HUD-Sponsored Training.

HUD will be providing and sponsoring training on the

Emergency Low Income Housing Preservation Act of 1987

(ELIHPA) and LIHPRHA for resident and community groups.

However, the requirement that this training be obtained

as a condition of receiving a technical assistance

grant was removed from the NOFA by the Housing and

Community Development Act of 1992.  This change was

published in the Federal Register on December 3, 1992.

Nevertheless, HUD-sponsored and/or other training is

strongly recommended for all recipients.  Once the

HUD-sponsored training is made available at a nationwide

level, the RIS should give all grantees and applicants

information on those training sessions and strongly

encourage these groups to attend.

c.   Resident Supported Purchase.

The NOFA states in Paragraph I.E.1. that an eligible

applicant is an entity that "represents the residents

of the eligible property, intends to purchase the

property, and complies with the applicable criteria."

While the strict definition of a Community Based

Nonprofit Organization (CBO) does not require

documentation of resident support where a CBO is the

applicant, these grants are meant to support

resident-supported purchases.  Grants to CBOs should only be

3

_____________________________________________________________________

awarded to organizations who intend to work towards

purchasing the property as a priority purchaser with a

majority of resident support.  This resident support is

not required for a Phase I or Phase II application, as

organizing and training residents are eligible

activities under Phase I and Phase II grants.

d.   Conflict of Interest Requirements.

An additional exhibit, Exhibit 14 -- conflict of

Interest Certification, is now required of all

applicants and is included as Attachment 1 of these

instructions.  All applicants who have not been awarded

grant funds as of the date of this Notice must submit

this certification.  The RIS should send a copy of this

additional exhibit to all known organizations who have

made an application which is pending, or who are

currently making or considering making an application

under the Preservation Technical Assistance NOFA.  The

RIS should also include this exhibit with responses to

any future requests for application packages.

e.   Application Exhibit 1.  Standard Form 424

1.   The funds available in the NOFA will be listed in

the Catalog of Federal Domestic Assistance under

number 14.187.  This number should be entered in

item 10 of this form.

2.   This program is not subject to review by the State

Executive Order 12372 Process, therefore, in item

16.b. the first "No" box should be checked.

f.   Application Exhibit 3, Section 1A

Section 1A of Exhibit 3 of the application package

requires the applicant to provide a narrative

containing a detailed description of activity under the

proposed phase.  Please note that while the Selection

Review Form does not specify the level of detail

required, it is expected that, at a minimum, the

narrative will include a summary of steps to be taken

in each activity, and/or organizations or consultants

the applicant plans to enter into a contract with for

technical assistance.  This narrative should give the

RIS some basis for reviewing the acceptability of the

level of funding requested for each activity.

4

_____________________________________________________________________

4.   ACCEPTANCE BY APPLICANT.

Applicants will have 30 days from the date of grant approval

to indicate their acceptance of the Technical Assistance

Planning Grant.  If applicants do not accept funding within

30 days, the field office will inform the applicant that the

award has been withdrawn.  If an applicant determines that

it needs additional funds to complete tasks identified in

its initial application, it may submit an amended

application, in accordance with Notice H92-81, as long as

the maximum grant amount for that phase (described in

Paragraph 7 of Notice H92-81) has not yet been reached.

5.   RESERVATION OF FUNDS.

Upon receipt of a 185.1 from the Regional Office, the field

office will prepare a form HUD-718 and submit it to the

Regional Accounting Division (RAD) to reserve funds for the

grantee.  If a grantee is being awarded only Phase I grant

funds, the amount shown on the form HUD-718 should include

an additional $100,000 for the maximum Phase II and III

grants ($50,000 for each phase, or $100,000).  If an initial

award is for Phase II, the field office should accordingly

reserve an additional $50,000 (the maximum Phase III

amount).  This additional reservation is to ensure that

there will be funds available for successful applicants in

subsequent phases.  A sample form HUD-718 is included as

Attachment 2.  Please note that the grant agreement will be

made for the current phase of grant award and the grantee

will have access only to funds made available in the phase

of their current grant award.

6.  GRANT AGREEMENT.

a.   Grant Numbering.

The grant agreement will be prepared using a sample

grant agreement (Attachment 3) which was prepared by

Headquarters office of General Counsel.  Grants will be

numbered using the FHA Project Number of the Project

for which the applicant is seeking to purchase,

followed by a hyphen and the number 921.  (Example:  If

the project's 8-digit FHA Number is 017-11111, the

grant number will be 017-11111-921.)  The "92"

reflects the Appropriation year for these funds, the

"1" shows that this is the first technical assistance

grant funded from this NOFA for this particular

project.  If this is the second grantee receiving funds

for the same project (i.e., a previous grantee received

funds but did not successfully purchase the property,

and another eligible applicant is awarded a technical

5

_____________________________________________________________________

assistance grant for the same property) the grant

number shall end with a "2".  If a third grant is

awarded, the number will end with a 3, and so forth.

b.   Tax Identification Number.

The applicant's Tax Identification Number (TIN) must be

on the grant agreement.  A Phase I grant recipient

organization may, at the time it makes an application,

not be organized for tax purposes and may not yet have

a TIN.  However, all applicant organizations must have

a TIN before executing the grant agreement.  Inquiries

on how to receive a TIN through the Internal Revenue

Service can be made by calling 1-800-829-3676 Monday

through Friday between the hours of 8:00 a.m and 5:00

p.m. Eastern Standard Time, or Saturday between the

hours of 9 a.m. and 3 p.m. Eastern Standard Time.

c.   Grant Execution.

1.   The Field Office Manager will execute the grant

agreement and the RIS will be responsible for

monitoring performance under the grant agreement.

2.   Three copies of the grant agreement shall be

executed with original signatures. one will be

given to the grantee, one will be maintained in

the grant file in the field office, and one will

be sent to the RAD in accordance with Paragraph

8.c.3. below.

3.   If any amendments or changes to the attached grant

agreement are necessary prior to execution, they

will be made by Regional Counsel, or Field Counsel

if Regional Counsel has so delegated.

d.   Subsequent Phases.

If a grantee is awarded funds in subsequent phases, the

field office need only execute the Rider to the Grant

Agreement (included with Attachment 3), rather than

executing the entire grant agreement.

e.   Failure to Perform.

Failure to perform under the terms of the grant

agreement in any phase of this program will disqualify

a grantee from receiving funding for other phases, and

will disqualify the grantee from receiving any unspent

balance of the current phase.

6

_____________________________________________________________________

7.   MEETING WITH RECIPIENTS.

a.   Once a successful grant applicant has accepted the

grant award, the RIS should arrange a meeting with the

grant recipient.  Prior to the meeting, the RIS should

mail the grantee a copy of the proposed grant agreement

and a form HUD-2530, Previous Participation

Certification.  The awardee must return the completed

form HUD-2530 as soon as possible.  The Field Office

must obtain 2530 clearance of all applicants prior to

executing the grant agreement.

b.   At the scheduled meeting, the recipient will:

1.   Sign the grant agreement.

2.   Return the previous participation clearance form.

3.   Receive the following:

A.   Part 1 of the LOCCS User Guide (Attachment 9,

see paragraph 8.g. below).

B.   Copies of Office of Management and Budget

(OMB) Circulars A-110, A-122 and, if

necessary, A-133 (Attachment 4).  (A-133

applies only to grantees which will receive

more than $100,000 in federal funds in one

fiscal year.)  These circulars include the

administrative and financial requirements for

non-profit organizations receiving grant

funds from the federal government.  Recipients

may also receive copies directly from OMB

Publications by calling (202)395-7332.

C.   Forms HUD-27054 and SF-1199A (Attachments 5

and 6).  These forms should be returned to

the RIS to set up a LOCCS-VRS account for the

recipient (see Paragraphs 8.b. and 8.c.).

4.   Be briefed on the LOCCS-VRS system as described in

Paragraph 8 and be shown the LOCCS-VRS video

previously received by field office staff

responsible for administering the HOPE 2 program.

c.   The Director of HM and the Field Office Manager will

participate in the meeting, as necessary.  The Field

Office Manager will execute the grant agreement.

d.   Costs may be incurred by the applicant as soon as the

grant agreement is executed, however, no funds will be

disbursed until the applicant's LOCCS account is

7

_____________________________________________________________________

established.  Grantees should be informed that it could

take two to three weeks before their grant account is

accessible.

8.   PROCEDURES FOR DRAWING DOWN GRANT FUNDS.

a.   The Line of Credit Control System - Voice Response

System (LOCCS-VRS) is the system that will enable

recipients to draw down Preservation grant funds using

a touchtone telephone.  In most cases, funds will be

wired to the recipient's bank account within 48 hours

of the time the RIS approves the telephone request.

b.   Establishing a line of Credit.

To establish a line of credit, the recipient must

complete the forms SF-1199A and HUD-27054 (carefully

following the instructions attached to the forms), and

send the completed forms to the RIS, as soon as

possible.  The program code to be used on forms for

this program is PTAG.  It is very important that the

bank the recipient uses to receive grant funds is a

member of the Federal Reserve System.

c.   Field Office Actions

1.   One LOCCS-VRS Access Authorization Form (form HUD

27054) should be completed for each of the two or

three staff persons of the recipient organization

who will perform draw down functions.  The

completed form will be returned to the RIS at the

appropriate field office for review/verification.

The field office will send the access request form

(HUD-27054) to the LOCCS Security Officer at the

following address:

Department of Housing and Urban Development

Office of Information Policies and Systems,

AISAO

Room 3184

451 7th Street, SW

Washington, DC  20410-3600

For information relating to LOCCS, contact the

LOCCS Security Officer at Headquarters on

(202)708-0764.

2.   The SF-1199A, Direct Deposit Sign-Up form,

provides the authorization to send payments

directly to the recipient's bank account using the

Treasury Automated Clearinghouse payment system.

The recipient is responsible for preparing a

8

_____________________________________________________________________

SF-1199A and submitting the first page (original) and

a BLANK CHECK marked "CANCELED" or "VOID" to the

RIS, where the form is reviewed for verification

of the name, address, and an authorized signature.

Once the SF-1199A is reviewed and determined

satisfactory by the RIS, the form and blank check

should be transmitted to the following address for

data entry into LOCCS:

Department of Housing and Urban Development

Office of Finance and Accounting

Cash and Credit Management Division

PO Box 44816

Washington, DC 20026-4816

Upon receipt of the SF-1199A and the blank check,

the Office of Finance and Accounting (OFA) shall

review it for original signatures of the recipient

and the banking official.  OFA shall verify that

the account number and the ABA banking number are

the same on the SF-1199A and the "Void" check, and

enter the banking information into LOCCS.

3.   After the RIS submits the SF-1199A to OFA and one

copy of the executed grant agreement to the RAD

the following activities will be completed:

A.   The RAD will:

1.   Enter the Preservation Technical

Assistance Grant into the Program

Accounting System (PAS).

2.   Assign the grant to a recipient's TAX ID

in LOCCS.

B.   LOCCS will:

1.   Automatically generate and mail the

recipient a VRS grant number following

verification of the grant assignment to

a TAX ID number.  The VRS grant number

is needed to identify all grants during

the telephone payment request.

2.   Maintain up to date account information

by automatically retrieving grant

balance and voucher requests each night.

C.   The RIS will enter the budget (i.e.,

line-item activities from Exhibit 3 of the

application) for the grant into LOCCS.

9

_____________________________________________________________________

d.   Field Office Program Authorization.

The RIS and the Director of HM will be the authorized

LOCCS users for this program.  Because the LOCCS users

in the field office are the same persons who are

already authorized users through the HOPE 2 LOCCS

system, they need only submit a new form HUD-27054A

(attachment 7) using the "PTAG" program code, which

will give them access to the Preservation LOCCS system.

If a RIS or HM Director is not yet an authorized user

in the LOCCS system, they should use the authorization

procedures in Interim Notice H 92-12 "Actions

Subsequent to Notification of Funding Approval for the

HOPE for Homeownership of Multifamily Units Program,"

Attachment 11, for guidance.  The LOCCS User Guide may

also be referenced by HUD Staff for further guidance.

e.   Regional Program Authorization.

The RIL will have query authority in the LOCCS system

to monitor and track grant funds spent.  The RIL should

also submit a new form HUD-27054A (attachment 7)

requesting query authority for this program using the

"PTAG" program code.

f.   Headquarters Actions.

After OFA in Headquarters receives, verifies and enters

information from the SF1199A into LOCCS, the

Headquarters LOCCS Security Officer will issue a letter

to provide a user an identification number and password

for the individual in the recipient's organization who

will be authorized to draw down the funds.  Enclosed

with this letter will be specific instructions on how

to use the LOCCS Preservation system.

g.   Recipient Preparation of Voucher.

Form HUD-9738, a Budget Line Item LOCCS voucher, will

be used for Preservation Technical Assistance Planning

Grants (Attachment 8).  The voucher number is made up

of nine digits; 3 digits assigned on the form HUD-9738

and 6 digits will be determined automatically and

spoken back to the caller.  The caller will write the

voucher number to confirm it was recorded correctly.

This procedure will allow recipients to photocopy

vouchers as needed instead of relying on HUD to supply

forms.  This procedure also ensures that the voucher

numbers are unique.  The grant recipient's name and TAX

ID number are also standard information on the form,

and although not required as an entry item by the Voice

10

_____________________________________________________________________

Response System, assist in the potential auditing of

the recipient's records.  The vouchers are based on

budget line items as designated in the recipient's

budget submission.  The line items on the form HUD-9738

match the line items on Exhibit 3 of the approved

application.  LOCCS will prompt for each line item

number entry and amount, speaking back the line item

category and amount for confirmation.  After the line

item entries are complete, LOCCS will speak back the

line items entered, their amount, and a voucher total

for final confirmation.  The caller then has a final

option to process or cancel the request.  A copy of the

completed voucher must be sent to the RIS in the field

office after confirmation of the LOCCS drawdown.  A

copy of the completed voucher must be received by the

RIS within seven days, or no further requests for funds

will be processed.  A description of the LOCCS-VRS

system is included in Attachment 9, Part 1 of the LOCCS

User Guide.  Section 3 of Attachment 9 includes a

sample LOCCS-VRS dialogue.

h.   Funding Request Limits.

1.   No single voucher request may be in excess of

$5,000.

2.   No line item request for funds may exceed 120

percent of the budget submitted as Exhibit 3 of

the application package.

i.   Approving Budget Requests.

The RIS will access LOCCS daily and review and approve

grant requests as appropriate.  Every request for funds

must be approved by the RIS before the funds are

disbursed.  The RIS is responsible for ensuring that

the funding limit in Paragraph 8.h.1. is not exceeded.

The LOCCS system will ensure that the funding limit in

Paragraph 8.h.2. is not exceeded.  The RIS must not

approve a LOCCS funding request unless a hard-copy of

form HUD-90738 has been received for all previous LOCCS

funding requests from the grantee, and the grantee has

adequately accounted for expenses in the previous

requests.  Because only the RIS and the Director of HM

will have access to the LOCCS accounts, the Director of

HM will have back up responsibilities for reviewing the

LOCCS accounts.  The RIS will withhold approval of

LOCCS budget line-item requests if the grantee has not

met the reporting requirements described in Paragraph

12.

11

_____________________________________________________________________

9.  PROCESSING AMENDMENTS.

If a grantee submits a second application for the original

or subsequent phase, the application need only be amended

sufficiently to allow the RIS to make a determination to

award the grant agreement.  The application amendment will

include, at a minimum, resubmission of Exhibit 2 - Summary

Information, Exhibit 3 - Description of Activities and

Description of Costs, and the Acknowledgement of Application

Receipt form.  The RIS shall process application amendments

in the same manner as a newly submitted complete application

(see Notice H92-81 Paragraphs 9 through 12).  These

amendments will be approved or denied within 30 days from

receipt by the field office.  If the amended application is

for additional funds for a previously funded phase, that

amendment shall only be accepted for processing if the

maximum grant amount for that phase has not been reached.

10.  WITHHOLDING/DEOBLIGATION OF FUNDS.

a.   Decision to Withhold Funds.

The field office may withhold disbursement of funds at

any time it is determined that continuing to provide

funding would not be in the best interests of the

Department.  The RIS or the Director of HM may make

such a determination upon a finding that stated tasks

have not been accomplished; ineligible activities have

been vouchered for (see Paragraph 9 of Notice H92-81);

fraud, waste or mismanagement has taken place; or the

purchasing plan is not technically feasible.  The RIS

may also temporarily withhold disbursement of funds if

a grantee fails to adequately account and voucher for

previously disbursed funds or if the grantee fails to

submit reports required in Paragraph 12.  If an owner

accepts a purchase offer from any other qualified

purchaser, no further funding will be available to the

applicant under this NOFA, including funds previously

awarded but not yet spent.

b.   Deobligation of Funds.

Any applicant may be required to demonstrate that it

has sufficient capacity to warrant continued

consideration for funding.  Should HUD terminate the

grant for cause, the RIS shall make requests for

deobligation of funds through the Director of HM to the

RHD.  A form HUD-718 should be used to deobligate

remaining funds. once deobligated, prior year funds

(recaptures) are subject to current year appropriation

act requirements and/or administrative actions.

12

_____________________________________________________________________

11.  REALLOCATION OF FUNDS.

The Preservation Division in Headquarters will make periodic

reviews of the grant funds spent by Regional Offices.  Upon

making an assessment that a regional reallocation would be

beneficial to the Department, the Director of the Office of

Multifamily Housing Preservation and Property Disposition is

authorized to transfer funds across regions.  The RIL shall

monitor funds spent in its Region.  If no money is left in a

Regional pool or if it is anticipated that funds will fall

short of demand, the RIL may recommend that the RHD make a

request for additional grant funds to the Office of

Multifamily Housing Preservation and Property Disposition.

12.  REPORTING REQUIREMENTS.

Recipients are required to make reports on the progress of

their Preservation Technical Assistance Grants.

a.   Semi-annual Report.  Recipients must submit on a

semi-annual basis a narrative description describing:

(1)  The accomplishments, to date, on each line item

activity;

(2) A justification of the amount of grant funds used;

(3) The progress resulting from training activities.

These reports will be submitted to the RIS on October

31 and April 30 for the six months ending September 30

and March 31, respectively.  If the recipient has

received funds in more than one phase during that

six-month period, the report will combine activities from

each separate phase.

b.  Final Report.  Within 90 days of completion of each

phase of funding each recipient will submit:

(1)  Audit Report.  Independent audit statements

meeting the requirements of OMB Circular A-110 and

A-133, if necessary.

(2)  Closeout report.  Narrative description of the

following:

(A)  The accomplishments on each line item

activity;

(B)  A complete report on the use of all grant

funds including any funds held in the

13

_____________________________________________________________________

recipients' bank accounts and any funds not

drawn down;

(C)  A report on training activities and any

measurable benefits resulting from such

training.  This report should also include

information on any ongoing training planned

for the period subsequent to the grant term.

c.   Other Reports.  In addition to the above, recipients

will routinely submit a hard copy of each voucher used

to draw down funds (see Paragraph 8.g.) and such other

documentation as may be required by HUD.

13.  QUARTERLY REPORTS.

a.   The RIL will make quarterly reports to the Headquarters

Preservation Division on all grants awarded.  These

reports will be submitted on October 31, January 31,

April 30 and July 31 for the three months ending one

month prior to those submission deadlines.  These

reports will include:

(1)  The name and address of each recipient of

assistance;

(2)  The phases for which the recipient has received a

grant award; and

(3)  The dollar amount of the assistance for each grant

awarded.

b.   Headquarters Office of Preservation and Property

Disposition will give public notice through the Federal

Register of all grants awarded during each quarter.

___________________________________

Assistant Secretary for Housing

-Federal Housing Commissioner

14

_____________________________________________________________________

ATTACHMENT 1

_____________________________________________________________________

EXHIBIT 14

CONFLICT OF INTEREST CERTIFICATION

Applicants shall certify to the following:

It will contract to no professional, including but not

limited to attorneys, architects, engineers, and accountants, who

are already providing services under Title II or VI of the

Preservation regulations to the owner/seller of the project.  It

will further assure that no person with a personal or

professional relationship with the owner/seller shall be involved

in the applicant's planning for the project if that relationship

could be construed as a conflict of interest affecting the

legitimate purchase of the project.

I certify that the applicant organization has, to the best

of my knowledge, complied and will continue to comply with the

above requirement.

_______________________________________

Signature and date

_______________________________________

Title

______________________________

Name of Organization

_____________________________________________________________________

ATTACHMENT 2

_____________________________________________________________________

SAMPLE FORM HUD-718

__________________________________________________________________________

FUNDS RESERVATION AND CONTRACT AUTHORITY

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

_____________________________________________________________________

ATTACHMENT 3

_____________________________________________________________________

Project Name

Location

Project Number

GRANT AGREEMENT FOR PRESERVATION

TECHNICAL ASSISTANCE PLANNING GRANTS

This Grant Agreement, made this _____ day of _____________,

1992, between the United States Department of Housing and Urban

Development ("HUD") and _______________________________________,

(the "Grantee") (Employer Identification Number ____-_________)

with an address of ______________________________________________

__________________________, provides as follows:

WHEREAS, the Grantee has requested a Technical Assistance

Planning Grant pursuant to the Emergency Low Income Housing

Preservation Act of 1987 ("ELIHPA") or the Low Income Housing

Preservation and Resident Homeownership Act of 1990 ("LIHPRHA").

WHEREAS, ________________________ (the "Project") is subject

to the provisions of ELIHPA or LIHPRHA, because it meets the

definition of "eligible low income housing" in ELIHPA or LIHPRHA.

NOW, THEREFORE, in reliance upon and in consideration of the

mutual representations and obligations hereunder, HUD and the

Grantee agree as follows:

ARTICLE I.  ADMINISTRATIVE REQUIREMENTS

The Grantee agrees to carry out its grant activities under

this Agreement in compliance with ELIHPA or LIHPRHA; Part 248 of

Title 24 of the Code of Federal Regulations, as amended by an

interim rule published at 57 Federal Register 11992 on April 8,

1992 (the "Regulations"); the Notice of Fund Availability

published on September 3, 1992 at 57 Fed. Reg. 40570 (the

"NOFA"); Office of Management and Budget Circular A-110, "Grants

and Agreements with Institutions of Higher Education, Hospitals,

and Other Nonprofit Organizations," published July 30, 1976 at 41

Fed. Reg. 32016 and amended February 10, 1987 at 52 Fed. Reg.

4240, ("OMB Circular A-110"); Office of Management and Budget

Circular A-122 ("OMB Circular A-122"); Office of Management and

Budget Circular A-133 ("OMB Circular A-133"); 24 CFR part 45,

published July 7, 1992 at 57 FR 33252, and any other applicable

laws, regulations, and requirements (including recordkeeping

requirements).  The Grantee also agrees to accept responsibility

for such compliance by any other entities to which the Grantee

makes grant funds available.

_____________________________________________________________________

ARTICLE II.  DEFINITIONS

(a)  The term "Approved Application Package" refers to the

application for grant assistance submitted by the Grantee

and approved by HUD.  The Approved Application Package

includes any subsequent revisions made to the application

package by the Grantee and approved by HUD for the purposes

of adjusting the Grantee's budget within a particular phase

of activity or for funding additional Phases of activity.

(b)  The term "Grant" refers to funds provided under this Grant

Agreement.

(c)  The term "Grantee" refers to the grant recipient(s) as

designated in the Approved Application Package.  Where there

are joint applicants, all applicants are deemed the

"Grantee."

(d)  The term "Grant Officer" means the official authorized by

HUD to execute and/or administer this grant.  The Grant

Officer is the Resident Initiatives Specialist or her/his

designees.

(e)  The term "phases of activity" refers to the three separate

phases for which technical assistance planning grants may be

provided, as set forth in the NOFA.

ARTICLE III.  APPROVED APPLICATION PACKAGE

The Approved Application Package is attached to and made a

part of this Agreement.  The funding provided under this

Agreement shall not be used for any activities except those

specifically provided for in the Approved Application Package.

Any amendments made to the Approved Application Package for the

purpose of receiving additional technical assistance planning

grant funds for a subsequent phase of activity shall be approved

by HUD and made a part of this Agreement.

ARTICLE IV.  SCOPE AND CONDUCT OF WORK

(a)  The Approved Application Package may include the following

activities which are intended to be performed and funded in

three separate phases:

PHASE I ACTIVITIES:  establishing and organizing a

Resident Council or Community-based Nonprofit

Organization; providing training to project and

community residents, board members and affiliated

persons regarding ELIHPA and LIHPRHA acquisition

opportunities, housing management and development;

assisting residents and nonprofit members in choosing

among homeownership and rental options for the project;

_____________________________________________________________________

3

incorporating the purchasing entity and applying for

tax exempt status under section 501(c) of the Internal

Revenue Code; establishing accounting procedures; and

related activities.

PHASE II ACTIVITIES:  preparing and submitting an

expression of interest and a bona fide offer;

architectural and engineering services, as necessary to

supplement the capital needs assessment developed by

HUD; financial and legal services; training for the

board and members of the purchasing entity and for

residents of the project; and related activities.

PHASE III ACTIVITIES:  preparing a plan of action or

resident homeownership plan; architectural and

engineering services, as necessary to supplement the

capital needs assessment developed by HUD; financial

and legal services; training for the board and members

of the purchasing entity and for residents of the

project; preparing the transfer of physical assets

package; and related activities.

(b)  The Grantee shall complete the work items set forth in the

Approved Application Package.  This shall include providing

the necessary personnel, materials, services, equipment,

facilities (except as otherwise specified herein) and

otherwise doing all things necessary for or incidental to

the performance of the work items as set forth in the

Approved Application Package and this Grant Agreement.  Only

those work items that have been approved by HUD may be

funded by the grant assistance provided under this

Agreement.

(c)  The Grantee may not use grant proceeds to fund

entertainment, including the cost of food and beverages; the

purchase of land or buildings or any improvement to land or

buildings; payment of fees for lobbying activities; earnest

money deposits; activities funded from other sources and

activities completed prior to the date of this Agreement.

This paragraph merely illustrates various types of

ineligible activities; it is not meant to be exhaustive.

(d)  During the term of this Grant Agreement, the Grant Officer

is responsible for monitoring the approved activities of the

Grantee.

(e)  In the event the Grantee deviates without written approval

of the Grant Officer, such deviation shall be at the risk of

the Grantee.  Any costs related thereto shall be borne by

the Grantee.

_____________________________________________________________________

4

ARTICLE V.  TERM OF GRANT AGREEMENT

This Grant Agreement shall continue in effect from the date of

execution until the occurrence of any of the following events:

(1)  upon completion of the activities contained in the

Approved Application Package, including any additional

activities funded after amendment of the Approved

Application Package and amendment of this Agreement;

(2)  upon depletion of the technical assistance planning

grant provided pursuant to this Agreement;

(3)  upon default by the Grantee, pursuant to Article VII of

this Agreement; or

(4)  upon the acceptance of a purchase offer from another

entity by the owner of the Project.

ARTICLE VI.  AMOUNT OF GRANT ASSISTANCE

(a)  Subject to the provisions of this Grant Agreement, HUD will

make available to the Grantee, grant funds in the following

amounts for the following phases of activity:

PHASE I     $_____________

PHASE II    $_____________

PHASE III   $_____________

(b)  Grant funds shall be disbursed in the manner set forth in

Article VII of this Agreement.

(c)  The approval of funding under this Agreement for one or more

phases of activity does not guarantee that the Grantee will

receive funding for subsequent phases of activity.

(d)  Funding for a subsequent phase will not be approved unless

and until the Grantee has adequately demonstrated, through

amendment of its Approved Application Package, that the

activities required to complete the preceding phases have

been completed.

ARTICLE VII.  PROCEDURES FOR DRAWING DOWN GRANT FUNDS

The Line of Credit-Control System - Voice Response System

(LOCCS-VRS) is the system that will enable recipients to draw down

preservation technical assistance grant funds.  A request by the

_____________________________________________________________________

5

Grantee to draw down grant funds under this system constitutes a

representation by the Grantee that it and all participating

parties are complying with the terms of this Grant Agreement.

The procedure for grantees to follow to drawdown funds will be

issued in separate instructions.

ARTICLE VIII.  PROGRESS REPORTS

The Grantee shall submit a progress report at the completion of

each phase of activities, but not less than twice a year.

Progress reports shall include reports on both performance and

financial progress and shall conform to OMB Circular A-110.

(a)  The performance reports must contain the information

required under OMB Circular A-110 Attachments G and H.

(b)  The financial reports shall be submitted on Standard Form

269.

(c)  No grant payments will be approved for Grantees with overdue

progress reports until the report has been submitted and

approved.

ARTICLE IX.  CLOSEOUT

(a)  Within 30 days of expiration of the term of this Grant

Agreement or completion of grant activities, whichever

occurs first, the Grantee shall request HUD approval to

initiate closeout in compliance with OMB Circular

A-110, Attachment K.  At HUD's option, the Grantee will

delay initiation of closeout until the resolution of any HUD

monitoring findings.  If HUD exercises this option, the

Grantee must promptly resolve the findings.

(b)  The Grantee recognizes that the closeout process may entail

a review by HUD to determine compliance with the Grant

Agreement by the Grantee and all participating parties.  The

Grantee agrees to cooperate with any review in any way

possible, including making available records requested by

HUD.

(c)  The Grantee shall immediately, upon expiration of the term

of this Grant Agreement or completion of grant activities,

whichever occurs first, refund any balance of unencumbered

grant funds that HUD has advanced or paid.

(d)  Within 90 days after HUD approval to initiate closeout, the

Grantee shall provide to HUD the following, in the format(s)

approved by HUD:

_____________________________________________________________________

6

1.   A certification of compliance with all requirements

of this Grant Agreement.

2.   A report listing the amount and types of costs charged

to the grant that meet the allowability and

allocability cost requirements of OMB Circular A-122

(cost principles applicable to nonprofit

organizations).

3.   A final performance report, in the form prescribed in

Article VIII of this Agreement, providing a comparison

of actual accomplishment with each of the activities

indicated in the Approved Application Package, and

additional pertinent information including explanation

of any significant cost overruns.

(e)  The Grantee agrees that the grant may be reduced, in

accordance with OMB Circular A-122, if the costs of

completing the activities contained in the Approved

Application Package are less than the grant amount plus

other funds provided to the Grantee.

(f)  When HUD has determined that the grant funds have been

expended in accordance with this Grant Agreement and the

Approved Application Package, that the activities in the

Approved Application Package were completed to HUD's

satisfaction, and that all Federal requirements were

satisfied, HUD and the Grantee will execute an agreement

indicating that the grant has been closed out.

(g)  The Closeout Agreement will include the Grantee's agreement

to continue to abide by any applicable federal requirements.

ARTICLE X.  DEFAULT

(a)  A default under this Grant Agreement consists of any use of

grant funds for a purpose other than as authorized by this

Agreement and the Approved Application Package, any material

noncompliance with ELIHPA or LIHPRHA or the Regulations, as

determined by HUD, any other material breach of this

Agreement, or any fraud or misrepresentation in the

application submissions which, if known to HUD, would have

resulted in this grant not being provided.  If HUD

determines preliminarily that the Grantee is in default, HUD

will give the Grantee notice of this determination and the

corrective or remedial action proposed by HUD.  The Grantee

shall have an opportunity to demonstrate, within the time

prescribed by HUD (not to exceed thirty days from the date

of the notice), and on the basis of facts and data, that it

is not in default, or that the proposed corrective or

remedial action is inappropriate, before HUD implements the

_____________________________________________________________________

7

corrective or remedial action.  If HUD determines that the

Grantee will continue to expend grant funds contrary to this

Agreement unless HUD takes immediate action, HUD may

implement a remedial action appropriate to prevent such

misspending concurrently with issuing a notice of default.

Corrective or remedial actions that HUD may instruct the

Grantee to undertake under this Agreement including one or

more of the following:

(1)  Prepare and follow a schedule of actions and/or a

management plan for properly completing the approved

activities affected by the default;

(2)  Cancel or revise the affected activities before grant

funds have been expended for these activities, revise

the grant budget as necessary, and substitute other

eligible activities;

(3)  Discontinue draws under the LOCCS System, and not incur

further costs, for the affected activities; and

(4)  Reimburse the preservation technical assistance program

account in the amount not used in accordance with this

Agreement.

(b)  Where HUD determines that corrective or remedial actions by

the Grantee have not been undertaken as instructed, or will

not be effective to correct the default and to prevent

further default, HUD may take one or more of the following

additional corrective and remedial actions under this

Agreement:

(1)  Change the method of payment under the LOCCS;

(2)  Suspend the Grantee's authority to make draws under the

LOCCS for affected activities for not more than ninety

(90) days, pending action to cure the default and

prevent further default by the Grantee, or final

remedial action by HUD;

(3)  Reduce the grant in the amount affected by the default;

(4)  Terminate the grant as to all further activities;

(5)  Take action against the Grantee under 24 CFR Part 24

and Executive order 12549 with respect to future HUD or

Federal grant awards; and

(6)  Take any other remedial action legally available.

(c)  No delay or omission by HUD in exercising any right or

remedy under this Agreement shall impair HUD's ability to

_____________________________________________________________________

8

exercise such right or remedy, or constitute a waiver of, or

acquiescence in, any Grantee default.

ARTICLE XI.  LOBBYING ACTIVITIES

(a)  The Grantee certifies that no Federal appropriated funds

have been paid, and agrees that no Federal appropriated

funds will be paid, by or on behalf of the Grantee, to any

person for influencing or attempting to influence an officer

or employee of an agency, a Member of Congress, an officer

or employee of Congress, or an employee of a Member of

Congress in connection with the awarding of any Federal

contract, the making of any Federal grant, the making of any

Federal loan, the entering into of any cooperative

agreement, and the extension, continuation, renewal,

amendment or modification of any Federal contract, grant,

loan, or cooperative agreement.

(b)  If any funds other than Federal appropriated funds have been

paid or will be paid to any person for influencing or

attempting to influence an officer or employee of any

agency, a Member of Congress, an officer or employee of

Congress, or an employee of a Member of Congress in

connection with this Federal grant, the Grantee shall

complete and submit Standard Form-LLL, "Disclosure Form to

Report Lobbying," in accordance with its instructions.

ARTICLE XII.  DEBARMENT, SUSPENSION AND OTHER RESPONSIBILITY

MATTERS

The Grantee certifies that to the best of its knowledge and

belief, that it and its principals:

(a)  Are not presently debarred, suspended, proposed for

debarment, declared ineligible, or voluntarily excluded from

covered transactions by any Federal department or agency;

(b)  Have not within a three-year period preceding this Agreement

been convicted of or had a civil judgment rendered against

them for commission of fraud or a criminal offense in

connection with obtaining, attempting to obtain, or

performing a public (Federal, State or local) transaction;

violation of Federal or State antitrust statutes or

commission of embezzlement, theft, forgery, bribery,

falsification or destruction of records, making false

statements, or receiving stolen property;

(c)  Are not presently indicted for or otherwise criminally or

civilly charged by a governmental entity (Federal, State or

local) with commission of any of the offenses enumerated in

_____________________________________________________________________

9

paragraph (b) of this article; and

(d)  Have not within a three-year period preceding this Agreement

had one or more public transactions (Federal, State or

local) terminated for default.

ARTICLE XIII.  DRUG-FREE WORKPLACE REQUIREMENTS

The Grantee certifies that it will, or will continue to, provide

a drug-free workplace by:

(a)  Publishing a statement notifying employees that the unlawful

manufacture, distribution, dispensing, possession, or use of

a controlled substance is prohibited in the Grantee's

workplace and specifying the actions that will be taken

against employees for violation of such prohibition;

(b)  Establishing an ongoing drug-free awareness program to

inform employees about:

(1)  The dangers of drug abuse in the workplace;

(2)  The Grantee's policy of maintaining a drug-free

workplace;

(3)  Any available drug counseling, rehabilitation, and

employee assistance programs; and

(4)  The penalties that may be imposed upon employees for

drug abuse violations occurring in the workplace;

(c)  Making it a requirement that each employee to be engaged in

the performance of the grant be given a copy of the

statement required by paragraph (a) of this article;

(d)  Notifying the employee in the statement required by

paragraph (a) of this article that, as a condition of

employment under the grant, the employee will:

(1)  Abide by the terms of the statement; and

(2)  Notify the employer in writing of his or her conviction

for a violation of a criminal drug statute occurring in

the workplace no later than five calendar days after

such conviction;

(e)  Notifying the Department in writing, within ten calendar

days after receiving notice under paragraph (d)(2) of this

article from an employee or otherwise receiving actual

notice of such conviction.  Employers of convicted employees

must provide notice, including position title, to the Grant

_____________________________________________________________________

10

Officer;

(f)  Taking one of the following actions, within thirty calendar

days of receiving notice under paragraph (d)(2), with

respect to any employee who is so convicted:

(1)  Taking appropriate personnel action against such an

employee, up to and including termination, consistent

with the requirements of the Rehabilitation Act of

1973, as amended; or

(2)  Requiring such employee to participate satisfactorily

in a drug abuse assistance or rehabilitation program

approved for such purposes by a Federal, State or local

health, law enforcement, or other appropriate agency;

(g)  Making a good faith effort to continue to maintain a

drug-free workplace through implementation of paragraphs (a),

(b), (c), (d), (e) and (f) of this article.

ARTICLE XXV.  AMENDMENTS

This Grant Agreement may be modified at any time by written

amendment, as agreed upon by both the Grantee and HUD.

Amendments that reflect the rights and obligations of either

party shall be executed by HUD (the Grant Officer) and the

Grantee.

ARTICLE XV.  ASSIGNMENT

The Grantee's rights under this Agreement may not be

assigned without prior written approval of HUD.

ARTICLE XVI.  SPECIAL CONDITIONS

_____________________________________________________________________

11

This Agreement is hereby executed on behalf of the parties

as follows:

UNITED STATES OF AMERICA

Secretary of Housing and Urban Development

BY:________________________________________

Signature

Director, Housing Management

HUD _______________________________ Office

___________________________________________

Date

GRANTEE

___________________________________________

Name of Organization

___________________________________________

Signature of Authorized Official

___________________________________________

Title

___________________________________________

Date

_____________________________________________________________________

Project Name

Location

Project Number

RIDER TO GRANT AGREEMENT FOR PRESERVATION

TECHNICAL ASSISTANCE PLANNING GRANTS

This Rider, made this _______ day of ______________, 1992

between the United States Department of Housing and Urban

Development ("HUD") and ________________________________________,

(the "Grantee") (Employer Identification Number ____-________)

with an address of ________________________________________________

__________________________, is attached to and made a part of

that Grant Agreement dated  __________________________ between

HUD and the Grantee for a Technical Assistance Planning Grant

("Grant Agreement").

WHEREAS, the Grantee successfully completed the activities

contained in its Approved Application Package and for which

funding was provided pursuant to the Grant Agreement;

WHEREAS, the Grantee has amended its Approved Application

Package to request additional funding for subsequent phases of

activity;

WHEREAS, the amendments to the Approved Application Package

have been approved by HUD and HUD agrees to provide additional

funding for subsequent phases of activity;

NOW, THEREFORE, in reliance upon and in consideration of the

mutual representations and obligations hereunder, HUD and the

Grantee agree to amend the Grant Agreement as follows:

1.  The amendments to the Approved Application Package, as

approved by HUD, are attached to and made a part of the Grant

Agreement.

2.  HUD will make available to the Grantee, grant funds in

the following amounts for the following phases of activity:

PHASE II    $_______________

PHASE III   $_______________

3.  Except where specifically amended by this Rider, all

provisions of the Grant Agreement shall continue in full force

and effect and shall be equally applicable to the additional

_____________________________________________________________________

assistance set forth in this Rider.

This Agreement is hereby executed on behalf of the parties as

follows:

UNITED STATES OF AMERICA

Secretary of Housing and Urban Development

BY:________________________________________

Signature

Director, Housing Management

HUD _______________________________ Office

___________________________________________

Date

GRANTEE

___________________________________________

Name of Organization

___________________________________________

Signature of Authorized Official

___________________________________________

Title

___________________________________________

Date

_____________________________________________________________________

ATTACHMENT 4

_____________________________________________________________________

PARTS OF ATTACHMENT 4 CONTAIN FEDERAL REGISTER DOCUMENTS

HARD COPIES OF THIS DOCUMENT MAY BE OBTAINED FROM THE LIBRARY.

_____________________________________________________________________

EXECUTIVE OFFICE OF THE PRESIDENT

OFFICE OF MANAGEMENT AND BUDGET

WASHINGTON, D.C. 20503

March 8, 1990

OMB Circular No. A-133

TO THE HEADS OF EXECUTIVE DEPARTMENTS AND ESTABLISHMENTS

SUBJECT:  Audits of Institutions of Higher Education and other

Nonprofit Institutions

1.   Purpose.  Circular A-133 establishes audit requirements and

defines Federal responsibilities for implementing and monitoring

such requirements for institutions of higher education and other

nonprofit institutions receiving Federal awards.

2.   Authority.  Circular A-133 is issued under the authority of

the Budget and Accounting Act of 1921, as amended; the Budget and

Accounting Procedures Act of 1950, as amended; Reorganization

Plan No. 2 of 1970; and Executive Order No. 11541.

3.   Supersession.  Circular A-133 supersedes Attachment F,

subparagraph 2h, of Circular A-110, "Uniform Administrative

Requirements for Grants and other Agreements with Institutions of

Higher Education, Hospitals, and other Nonprofit organizations."

4.   Applicability.  The provisions of Circular A-133 apply to:

a.   Federal departments and agencies responsible for

administering programs that involve grants, cost-type contracts

and other agreements with institutions of higher education and

other nonprofit recipients.

b.   Nonprofit institutions, whether they are recipients,

receiving awards directly from Federal agencies, or are sub-recipients,

receiving awards indirectly through other recipients.

These principles, to the extent permitted by law, constitute

guidance to be applied by agencies consistent with and within the

discretion, conferred by the statutes governing agency action.

5.   Requirements and Responsibilities.

The specific requirements and responsibilities of Federal

departments and agencies and institutions of higher education and

other nonprofit institutions are set forth in the attachment.

6.   Effective Date.  The provisions of circular A-133 are

effective upon publication and shall apply to audits of nonprofit

institutions for fiscal years that begin on or after January 1,

1990.  Earlier implementation is encouraged.  However, until this

_____________________________________________________________________

Circular is implemented, the audit provisions of Attachment F to

Circular A-110 shall continue to be observed.

7.   Policy Review (Sunset) Date.  Circular A-133 will have a

policy review three years from the date of issuance.

8.   Inquiries.  Further information concerning circular A-133

may be obtained by contacting the Financial Management Division,

Office of Management and Budget, Washington, D.C. 20503,

telephone (202) 395-3993.

Richard G. Darman

Director

2

_____________________________________________________________________

-    Individual awards not in the student aid or

research and development category.

j.   "Management decision" moans the evaluation by the

management of an establishment of the findings and

recommendations included in an audit report and the issuance of a

final decision by management concerning its response to such

findings and recommendations, including actions concluded to be

necessary.

k.   "Nonprofit institution" means any corporation, trust,

association, cooperative or other organization which 1) is

operated primarily for scientific, educational, service,

charitable, or similar purposes in the public interest; 2) is not

organized primarily for profit; and 3) uses its net proceeds to

maintain, improve, and/or expand its operations.  The term

"nonprofit institutions" includes institutions of higher

education, except those institutions that are audited as part of

single audits in accordance with Circular A-128 "Audits of State

and Local Governments."  The term does not include hospitals

which are not affiliated with an institution of higher education,

or State and local governments and Indian tribes covered by

Circular A-128 "Audits of State and Local Governments."

l.   "Oversight" agency means the Federal agency that

provides the predominant amount of direct funding to a recipient

not assigned a cognizant agency, unless no direct funding is

received.  Where there is no direct funding, the Federal agency

with the predominant indirect funding will assume the general

oversight responsibilities.  The duties of the oversight agency

are described in paragraph 4 of this Attachment.

m.   "Recipient" means an organization receiving financial.

assistance to carry out a program directly from Federal agencies.

n.   "Research and development" includes all research

activities, both basic and applied, and all development

activities that are supported at universities, colleges, and

other nonprofit institutions.  "Research" is defined as a

systematic study directed toward fuller scientific knowledge or

understanding of the subject studied.  "Development" is the

systematic use of knowledge and understanding gained from

research directed toward the production of useful materials,

devices, systems, or methods, including design and development of

prototypes and processes.

o.   "Student Financial Aid" includes those programs of

general student assistance in which institutions participate,

such as those authorized by Title IV of the Higher Education Act

of 1965 which is administered by the U.S. Department of Education

and similar programs provided by other Federal agencies.  It does

not include programs which provide fellowships or similar awards

3

_____________________________________________________________________

to students on a competitive basis, or for specified studies or

research.

p.   "Sub-recipient" means any person or government

department, agency, establishment, or nonprofit organization that

receives financial assistance to carry out a program through a

primary recipient or other sub-recipient, but does not include an

individual that is a beneficiary of such a program.  A sub-recipient

may also be a direct recipient of Federal awards under

other agreements.

q.   "Vendor" means an organization providing a recipient or

sub-recipient with generally required goods or services that are

related to the administrative support of the Federal assistance

program.

2.   Audit of Nonprofit Institutions.

a.   Requirements Based on Awards Received.

(1)  Nonprofit institutions that receive $100,000 or

more a year in Federal awards shall have an audit made in

accordance with the provisions of this Circular.  However,

nonprofit institutions receiving $100,000 or more but receiving

awards under only one program have the option of having an audit

of their institution prepared in accordance with the provisions

of the Circular or having an audit made of the one program.  For

prior or subsequent years, when an institution has only loan

guarantees or outstanding loans that were made previously, the

institution may be required to conduct audits for those programs,

in accordance with regulations of the Federal agencies providing

those guarantees or loans.

(2)  Nonprofit institutions that receive at least

$25,000 but less than $100,000 a year in Federal awards shall

have an audit made in accordance with this Circular or have an

audit made of each Federal award, in accordance with Federal laws

and regulations governing the programs in which they participate.

(3)  Nonprofit institutions receiving less than $25,000

a year in Federal awards are exempt from Federal audit

requirements, but records must be available for review by

appropriate officials of the Federal grantor agency or

subgranting entity.

b.   Oversight by Federal

(1)  To each of the larger nonprofit institutions the

Office of Management and Budget (OMB) will assign a Federal

agency as the cognizant agency for monitoring audits and ensuring

the resolution of audit findings that affect the programs of more

than one agency.

4

_____________________________________________________________________

(2)  Smaller institutions not assigned a cognizant

agency will be under the general oversight of the Federal agency

that provides them with the most funds.

(3)  Assignments to Federal cognizant agencies for

carrying out responsibilities in this section are set forth in a

separate supplement to this Circular.

(4)  Federal Government-owned, contractor-operated

facilities at institutions or laboratories operated primarily for

the Government are not included in the cognizance assignments.

These will remain the responsibility of the contracting agencies.

The listed assignments cover all of the functions in this

Circular unless otherwise indicated.  The Office of Management

and Budget will coordinate changes in agency assignments.

3.   Cognizant Agency Responsibilities.  A cognizant agency

shall:

a.   Ensure that audits are made and reports are received in

a timely manner and in accordance with the requirements of this

Circular.

b.   Provide technical advice and liaison to institutions

and independent auditors.

c.   Obtain or make quality control reviews of selected

audits made by non-Federal audit organizations, and provide the

results, when appropriate, to other interested organizations.

d.   Promptly inform other affected Federal agencies and

appropriate Federal law enforcement officials of any reported

illegal acts or irregularities.  A cognizant agency should also

inform State or local law enforcement and prosecuting

authorities, if not advised by the recipient, of any violation of

law within their jurisdiction.

e.   Advise the recipient of audits that have been found not

to have met the requirements set forth in this Circular.  In such

instances, the recipient will work with the auditor to take

corrective action.  If corrective action is not taken, the

cognizant agency shall notify the recipient and Federal awarding

agencies of the facts and make recommendations for follow-up

action.  Major inadequacies or repetitive substandard performance

of independent auditors shall be referred to appropriate

professional bodies for disciplinary action.

f.   Coordinate, to the extent practicable, audits or

reviews made for Federal agencies that are in addition to the

audits made pursuant to this Circular, so that the additional

5

_____________________________________________________________________

audits or reviews build upon audits performed in accordance with

the Circular.

g.   Ensure the resolution of audit findings that affect the

programs of more than one agency.

h.   Seek the views of other interested agencies before

completing a coordinated program.

i.   Help coordinate the audit work and reporting

responsibilities among independent public accountants, State

auditors, and both resident and non-resident Federal auditors to

achieve the most cost-effective audit.

4.   Oversight Agency Responsibilities.  An oversight agency

shall provide technical advice and counsel to institutions and

independent auditors when requested by the recipient.  The

oversight agency may assume all or some of the responsibilities

normally performed by a cognizant agency.

5.   Recipient Responsibilities.  A recipient that receives a

Federal award and provides $25,000 or more of it during its

fiscal year to a sub-recipient shall:

a.   Ensure that the nonprofit institution sub-recipients

that receive $25,000 or more have met the audit requirements of

this circular, and that sub-recipients subject to OMB Circular

A-128 have met the audit requirements of that Circular;

b.   Ensure that appropriate corrective action is taken

within six months after receipt of the sub-recipient audit report

in instances of noncompliance with Federal laws and regulations;

c.   Consider whether sub-recipient audits necessitate

adjustment of the recipient's own records; and

d.   Require each sub-recipient to permit independent

auditors to have access to the records and financial statements

as necessary for the recipient to comply with this Circular.

6.   Relation to other Audit Requirements.

a.   An audit made in accordance with this Circular shall be

in lieu of any financial audit required under individual Federal

awards.  To the extent that an audit made in accordance with this

Circular provides Federal agencies with the information and

assurances they need to carry out their overall responsibilities,

they shall rely upon and use such information.  However, a

Federal agency shall make any additional audits or reviews

necessary to carry out responsibilities under Federal law and

regulation.  Any additional Federal audits or reviews shall be

6

_____________________________________________________________________

planned and carried out in such a way as to build upon work

performed by the independent auditor.

b.   Audit planning by Federal audit agencies should

consider the extent to which reliance can be placed upon work

performed by other auditors.  Such auditors include State, local,

Federal, and other independent auditors, and a recipient's

internal auditors.  Reliance placed upon the work of other

auditors should be documented and in accordance with Government

Auditing standards.

c.   The provisions of this Circular do not limit the

authority of Federal agencies to make or contract for audits and

evaluations of Federal awards, nor do they limit the authority of

any Federal agency Inspector General or other Federal official.

d.   The provisions of this Circular do not authorize any

institution or sub-recipient thereof to constrain Federal

agencies, in any manner, from carrying out additional audits,

evaluations or reviews.

e.   A Federal agency that makes or contracts for audits, in

addition to the audits made by recipients pursuant to this

Circular, shall, consistent with other applicable laws and

regulations, arrange for funding the cost of such additional

audits.  Such additional audits or reviews include financial,

performance audits and program evaluations.

7.   Frequency of Audit.  Audits shall usually be performed

annually but not less frequently than every two years.

8.   Sanctions.  No audit costs may be charged to Federal awards

when audits required by this Circular have not been made or have

been made but not in accordance with this Circular.  In cases of

continued inability or unwillingness to have a proper audit in

accordance with the Circular, Federal agencies must consider

appropriate sanctions including:

--   withholding a percentage of awards until the audit is

completed satisfactorily;

--   withholding or disallowing overhead costs; or

--   suspending Federal awards until the audit in made.

9.   Audit Costs.  The cost of audits made in accordance with the

provisions of this Circular are allowable charges to Federal

awards.  The charges may be considered a direct cost or an

allocated indirect cost, determined in accordance with the

provisions of Circular A-21, "Cost Principles for Universities"

or Circular A-122, "Cost Principles for Nonprofit Organizations"

7

_____________________________________________________________________

FAR subpart 31, or other applicable cost principles or

regulations.

10.  Auditor Selection.  In arranging for audit services

institutions shall follow the procurement standards prescribed by

Circular A-110, "Uniform Requirements for Grants and Agreements

with Institutions of Higher Education, Hospitals and other

Nonprofit Organizations."

11.  Small and Minority Audit Firms.

a.   Small audit firms and audit firms owned and controlled

by socially and economically disadvantaged individuals shall have

the maximum practicable opportunity to participate in contracts

awarded to fulfill the requirements of this Circular.

b.   Recipients of Federal awards shall take the following

steps to further this goal:

(1)  Ensure that small audit firms and audit firms

owned and controlled by socially and economically disadvantaged

individuals are used to the fullest extent practicable;

(2)  Make information on forthcoming opportunities

available and arrange timeframes for the audit to encourage and

facilitate participation by small audit firms and audit firms

owned and controlled by socially and economically disadvantaged

individuals;

(3)  Consider in the contract process whether firms

competing for larger audits intend to subcontract with small

audit firms and audit firms owned and controlled by socially and

economically disadvantaged individuals;

(4)  Encourage contracting with small audit firms or

audit firms owned and controlled by socially and economically

disadvantaged individuals which have traditionally audited

government programs, and in cases where this is not possible,

assure that these firms are given consideration for audit

subcontracting opportunities;

(5)  Encourage contracting with consortiums of small

audit firms as described in section (1), above, when a contract

is too large for an individual small audit firm or audit firm

owned and controlled by socially and economically disadvantaged

individuals; and

(6)  Use the services and assistance, as appropriate,

of such organizations as the Small Business Administration in the

solicitation and utilization of small audit firms or audit firms

owned and controlled by socially and economically disadvantaged

individuals.

8

_____________________________________________________________________

12.  Scope of Audit and Audit Objectives.

a.   The audit shall be made by an independent auditor in

accordance with Government Auditing Standards developed by the

Comptroller General of the United States covering financial

audits.  An audit under this Circular should be an

organization-wide audit of the institution.  However, there may

be instances where Federal auditors are performing audits or are

planning to perform audits at nonprofit institutions.  In these

cases, to minimize duplication of audit work, a coordinated audit

approach may be agreed upon between the independent auditor, the

recipient and the cognizant agency or the oversight agency.

Those auditors who assume responsibility for any or all of the

reports called for by paragraph 15 should follow guidance set

forth in Government Auditing Standards in using work performed by

others.

b.   The auditor shall determine whether:

(1)  The financial statements of the institution

present fairly its financial position and the results of its

operations in accordance with generally accepted accounting

principles;

(2)  The institution has an internal control structure

to provide reasonable assurance that the institution is managing

Federal awards in compliance with applicable laws and

regulations, and controls that ensure compliance with the laws

and regulations that could have a material impact on the

financial statements; and

(3)  The institution has complied with laws and

regulations that may have a direct and material effect on its

financial statement amounts and on each major Federal program.

13.  Internal Controls Over Federal Awards; Compliance Reviews.

a.   General.  The independent auditor shall determine and

report on whether the recipient has an internal control structure

to provide reasonable assurance that it is managing Federal

awards in compliance with applicable laws, regulations, and

contract terms, and that it safeguards Federal funds.  In

performing these reviews, independent auditors should rely upon

work performed by a recipient's internal auditors to the maximum

extent possible.  The extent of such reliance should be based

upon the Government Auditing Standards.

b.   Internal Control Review.

(1)  In order to provide this assurance on internal

controls, the auditor must obtain an understanding of the

9

_____________________________________________________________________

internal control structure and assess levels of internal control

risk.  After obtaining an understanding of the controls, the

assessment must be made whether or not the auditor intends to

place reliance on the internal control structure.

(2)  As part of this review, the auditor shall:

(a)  Perform tests of controls to evaluate the

effectiveness of the design and operation of the policies and

procedures in preventing or detecting material noncompliance.

Tests of controls will not be required for those areas where the

internal control structure policies and procedures are likely to

be ineffective in preventing or detecting noncompliance, in which

case a reportable condition or a material weakness should be

reported in accordance with paragraph 15 c(2) of this Circular.

(b)  Review the recipient's system for monitoring

sub-recipients and obtaining and acting on sub-recipient audit

reports.

(c)  Determine whether controls are in effect to

ensure direct and indirect costs were computed and billed in

accordance with the guidance provided in the general requirements

section of the compliance supplement to this circular.

c.   Compliance Review.

(1)  The auditor shall determine whether the recipient

has complied with laws and regulations that may have a direct and

material effect on any of its major Federal programs.  In

addition, transactions selected for non-major program shall be

touted for compliance with Federal laws and regulations that

apply to such transactions.

(2)  In order to determine which major programs are to

be tested for compliance, recipients shall identify, in their

accounts, all Federal funds received and expended and the

programs under which they were received.  This shall include

funds received directly from Federal agencies, through other

State and local governments or other recipients.  To assist

recipients in identifying Federal awards, Federal agencies and

primary recipients shall provide the Catalog of Federal Domestic

assistance (CFDA) numbers to the recipients when making the

awards.

(3)  The review must include the selection of an

adequate number of transactions from each major Federal financial

assistance program so that the auditor obtains sufficient

evidence to support the opinion on compliance required by

paragraph 15c(3) of this Attachment.  The selection and testing

of transactions shall be based on the auditors' professional

judgment considering such factors as the amount of expenditures

10

_____________________________________________________________________

for the program; the newness of the program or changes in its

conditions; prior experience with the program particularly as

revealed in audits and other evaluations (e.g., inspections,

program reviews, or system reviews required by Federal

Acquisition Regulations); the extent to which the program is

carried out through sub-recipients; the extent to which the

program contracts for goods or services; the level to which the

program is already subject to program reviews or other forms of

independent oversight; the adequacy of the controls for ensuring

compliance; the expectation of adherence or lack of adherence to

the applicable laws and regulations; and the potential impact of

adverse findings.

(4)  In making the test of transactions, the auditor

shall determine whether:

--   the amounts reported as expenditures were for

allowable services, and

--   the records show that those who received

services or benefits were eligible to receive

them.

(5)  In addition to transaction testing, the auditor

shall determine whether:

--   matching requirements, levels of effort and

earmarking limitations were met,

--   Federal financial reports and claims for

advances and reimbursement contain

information that is supported by books and

records from which the basic financial

statements have boon prepared, and

--   amounts claimed or used for matching were

determined in accordance with 1) OMB Circular

A-21, "Cost Principles for Educational

Institutions"; 2) matching or cost sharing

requirements in Circular A-110, "Uniform

Requirements for Grants and Agreements with

Institutions of Higher Education, Hospitals

and Other Nonprofit Organizations"; 3)

Circular A-122, "Cost Principles for

Nonprofit Organizations"; 4) FAR subpart 31

cost principles; and 5) other applicable cost

principles or regulations.

(6)  The principal compliance requirements of the

largest Federal programs may be ascertained by referring to the

"Compliance Supplement for Single Audits of Educational

Institutions and other Nonprofit Organizations," and the

11

_____________________________________________________________________

"Compliance Supplement for Single Audits of State and Local

Governments," issued by OMB and available from the Government

Printing office.  For those programs not covered in the

Compliance Supplements, the auditor should ascertain compliance

requirements by reviewing the statutes, regulations, and

agreements governing individual programs.

(7)  Transactions related to other awards that are

selected in connection with examinations of financial statements

and evaluations of internal controls shall be tested for

compliance with Federal laws and regulations that apply to such

transactions.

14.  Illegal Acts.  If, during or in connection with the audit of

a nonprofit institution, the auditor becomes aware of illegal

acts, such acts shall be reported in accordance with the

provisions of the Government Auditing Standards.

15.  Audit

a.   Audit reports must be prepared at the completion of the

audit.

b.   The audit report shall state that the audit was made in

accordance with the provisions of this circular.

c.   The report shall be made up of at least the following

three parts:

(1)  The financial statements and a schedule of Federal

awards and the auditor's report on the statements and the

schedule.  The schedule of Federal awards should identify major

programs and show the total expenditures for each program.

Individual major programs other than Research and Development and

Student Aid should be listed by catalog number as identified in

the Catalog of Federal Domestic Assistance.  Expenditures for

Federal programs other than major programs shall be shown under

the caption "other Federal assistance."  Also, the value of

non-cash assistance such an loan guarantees, food commodities or

donated surplus properties or the outstanding balance of loans

should be disclosed in the schedule.

(2)  A written report of the independent auditor's

understanding of the internal control structure and the

assessment of control risk.  The auditor's report should include

an a minimum:  1) the scope of the work in obtaining understanding

of the internal control structure and in assessing the control

risk, 2) the nonprofit institution's significant internal

controls or control structure including the controls established

to ensure compliance with laws and regulations that have a

material impact on the financial statements and those that

provide reasonable assurance that Federal awards are being

12

_____________________________________________________________________

managed in compliance with applicable laws and regulations, and

3) the reportable conditions, including the identification of

material weaknesses, identified as a result of the auditor's work

in understanding and assessing the control risk.  If the auditor

limits his/her consideration of the internal control structure

for any reason, the circumstances should be disclosed in the

report.

(3)  The auditor's report on compliance containing:

--   An opinion as to whether each major Federal

program was being administered in compliance with

laws and regulations applicable to the matters

described in paragraph 13(c)(3) of this

Attachment, including compliance with laws and

regulations pertaining to financial reports and

claims for advances and reimbursements;

--   A statement of positive assurance on those items

that were tested for compliance and negative

assurance on those items not tested;

--   Material findings of noncompliance presented in

their proper perspective:

o    The size of the universe in number of items

and dollars,

o    The number and dollar amount of transactions

tested by the auditors,

o    The number and corresponding dollar amount of

instances of noncompliance;

--   Where findings are specific to a particular

Federal award, an identification of total amounts

questioned, if any, for each Federal award, as a

result of noncompliance and the auditor's

recommendations for necessary corrective action.

d.   The three parts of the audit report may be bound into a

single document, or presented at the same time as separate

documents.

e.   Nonmaterial findings need not be disclosed with the

compliance report but should be reported in writing to the

recipient in a separate communication.  The recipient, in turn,

should forward the findings to the Federal grantor agencies or

subgrantor sources.

f.   All fraud or illegal acts or indications of such acts,

including all questioned costs found as the result of these acts

13

_____________________________________________________________________

that auditors become aware of, may be covered in a separate

written report submitted in accordance with the Government

Auditing Standards.

g.   The auditor's report should disclose the status of

known but uncorrected significant material findings and

recommendations from prior audits that affect the current audit

objective as specified in the Government Auditing Standards.

h.   In addition to the audit report, the recipient shall

provide a report of its comments on the findings and

recommendations in the report, including a plan for corrective

action taken or planned and comments on the status of corrective

action taken on prior findings.  If corrective action is not

necessary, a statement describing the reason it is not should

accompany the audit report.

i.   Copies of the audit report shall be submitted in

accordance with the reporting standards for financial audits

contained in the Government Auditing Standards.  Sub-recipient

auditors shall submit copies to recipients that provided Federal

awards.  The report shall be due within 30 days after the

completion of the audit, but the audit should be completed and

the report submitted not later than 13 months after the end of

the recipient's fiscal year unless a longer period is agreed to

with the cognizant or oversight agency.

j.   Recipients of more than $100,000 in Federal awards

shall submit one copy of the audit report within 30 days after

issuance to a central clearinghouse to be designated by the

Office of Management and Budget.  The clearinghouse will keep

completed audit reports on file.

k.   Recipients shall keep audit reports, including

sub-recipient reports, on file for three years from their issuance.

16.  Audit Resolution.

a.   As provided in paragraph 3, the cognizant agency shall

be responsible for ensuring the resolution of audit findings that

affect the programs of more than one Federal agency.  Resolution

of findings that relate to the programs of a single Federal

agency will be the responsibility of the recipient and the

agency.  Alternate arrangements may be made on case-by-case basis

by agreement among the agencies concerned.

b.   A management decision shall be made within six months

after receipt of the report by the Federal agencies responsible

for audit resolution.  Corrective action should proceed as

rapidly as possible.

14

_____________________________________________________________________

ATTACHMENT 5

_____________________________________________________________________

LOCCS

Voice Response System

Access Authorization

__________________________________________________________________________

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

form HUD-27054 (8/92)

_____________________________________________________________________

__________________________________________________________________________

Instructions for the

LOCCS Voice Response Access Authorization

Security Form

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

form HUD-27054

_____________________________________________________________________

ATTACHMENT 6

_____________________________________________________________________

Standard Form 1199A

__________________________________________________________________________

DIRECT DEPOSIT SIGN-UP FORM

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

_____________________________________________________________________

ATTACHMENT 7

_____________________________________________________________________

__________________________________________________________________________

LOCCS Access Authorization

Security Form

for HUD Staff

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

form HUD-27054-A (8/92)

_____________________________________________________________________

__________________________________________________________________________

Instructions for

LOCCS Access Authorization

Security Form

for HUD Staff

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

form HUD-27054-A

_____________________________________________________________________

ATTACHMENT 8

_____________________________________________________________________

__________________________________________________________________________

LOCCS/VRS

Preservation Technical Assistance

Planning Grant Payment Voucher

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

form HUD-9738 (1\12\93)

page 1 of 2

_____________________________________________________________________

__________________________________________________________________________

Instructions for the

Preservation of Affordable Housing Program

Technical Assistance

Planning Grant Payment Voucher:

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

form HUD-9738

page 2 of 2

_____________________________________________________________________

ATTACHMENT 9

_____________________________________________________________________

LINE OF CREDIT CONTROL SYSTEM (LOCCS)

USER GUIDE

AUGUST 1992

_____________________________________________________________________

INTRODUCTION

The Line of Credit Control System, (LOCCS), User's Guide has been written

to service Program/Recipients and HUD Field Offices for their particular

applications.  Content is universal in scope and is not intended to provide

an in depth and complete detail of the LOCCS System.  If you have any

questions about LOCCS that exceed the boundaries of this user's guide,

please contact your respective field office or HUD program representative.

ABOUT PART 1

Part 1 of this user's guide is written to address general specifics and

need-to-know information that is basically of important to the Grantee/

Recipient.  Highlights of Part 1 include:

-       Generation of a VRS Number

-       Designation of a Depository - Direct Deposit Sign-Up Form

(SF 1199A)

-       Security Access Controls - Grantee/Recipient

-       Operation of the VRS System

-       Sample Vouchers and related VRS dialogue

-       Return of Funds - Wire Transfers

ABOUT PARTS 2 AND 3

Parts 2 and 3 are provided for HUD Program Office Staff.  Highlights of

Parts 2 and 3 include:

-       Accessing LOCCS by program staff

-       LOCCS Screens

-       LOCCS Security Procedures

-       Exhibits of Access Authorization Form (HUD-27054A) & ADP

Policy Statement

NOTE

Referenced exhibits, related instructions, VRS sample drawdowns and

associated VRS dialogues are contained within their respective parts to

the guide.

July 22, 1992                      i

_____________________________________________________________________

TABLE OF CONTENTS

Page

PART 1 - GRANTEE/RECIPIENT  ................. 1-1

SECTION 1.  LINE OF CREDIT CONTROL SYSTEM (LOCCS) - VOICE RESPONSE

SYSTEM (VRS)............................................. 1-1

1.1 Background of LOCCS........................................ 1-1

1.2 Background of Voice Response System ....................... 1-1

SECTION 2.  ESTABLISHMENT OF LINE OF CREDIT  ........................ 2-1

2.1 Generation of a VRS Number  ............................... 2-1

2.2 Designation of Depository-Direct Sign-Up Form (SF 1199A)... 2-1

2.3 Security Access Controls - Grantee/Recipient .............. 2-2

2.4 LOCCS Voice Response Access Authorization Form (HUD-27054). 2-2

2.5 Accessing LOCCS - Grantee/Recipient  ...................... 2-4

2.6 Changing Password via VRS ................................. 2-4

2.7 Logging Off the VRS ....................................... 2-4

2.8 Change of Address for Recipient of HUD Grants (HUD 27056) . 2-5

2.9 LOCCS Headquarters-Generated Letters  ..................... 2-5

EXHIBIT

2-1 Sample Letter, VRS Number Sent to Grantee/Recipient ....... 2-6

2-2 Direct Deposit Sign-Up Form, SF 1199A  .................... 2-7

2-3 Certified Letter, User ID and Password  ................... 2-9

2-4 LOCCS Voice Response Access Authorization Form, HUD 27054..2-10

2-5 Change of Address Request for Recipients of

HUD Grants or Contracts (HUD 27056 ....................... 2-12

July 22, 1992                     ii

_____________________________________________________________________

TABLE OF CONTENTS

Page

SECTION 3.  OPERATION OF VOICE RESPONSE SYSTEM (VRS)................  3-1

3.1 Preparation of Grant Vouchers for Payments ................  3-1

3.2 Calling-in the Grant Voucher Request ......................  3-1

3.3 LOCCS-VRS Edits and Reviews  ..............................  3-2

EXHIBIT

3-1 Request Voucher for Grant Payment, HUD 27053  .............  3-3

3-1 SAMPLE LOCCS VRS GRANT DRAWDOWN DIALOUGE  .................  3-7

PHASE 1 DIALOGUE:  Asking for and confirming entry

of a voucher number  .......................  3-6

PHASE 2 DIALOGUE:  Entering a project number and amount .......  3-8

PHASE 3 DIALOGUE:  Voucher Repeat  ............................ 3-12

PHASE 4 DIALOGUE:  Voucher Confirmation Text  ................. 3-14

3.2  Sample Budget Line Item Payment Voucher  ................. 3-16

3.2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN DIALOGUE ...... 3-19

SECTION 4.  RETURN OF FUNDS - WIRE TRANSFER PROCEDURES..............  4-1

August 18, 1992                       iii

_____________________________________________________________________

TABLE OF CONTENTS

Page

PART 2 - HUD PROGRAM STAFF .............  5-1

SECTION 5.  LINE OF CREDIT CONTROL SYSTEM (LOCCS) - HUD EMPLOYEES...  5-1

5.1 Field Staff Overview of LOCCS-VRS.........................  5-1

5.2 Background of LOCCS and VRS...............................  5-1

SECTION 6.  ACCESSING LOCCS - HUD Employees ........................  6-1

6.1 Entering User ID and Password.............................  6-1

6.2 Changing the Password.....................................  6-2

6.3 Logging Off Screens ......................................  6-2

6.4 LOCCS SCREENS ............................................  6-3

PART 3 - LOCCS SECURITY PROCEDURES ............  7-1

SECTION 7.  LOCCS SECURITY PROCEDURES ..............................  7-1

7.1  LOCCS User Background ...................................  7-1

7.2  HUD Employees ...........................................  7-1

7.3  Grantee/Recipient .......................................  7-1

7.4  LOCCS access control ....................................  7-1

7.5  Issuing Security IDs and Passwords ......................  7-2

7.6  Privacy of IDs and Passwords ............................  7-2

7.7  Canceling Old Security IDs and Issuing New IDs ..........  7-2

7.8  Establishing and Update of Passwords ....................  7-3

7.9  Validation of Access ....................................  7-3

7.10 Procedural Controls......................................  7-4

7.11 Access Authorization Security Form ......................  7-4

7.12 HUD Departmental ADP Policy Statement ...................  7-5

7.13 HUD Employees ...........................................  7-5

EXHIBIT

7.1  Access Authorization Security Form.......................  7-7

7.2  HUD Departmental ADP Policy Statement ...................  7-8

July 22, 1992                       iv

_____________________________________________________________________

PART 1 - GRANTEE/RECIPIENT

SECTION 1.  LINE OF CREDIT CONTROL SYSTEM

1.1  Background of LOCCS

Payments are scheduled and disbursed by the Line of Credit Control System

(LOCCS), System ID A67.  This system uses a cash management computer

software program which ensures that distributions do not exceed authorized

limitations.  LOCCS and Program Accounting System (PAS) interface on a

nightly basis to ensure consistency of the information stored in the two

systems.  Each day, LOCCS generates a payment tape for Treasury which

disburses the payment via the Automated Clearing House (ACH) Payment System

and a Voucher and Schedule of Payment (SF-1166) for each Regional Agency

Location Code (ALC).  All payments are certified by Headquarters and

forwarded to Treasury for processing.

1.2  Background of Voice Response System

The LOCCS Voice System (VRS) enables the grantee/recipient to request

grant payment funds from HUD through the use of their touch-tone telephone.

The grantee/recipient must complete Form HUD 27054, LOCCS Voice Response

System Access Authorization, and submit the form to the HUD for review

prior to draw down.

NOTE:    The grantee/recipient shall contact the responsible Program

Office to obtain Form HUD-27054, LOCCS Voice Response System

Access Authorization and the program-specific voucher for grant

payment.

July 22, 1992                        1-1

_____________________________________________________________________

SECTION 2.  ESTABLISHMENT OF LINE OF CREDIT

The establishment of a Line of Credit has three phases:

o  Generation of a VRS Number;

o  Designation of a Depository; and

o  LOCCS Voice Response Access Authorization.

2.1  Generation of a VRS Number

To generate a VRS Number, the grantee/recipient must first return the fully

executed Funding Approval Grant (Contract) to HUD.

If the grantee/recipient has no grant awards currently funded with HUD, a

SF-1199A, Direct Deposit Sign Up Form, must be provided to HUD to identify

the grantee/recipient Tax Identification Number (TIN).  The TIN is a nine

(9) digit number which all employers must have for Federal income tax

purposes.  The TIN number will be linked automatically with the

project/grant number which will establish a Line of Credit and generate a

VRS number for the grantee/recipient.

Once the VRS number has been generated, HUD Headquarters in Washington,

D.C. will automatically generate a letter containing the VRS number and

mail the letter to the grantee/recipient.  The VRS number allows the

grantee/recipient to key in a number that identifies the project/grant over

the touch tone telephone.  A copy of a sample VRS number letter sent to the

grantee/recipient is shown in Exhibit 2-1.

2.2  Designation of Depository-Direct Deposit Sign-Up Form (SF 1199A)

The SF-1199A provides HUD with the authorization to make direct deposit

through the Federal Reserve to the grantee's/recipient's designated account

using the Treasury ACH Payment System.  This form must be completed and

returned to HUD if program guidelines require the grantee/recipient to

submit the form.  The SF-1199A is not needed on an annual basis.  Exhibit

2-2 provides an example and instructions for completing form SF 1199A.

A revised SF 1199A must be submitted if there is a change of depository, or

a change in mailing address of a designated depository.  Correspondence

regarding LOCCS-VRS will go to the address indicated for the payee

(grantee/recipient) on the SF-1199A, not the address on the grant/award.

If correspondence should be sent to somewhere other than was specified on

the SF-1199A, a Change of Address Form (HUD 27056) must be completed and

submitted to HUD.  See Section 2.6 for information regarding change of

address.

July 22, 1992                       2-1

_____________________________________________________________________

2.3  Security Access Controls - Grantee/Recipient

These users are personnel who work for the Recipient organizations that are

receiving funds for HUD programs (i.e., provide low-cost housing, rehab

housing, homeless housing, etc.).  These recipient organizations can be

states, municipalities, cities, counties, towns, and private organizations.

These users access LOCCS via the LOCCS Voice Response System (VRS).  All

Voice Response System (VRS) users will submit a signed and notarized LOCCS

Voice Response System (VRS) Access Authorization Form (Exhibit 2-4).

The Office of Information Policies and Systems (IPS), assigns USERIDs and

initial Passwords and writes the USERID and initial Password on the Access

Form.  A letter informing the user of the USERID and Password is sent back

to the user via certified mail stamped "OPEN BY ADDRESSEE ONLY".  The

original form is stored by AISAO for audit purposes.  Exhibit 2-3 depicts

a sample authorization letter.

Annually, grantee/recipient approving officials must validate their users.

A letter is sent to each recipient organization's approving official

listing valid users and VRS functions.  Termination of access or correction

of data will be the only update features allowed on this report.

Validation of this report must be signed by the approving official and

notarized for return to HUD within 15 days.

All reports must be returned to:

U.S. Department of Housing and Urban Development

Office of Information Policies and Systems

AISAO

451 Seventh St., S. W.,

Washington, DC 20410-3600

2.4  LOCCS Voice Response Access Authorization Form (HUD-27054)

This form (HUD 20754) is used by any recipient organizations that wish to

access the program areas that participate in the Voice Response System.

Instructions for completion are included on the reverse of the form (shown

as Exhibit 2-4).  Access  to the LOCCS-VRS is only for authorized

individuals who have obtained appropriate security User identification

numbers (IDs) and passwords.  It is recommended that each grantee/recipient

have at least two persons authorized to access LOCCS-VRS.

Each grantee/recipient authorized person must complete an individual

security access request form HUD-27054, LOCCS Voice Response Access

Authorization.  The form must be signed by the approving official

representing the grantee/recipient or his/her designee and notarized prior

to submission to HUD.  IN NO EVENT CAN THE APPROVING OFFICIALS APPROVE

THEMSELVES FOR ACCESS TO THE SYSTEM.

July 22, 1992                     2-2

_____________________________________________________________________

Upon receipt of the completed security form, HUD Headquarters will issue

each authorized person a user ID and a password.  The user ID and password

will be issued by certified mail, return receipt requested,  "OPEN BY

ADDRESSEE ONLY".  See Exhibit 2-3 Certified User ID and password letter.

It is crucial to the security of the HUD VRS that each individual safeguard

his/her user ID and password.  In no instance should this user ID and

password be "shared" with others.  A breach in the security system by any

staff member will result in an immediate termination of user ID and

password.

Form HUD 27054, LOCCS-Voice Response System Access Authorization Form

shall be completed whenever any of the following changes are required:

o    Add new users

o    Change user program access authority

o    Terminate User

o    Reset passwords

User ID cannot be changed; however, passwords can be changed as needed.

Passwords must be changed every 60 days from the last time a password was

established for the user ID.  The password change will be entered via the

touch-tone telephone.

It may be necessary to cancel the security access for an individual(s)

because of a change in personnel.  An ID may be immediately canceled by

calling the Office of Information Policies and Systems (IPS) at (202)

708-0764 in Washington, D.C.  IPS should be notified in writing as quickly

as possible but at least within three(3) working days from the time of the

cancellation.  The grantee/recipient should then submit to the HUD Program

Office the Form HUD 27054 terminating the user.

July 22, 1992                      2-3

_____________________________________________________________________

2.5  ACCESSING LOCCS - Grantee/Recipient

All LOCCS Voice Response users sign on to the system in the same manner.

Using a Touch-Tone telephone, the user dials the Voice Response number.

A greeting is heard asking the user to select a function or program area

or system to access.

All Voice Response users will have to key in their User IDs and passwords

before performing any LOCCS functions.

The VRS directs users to enter the user ID and password to gain access to

LOCCS.  The system also allows them to indicate if they want to change

their passwords.

The system will validate the user ID and password against the data base

that contains the authorized user list.  The system will also check the

status of the user ID record and check the approved function(s) permitted.

If an error is detected, the error condition will be spoken back to the

user.  The user is allowed three attempts to enter a correct user ID or

password, or to change the password.  After three attempts the user will

be automatically logged off the system and must start over.

If no errors are encountered, the user will be told how to proceed and

what functions to select.

2.6  Changing Password via VRS

The very first time the user accesses LOCCS after being assigned a user ID,

he or she have to use the initial password assigned to the user ID.  The

system will then ask the user to change the password.  A password that

will not be easily guessed by someone who knows the user should be chosen.

Don't use last name, nickname, etc.

The user may change the password whenever they call VRS.  To change the

password at signon time, precede the password entry with an asterisk(*)

when asked for the password.  The system will then ask for the new

password.  Enter the new password.  The system will ask you to re-enter the

password again to validate the original entry.  Don't forget the password.

After the User ID and Password have been validated, the user is told the

program area(s) he or she can access and the functions he or she can

perform.

2.7  Logging Off the Voice Response System (VRS)

When requesting funds, VRS users can exit the system anytime by entering

a #0 or by simply hanging up the telephone.  Caution:  Hanging up the

telephone prior to the system's instructions will terminate transactions,

and all entries up to that point will be voided.

July 22, 1992                      2-4

_____________________________________________________________________

2.8  Change of Address Request for Recipients of HUD Grants or Contracts

(HUD 27056)

Having the correct mailing address of each grantee/recipient is essential

to the effective operation of the LOCCS-VRS.  In order to keep address

records current, the Change of Address Request Form (HUD-27056) should be

used when there has been any change in the address.  It is the

grantee/recipient's responsibility to prepare and submit this form to the

HUD Program Office when there has been any change in the grantee/recipient

address.  Exhibit 2-5 contains an example of HUD 27056.

2.9  LOCCS HEADQUARTERS-GENERATED LETTERS

The grantee/recipient will receive several types of LOCCS

Headquarters-generated (Washington, D.C.) letters depending on the

individual needs and the performance of the grantee/recipient as a

participant in the LOCCS.  The following is a summary of these types of

letters.

o     VRS (Project) Number after grant is signed.

o     Notification of new/changed LOCCS-VRS access authorization.

o     Semi-annual listing to the authorizing official of users for

verification.

o     Voucher rejection by HUD.

o     Notice that financial reports are due.  This is sent before

the end of each reporting period.  If the required reports

are not received by the Program Office, LOCCS-VRS will

generate a follow up notice.

o     User IDs are terminated after 6 months of not accessing the

system.

July 22, 1992                      2-5

_____________________________________________________________________

EXHIBIT 2-1  Sample Letter - VRS Number Sent to Grantee/Recipient

U.S. DEPT. OF HUD

P.O. BOX 23699

WASHINGTON DC 20026-3699

____________

____________

CITY OF LEOMINSTER-CPD

23 WEST STREET

LEOMINSTER, MA 01453-0000

U.S.DEPT.of Housing ad Urban Development

Line of Credit Control System (LOCCS)

re: Community Development Block Grants (CDB1)

Grant Number : B90MC250013

Dear Grantee:

This is to advise you of the assignment of

your LOCCS Voice Response project number.  This

number is to be used for telephone queries and

requests for funds disbursement.

Your Voice Response project number for grant

B90MC250013 is: 05877-02001.

If you have any questions concerning this

matter, please call your local HUD field officer.

Thank you for your cooperation.

July 22, 1992                           2-6

_____________________________________________________________________

EXHIBIT 2-2  Direct Deposit Sign-Up Form, SF 1199A

___________________________________________________________________________

DIRECT DEPOSIT SIGN-UP FORM

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

July 22, 1992                    2-7

_____________________________________________________________________

EXHIBIT 2-2  Instructions for Preparation and Submission of

SF 1199A, Direct Deposit Sign-Up Form

__________________________________________________________________________

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

July 22, 1992                    2-8

_____________________________________________________________________

EXHIBIT 2-3 - Certified Letter, User ID and Password

__________________________________________________________________________

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

July 22, 1992                    2-9

_____________________________________________________________________

EXHIBIT 2-4 - LOCCS Voice Response System Access Authorization Form,

HUD 27054

__________________________________________________________________________

LOCCS

Voice Response System

Access Authorization

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

July 22, 1992                    2-10

_____________________________________________________________________

EXHIBIT 2-4 - Instructions for HUD 27054

__________________________________________________________________________

Instructions for the

LOCCS Voice Response Access Authorization

Security Form

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

July 22, 1992                    2-11

_____________________________________________________________________

EXHIBIT 2-5 - Change of Address Request for Recipients

of HUD Grants or Contracts, HUD 27056

__________________________________________________________________________

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

July 22, 1992                    2-12

_____________________________________________________________________

SECTION 3.

OPERATION OF VOICE RESPONSE SYSTEM (VRS)

The following information describes how to use LOCCS-VRS when requesting

program funds.

o Preparation of Grant Vouchers:

o Calling-in the Voucher Requests for:

O LOCCS-VRS Edits and Reviews.

3.1  Preparation of Grant Vouchers for Payments

Form HUD 27053, Request Vouched for Grant Payment (referred to as the

voucher or Standard Voucher) is pre-numbered form with an original and

(2) copies.  A budget line item payment voucher is a three (3) digit

pre-numbered form, which allows for 6 digit to be added.  The 6 digits will

be provided to the user while on the telephone.  Exhibit 3-2 is a sample of

a voucher, without the actual line numbers, that will be used for programs

that utilize the budget line item payment process.

The required Program voucher must be prepared before calling LOCCS-VRS with

the drawdown request.  The completed voucher is used as a prompt for

entering information through the touch-tone pad of the telephone and

confirming information (such as the HUD project number) that is spoken back

by the VRS simulated voice.  It is also the support documentation for audit

by HUD.  Section 3 Exhibits provides examples and instructions for

completing the required program vouchers for Grant payment.

3.2  Calling-in Grant Voucher Request

Once the voucher has been prepared, call-in the request.  This must be done

by one of the persons who is authorized to access the LOCCS-VRS and has

been issued a user ID and password by HUD.  The caller dials the telephone

number of the LOCCS-VRS equipment in HUD Headquarters:  703-391-1400

(Toll Call).

The caller is prompted by the VRS simulated voice to enter his/her user ID

and password.  After access is gained to the system, there are several

possible alternatives from which to select while making requests, each with

its own dialogue.  A sample LOCCS-VRS grant drawdown for the standard

voucher (HUD 27053) is given in Exhibit 3-1.  The actual drawdown process

will be much shorter and simpler than that illustrated in Exhibit 3-1 for

the standard voucher form.

If the caller wants to terminate a call prior to confirming the

information, he/she should enter #0 or simply hang-up and he/she can call

again using the same voucher number.  Caution:  Hanging up the telephone

prior to the system's instructions will terminate transactions, and all

entries up to that point will be voided.

Once a voucher number is used, it cannot be used again.  The system will

automatically reject it.

August 18, 1992                   3-1

_____________________________________________________________________

Vouchers called in between 8 a.m.- 6 p.m. EST will be sent to the Treasury

for payment and will be processed within two business days after receipt.

More than one voucher can be processed in the same phone call; however,

there can be only one drawdown per grant per day.

Once the caller has completed the call-in of the voucher request, the

voucher is retained on file for subsequent audit and documentary support

for the grantee/recipient request.  The documents are to be retained as

prescribed in the following handbooks:

a.     HUD Handbook 2225.6, Records Disposition Management:

HUD Records Schedules;

b.     HUD Handbook 2228.1, Records Disposition Management; and

c.     HUD Handbook 2228.2, General Records Schedules.

3.3  LOCCS-VRS Edits and Reviews

LOCCS-VRS Headquarters will perform a series of review edits (both generic

and program specific) of the voucher request.  The generic edits relate to

the correct user ID, password, project/grant identification, etc.  Programs

specific edits vary depending upon the grant program and are designed to

query the system about specific funding or reporting requirements or

limitations applicable to the grant.

Programs specific edits include reviews to determine if, for example:

(1) Cumulative cash drawdowns exceed a percentage of the total grant

amount; (2) Financial reports have not been received after the end of the

required reporting period.

Failure of one of these edits can cause the fund request to be sent to the

HUD Program Office for review and approval.  There is no default pay under

this system.  Therefore, HUD must complete the review or the request

remains as outstanding in the system.  The grantee/recipient should

immediately contact the local HUD representative when the computer

activated voice states that the request has been sent to the program office

for review and approval.

September 10, 1992                 3-2

_____________________________________________________________________

EXHIBIT 3-1 - Request Voucher for Grant Payment, HUD 27053

__________________________________________________________________________

Request Voucher

for Grant Payment

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

July 22, 1992                      3-3

_____________________________________________________________________

EXHIBIT 3-1 - Instructions for the Preparation and Submission of form

HUD 27053, Request Voucher for Grant Payment

Block 1:

Recipient Organization's Employer Identification Number (EIN) is

the nine (9) digit number that is also known as the Tax

Identification Number (TIN) in LOCCS-VRS and the

Claim or Payroll ID number on the SF-1199A.

Block 2:

Preprinted nine (9) digit all numeric voucher number.

Grantee/recipient must key the nine (9) digit number into the

touch-tone pad when calling LOCCS-VRS to request funds.

Block 3:

This block contains a maximum of 4-digit (xxxx) alpha/numeric

program area identifier as stated in block 5a of the HUD 27054,

LOCCS Voice Response System Access Authorization Form.

Block 4:

Enter the period covered by this request.

Block 5:

Enter the current balance of cash on hand.

Block 6:

Line 1:  Enter the 10-digit VRS number of the first project/grant

for which funds are being requested.  The first five digits of

this number identify the grantee/recipient; the second five

identify the specific project/grant.  The first five digits should

always be the same for a grantee/recipient.  The second five digits

should run consecutively for succeeding projects/grants within the

program.

Next, enter the HUD project/grant number for the project.  This

entry is for confirmation purposes only and will not be entered

into LOCCS-VRS through the touch-tone pad.  Instead, when the VRS

number is keyed in, the VRS simulated voice will speak the HUD

project/grant number for the caller to ensure the correct VRS

number was keyed.  Finally, enter the amount requested for that

particular project/grant.  Dollars should be entered to the left

of the asterisk(*) and cents to the right.

Lines 2 through 10:  List any other project grants in the same HUD

Programs Area for which funds are to be requested.  The total

amount requested is entered in the lower right hand corner of

block 6.

Block 7:

Enter the authorizing signature and date of signature.  The

authorizing signatory in Block 7, can not be the same person(s)

designated in block 3 of the HUD-27054, LOCCS Voice Response

System Access Authorization Form.

July 22, 1992                     3-4

_____________________________________________________________________

NOTE:  Once the pre-printed voucher number is used, the voucher number may

not be reused for future requests for funds.  The LOCCS-VRS simulated voice

will make it clear to the caller when it may or may not reuse a voucher

number.

July 22, 1992                     3-5

_____________________________________________________________________

EXHIBIT 3-1 - SAMPLE LOCCS VRS GRANT DRAWDOWN

The following example depicts a LOCCS-VRS drawdown dialogue for programs

using the standard voucher form HUD-27053.  Actual VRS dialogue is shown

in UPPERCASE ITALICIZED TEXT.

The Standard Voucher drawdown process is divided into four main phrases.

All of the phases are processed only once with the exception of Phase 2:

Entering a project and amount.  Phase 2 is repeated until all project

requests for the voucher have been entered.

Below is an outline of the Standard Voucher Dialogue which is presented on

the following pages:

PHASE 1:  Asking For and Confirming Entry of a Voucher Number.

Page 3-7

a.   Asking for a voucher number.

b.   Confirming entry of a voucher number.

c.   Asking for a Balance-on-Hand (BOH), if required.

PHASE 2:  Entering a Project Number and Amount.  Page 3-9

a.   Asking for a VRS project number.

b.   Asking for an amount.

c.   Repeating the amount requested.

d.   Speaking any review text.

e.   Asking if there are any more projects on this voucher.

PHASE 3:  Voucher Repeat Phase.  Page 3-13

a.   Repeating all projects and amounts entered and the voucher

total.

b.   Speaking any review text pertaining to the entire voucher.

PHASE 4:  Voucher Confirmation Phase.  Page 3-15

a.   Quoting confirmation text.

b.   Asking for another voucher.

July 22, 1992                      3-6

_____________________________________________________________________

EXHIBIT 3-1 - SAMPLE LOCCS VRS GRANT DRAWDOWN

PHASE 1 DIALOGUE:  Asking for and confirming entry of a voucher number.

1.a   Asking for a Voucher Number.

VRS   requests

PLEASE ENTER YOUR 9 DIGIT VOUCHER NUMBER.

if the voucher number has already been canceled:

VOUCHER NUMBER (xxxxxxxxx) HAS ALREADY BEEN CANCELED.

TO ENTER ANOTHER VOUCHER, PRESS 1.

TO RETURN TO A MENU SELECTION, PRESS 2

IF YOU ARE FINISHED, PRESS 3.

if the voucher number has already been used:

VOUCHER NUMBER (xxxxxxxxx) HAS ALREADY BEEN CALLED IN.

TO ENTER ANOTHER VOUCHER, PRESS 1.

TO RETURN TO A MENU SELECTION, PRESS 2

IF YOU ARE FINISHED, PRESS 3.

If there are no problems, go to PHASE 1.b - Confirming Entry of the

Voucher Number.

1.b   Confirming Entry of the Voucher Number.

VRS   responds

YOU HAVE ENTERED VOUCHER NUMBER (voucher number).

IF THIS IS CORRECT, PRESS 1.

TO REENTER, PRESS 2.

If the response is a "1" and a program area auto-review has been

set,

VRS   responds with

AN AUTOMATIC REVIEW IS REQUIRED ON ALL VOUCHERS CALLED IN

FROM THIS PROGRAM AREA.  THIS VOUCHER WILL REQUIRE A

(review office) HUD REVIEW.

1.c   Asking for the Balance-on-Hand (BOH) Amount.  (BOH requested only

if the program requires it.)

July 22, 1992                    3-7

_____________________________________________________________________

VRS   requests

PLEASE ENTER YOUR BALANCE-ON-HAND AMOUNT FOLLOWED BY A

POUND SIGN.

User  enters the Balance-on-Hand

VRS   responds with

YOU HAVE ENTERED A BALANCE-ON-HAND AMOUNT OF ($$$).

Continue with PHASE 2, Entering VRS Project Number and Amount.

July 22, 1992                     3-8

_____________________________________________________________________

EXHIBIT 3-1 - SAMPLE LOCCS VRS GRANT DRAWDOWN

PHASE 2 DIALOGUE:  Entering a project number and amount.

2.a   Asking for a VRS Project Number.

PLEASE ENTER YOUR (1st, 2nd, 3rd, etc.) 10 DIGIT VOICE

RESPONSE PROJECT NUMBER.

if the project does not exist:

VOICE RESPONSE NUMBER (project number) DOES NOT EXIST.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if the caller is not authorized for the TAX ID associated with this

project:

YOU ARE NOT AUTHORIZED FOR DRAWDOWN ACTIVITY ON PROJECT.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if the project has not been verified:

PROJECT NUMBER HAS NOT BEEN VERIFIED BY HUD PERSONNEL, AND IS

NOT AVAILABLE FOR DRAWDOWN.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if the Contract Effective Date has not been reached:

PROJECT NUMBER (project number) CONTRACT IS NOT EFFECTIVE

UNTIL (effective date).  VOUCHERS WILL NOT BE ACCEPTED

BEFORE THIS DATE.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if some type of manual suspension has been placed on the project:

A MANUAL SUSPENSION HAS BEEN PLACED ON PROJECT NUMBER

(project number).  PLEASE CALL THE HUD PROGRAM OFFICE FOR

MORE INFORMATION.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if there is an outstanding voucher on the project:

VOUCHER NUMBER (xxxxxxxxx) CALLED IN ON (call-in date) FOR

PROJECT NUMBER (xxxxxxx) HAS NOT BEEN RECEIVED BY HUD.

NO DRAWDOWNS AGAINST THIS PROJECT WILL BE ALLOWED UNTIL

THIS VOUCHER HAS BEEN

July 22, 1992                     3-9

_____________________________________________________________________

RECEIVED AND APPROVED.  IF YOU HAVE MORE PROJECTS ON THIS

VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if a voucher has already been called in on this project today:

A VOUCHER HAS ALREADY BEEN CALLED IN ON PROJECT (xxxxxxx).

ONLY ONE REQUEST PER DAY PER PROJECT IS ALLOWED.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if the entered project number does not belong in the program area

selected from the menu:

PROJECT NUMBER (xxxxxxx) IS A (program area) PROGRAM PROJECT.

MULTIPLE PROGRAM AREAS ARE NOT ALLOWED ON A SINGLE VOUCHER.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if an entered project's Region and Field Office is different from

the Region and Field Office for projects previously entered on this

voucher:

A SINGLE VOUCHER MUST CONTAIN PROJECTS WITHIN THE SAME REGION

AND FIELD OFFICE.

THE FIRST PROJECT ON THIS VOUCHER IS IN THE (region) REGION,

(field office) FIELD OFFICE.  PROJECT NUMBER (entered project

number) IS IN (region) REGION, (field office) FIELD OFFICE.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

if there are no problems:

YOU ARE REQUESTING FUNDS FOR (recipient) ON PROJECT

(xxxxxxx).

*Note:  The name of the HUD recipient is only spoken when the

previous project entered on the voucher is associated with a

different recipient.

if a project auto review has been set:

AN AUTOMATIC REVIEW IS REQUIRED ON ALL VOUCHERS CALLED IN FOR

THIS PROJECT.  THIS VOUCHER WILL REQUIRE A (review office)

HUD REVIEW.

July 22, 1992                     3-10

_____________________________________________________________________

Continue with PHASE 2.b - Asking for the Amount.

2.b   Asking for the Amount.

VRS   requests

PLEASE ENTER THE AMOUNT OF FUNDS REQUESTED, FOLLOWED BY A

POUND SIGN.

A general Available Balance edit is performed.

If Available Balance on the project is zero:

FUNDS FOR THIS PROJECT ARE FULLY DISBURSED. IF YOU HAVE MORE

PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

For a failed Available Balance edit:

YOUR REQUESTED AMOUNT OF ($$$). EXCEEDS YOUR AVAILABLE

BALANCE FOR THIS PROJECT.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

2.c   Repeating the Amount Requested.

VRS   responds with

YOUR HAVE ENTERED A REQUEST FOR ($$$).  ENTRY ACCEPTED.

If there are any review edits, go to PHASE 3.d - Speaking Any Review Edits.

If there are no review edits, go to PHASE 3.e - Are There Any More Projects

on This Voucher.

July 22, 1992                     3-11

_____________________________________________________________________

2.d   Speaking Any Review Text.

if the requested amount exceeds a dollar threshold,

VRS   responds with

THIS REQUEST EXCEEDS A MAXIMUM PROJECT DOLLAR THRESHOLD.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

If the requested amount exceeds Project Percent of Authorized Amount

threshold:

THIS REQUEST EXCEEDS A MAXIMUM PROJECT DOLLAR THRESHOLD. THIS

VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

2.e   Are There Any More Projects on This Voucher.

VRS   responds with

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

IF YOU WOULD LIKE TO CANCEL THIS PROJECT REQUEST, PRESS 3.

If the response is "1", go to PHASE 2.a - Asking for a VRS Project

Number.

If the response is "2", go to PHASE 3 - Voucher Repeat.

If the response is "3",

VRS   response with

YOUR REQUEST FOR PROJECT NUMBER (xxxxxxx) HAS BEEN CANCELED.

IF YOU HAVE MORE PROJECTS ON THIS VOUCHER, PRESS 1.

IF THERE ARE NO MORE PROJECTS ON THIS VOUCHER, PRESS 2.

If the response is "1", go to PHASE 2.a - Asking for a VRS Project

Number.

If the response is "2", go to PHASE 3 - Voucher Repeat.

July 22, 1992                     3-12

_____________________________________________________________________

EXHIBIT 3-1 - SAMPLE LOCCS VRS GRANT DRAWDOWN

PHASE 3 DIALOGUE:  Voucher Repeat.

3.a   Voucher Repeat.

If no entries were accepted on this voucher,

VRS   responds with

NO ENTRIES WERE ACCEPTED ON THIS VOUCHER.

THIS VOUCHER MAY BE USED AGAIN.

Continue with PHASE 4.b - Asking For Another Voucher.

If entries were accepted, the following is repeated for all projects

entered.

YOU HAVE REQUESTED FUNDS FOR:

PROJECT NUMBER (project number 1) FOR (request $1)

PROJECT NUMBER (project number 2) FOR (request $2)

PROJECT NUMBER (project number 3) FOR (request $3)

.

.

etc.

FOR A VOUCHER TOTAL OF (total $$$).

If there are any Voucher-Level Reviews they are spoken here.

See PHASE 3.b - Voucher Level Review Text.

TO PROCESS VOUCHER, PRESS 1.

TO CANCEL VOUCHER, PRESS 2.

Go to PHASE 4 - Voucher Confirmation Text.

July 22, 1992                     3-13

_____________________________________________________________________

3.b   Voucher-Level Review Text.

If the voucher amount exceeds a Program Area Dollar threshold,

VRS   responds with

THIS VOUCHER EXCEEDS A MAXIMUM DOLLAR THRESHOLD ESTABLISHED

FOR THIS PROGRAM AREA.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

YOUR BALANCE-ON-HAND AMOUNT SEEMS A LITTLE HIGH.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

BASED UPON YOUR LAST 30 VOUCHER REQUESTS FOR THIS RECIPIENT,

THIS VOUCHER AMOUNT SEEMS A LITTLE HIGH.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

July 22, 1992                     3-14

_____________________________________________________________________

EXHIBIT 3-1 - SAMPLE LOCCS VRS GRANT DRAWDOWN

PHASE 4 DIALOGUE:  Voucher Confirmation Text.

4.a   Speaking the Confirmation Text.

If the caller selects "1" to Process the Voucher,

VRS   responds with

VOUCHER ENTRY CONFIRMED.

If this voucher required a review:

THIS VOUCHER WILL NOT BE PAID WITHOUT REVIEW AND APPROVAL BY

(review office) HUD PERSONNEL.  PLEASE CALL YOUR HUD OFFICE

TO ASSIST IN THIS REVIEW PROCESS.

If the caller selects "2" to Cancel the Voucher:

THIS VOUCHER HAS BEEN CANCELED.

THE VOUCHER NUMBER MAY BE USED AGAIN.

Continue with PHASE 4.b - Asking for Another Voucher.

4.b   Asking for Another Voucher.

TO ENTER ANOTHER VOUCHER, PRESS 1.

TO RETURN TO A MENU SELECTION, PRESS 2.

IF YOU ARE FINISHED, PRESS 3

If the response is "1", go to PHASE 1.a - Asking for a Voucher

Number.

If the response is "2", go to a Menu Selection.

If the response is "3",

VRS   responds

THANK YOU FOR USING HUD'S VOICE RESPONSE SYSTEM, PLEASE HANG

UP NOW. (click)

July 22, 1992                    3-15

_____________________________________________________________________

EXHIBIT 3-2 - Sample of a Budget Line Item Payment Voucher

__________________________________________________________________________

LOCCS / VRS

Sample

Payment Voucher

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

__________________________________________________________________________

August 18, 1992                   3-16

_____________________________________________________________________

EXHIBIT 3-2 - Instructions for the Preparation and Submission a Budget Line

Item Payment Voucher

Block 1:   Preprinted three (3) digit and six (6) digit system

generated, nine (9) digit all numeric voucher number.

The VRS simulated voice will speak the six digit

VOUCHER NUMBER to the caller.  The caller must enter

the six digit number in block 1.  The caller will be

required to enter the nine (9) digit number prior to

terminating the call.

Block 2:   This block contains a preprinted maximum 4-digit (xxxx)

alpha/numeric LOCCS program area identifier.

Block 3:   Enter the period covered by this request.

Block 4:

Block 5:   Enter the 10-digit VRS number of the first project/grant

for which funds are being requested.  The first five

digits of this number identify the grantee/recipient;

the second five identify the specific program/grant.

The first five digits should always be the same for a

grantee/recipient.  The second five digits should run

consecutively for succeeding projects/grants within the

program.

Block 6:   Enter the Grantee Organization's Name for the Tax

Identification Number entered on block 6a.

Block 6a:  Grantee Organization's Tax Identification Number (TIN)

is either the payee's social security number  nine (9)

digits number separated by two hyphens e.g. 000-00-0000

or the payee's employer identification number (EIN)

nine(9) digit number separated by one hyphen e.g.

00-0000000  in LOCCS-VRS.  It is the number recorded

on the SF-1199A as the Claim or Payroll ID Number on

the SF-1199A and in Block 4 of the HUD 27054, LOCCS

Voice Access Authorization Form.

Block 7:   Enter the Payee Organization's Tax Identification Number

if different than recipient entered on block 4.

Block 7a:  Enter the Payee Organization's Name if different than

recipient entered on block 4a above.

Block 8:   Enter the HUD grant/project number for the project.

This entry is for confirmation purposes only and will

not be entered into LOCCS-VRS through the touch-tone

pad.  Instead, when the VRS project/grant number is

keyed in, the VRS simulated voice will speak the HUD

project/grant number for the caller.

August 18, 1992                   3-17

_____________________________________________________________________

Block 9:   Line items 1 through 16 enter the amount requested for

the particular budget line/activity.  Dollars should be

entered to the left of the asterisk(*) and cents to the

right.

Voucher Total:  Enter the total amount requested in the lower right

hand corner of Block 9.

Block 11:  Enter the Name and phone number (including area code of

the person who completed this form).

Block 12:  Enter the authorizing signature and date of signature.

The authorizing signatory Block 12, can not be the same

person(s) designated in Block 3 of the HUD-27054, LOCCS

Voice Response System Access Authorization Form.

Block 13:  Enter the authorizing signature and date of signature.

The authorizing signatory Block 12, can not be the same

person(s) designated in Block 3 of the HUD-27054, LOCCS

Voice Response System Access Authorization Form.

July 22, 1992                     3-18

_____________________________________________________________________

DRAFT

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

The following example depicts a LOCCS VRS Budget Line Item (BLI) drawdown

dialogue for programs using a line item based voucher form HUD-50080-XXXX.

Standard VRS dialogue is shown in UPPERCASE ITALICIZED TEXT.  Variable

dialogue is shown in lowercase bold, italicized text, within parentheses

(e.g., date, project number).

The BLI Voucher drawdown process is divided into five main phases.  All of

the phases are processed only once with the exception of Phase 3:  Entering

a Budget Line Item Number and Amount.  PHASE 3 is repeated until all line

item requests for the voucher have been entered.

Below is an outline of the BLI Voucher Dialogue which is presented on the

following pages:

PHASE 1:   Asking For and Confirming Entry of a Voucher

Number.                                          Page 3-20

a.    Asking for a voucher number.

b.    Confirming entry of a voucher number.

PHASE 2:   Entering and Confirming a Project Number.        Page 3-22

a.    Asking for a VRS project number.

b.    Confirming entry of a project number.

PHASE 3:   Entering a Budget Line Item Number and Amount.   Page 3-24

a.    Asking for a BLI number.

b.    Asking for the line item amount.

c.    Repeating the amount requested.

d.    Speaking any review text.

e.    Asking if there are any more line items on

this voucher.

PHASE 4:   Repeat Line Item Entry.                          Page 3-27

a.    Repeating the project, all BLI's and amounts

entered, and the voucher total.

b.    Speaking any review text pertaining to the

entire voucher.

PHASE 5:   Voucher Confirmation.                            Page 3-29

a.    Quoting confirmation text.

b.    Asking for another voucher.

July 22, 1992                     3-19

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

PHASE 1 DIALOGUE:  Asking for and confirming entry of a voucher number.

1.a   Asking for a Voucher Number.

VRS   requests

PLEASE ENTER YOUR PRE-PRINTED 3 DIGIT VOUCHER PREFIX FROM

BOX 1 ON YOUR VOUCHER FORM.

if an incorrect amount of digits are entered:

THREE DIGITS WERE REQUESTED; LESS THAN 3 WERE ENTERED.

if the three digits do not correspond to the program area:

YOU HAVE AN INCORRECT VOUCHER FORM FOR THE (program name)

PROGRAM.

THE CORRECT VOUCHER FORM HAS THE LETTERS (xxxx) IN BOX 2.

TO ENTER ANOTHER VOUCHER, PRESS 1;  TO RETURN TO A MENU

SELECTION, PRESS 2; IF YOU ARE FINISHED, PRESS 3.

If there are no problems, go to PHASE 1.b - Confirming Entry of the Voucher

Number.

1.b   Confirming Entry of the Voucher Number.

VRS   responds

YOUR GENERATED VOUCHER NUMBER SUFFIX IS (6-digit number);

ENTER THIS NUMBER IN BLOCK 1 OF YOUR VOUCHER FORM.

TO HAVE THIS NUMBER REPEATED, PRESS 1;

TO CONTINUE, PRESS 2.

If the response is a "2" and a program area auto-review has been set,

VRS   responds with

AUTOMATIC (program area) REVIEW SET.

ALL VOUCHERS FOR THIS PROGRAM AREA REQUIRE REVIEW.

July 22, 1992                      3-20

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

VRS   requests

PLEASE ENTER YOUR ENTIRE 9 DIGIT VOUCHER NUMBER FROM YOUR

VOUCHER FORM.

User  enters the entire voucher number.

if the voucher number is entered incorrectly:

YOU HAVE ENTERED YOUR VOUCHER NUMBER INCORRECTLY, PLEASE

RE-ENTER YOUR 9 DIGIT VOUCHER NUMBER.

if the voucher number is entered incorrectly a second time:

YOU HAVE ENTERED YOUR VOUCHER NUMBER INCORRECTLY, TWICE.

If this occurs, the user is logged off the system.

When the voucher number is entered correctly, continue with PHASE 2,

Entering a VRS Project Number.

July 22, 1992                     3-21

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

PHASE 2 DIALOGUE:  Entering and confirming a project number.

2.a   Asking for a VRS Project Number.

PLEASE ENTER YOUR 10 DIGIT VOICE RESPONSE PROJECT NUMBER.

if the project does not exist:

VOICE RESPONSE NUMBER (project number) DOES NOT EXIST.

PLEASE ENTER YOUR 10 DIGIT VOICE RESPONSE PROJECT NUMBER.

if the caller is not authorized for the TAX ID associated with this

project:

YOU ARE NOT AUTHORIZED FOR DRAWDOWN ACTIVITY ON PROJECT

(project number).

PLEASE ENTER YOUR 10 DIGIT VOICE RESPONSE PROJECT NUMBER.

if the project has not been verified:

PROJECT (project number) HAS NOT BEEN VERIFIED BY HUD

PERSONNEL AND IS NOT AVAILABLE FOR DRAWDOWN.

TO ENTER ANOTHER VOUCHER, PRESS 1; TO RETURN TO A MENU

SELECTION, PRESS 2; IF YOU ARE FINISHED, PRESS 3.

if the Contract Effective Date has not been reached:

PROJECT (project number) CONTRACT IS NOT EFFECTIVE UNTIL

(effective date).

TO ENTER ANOTHER VOUCHER, PRESS 1; TO RETURN TO A MENU

SELECTION, PRESS 2; IF YOU ARE FINISHED, PRESS 3.

If a manual suspension has been placed on the project:

A MANUAL SUSPENSION HAS BEEN PLACED ON PROJECT NUMBER

(project number).  PLEASE CALL THE HUD FIELD OFFICE FOR

MORE INFORMATION.

TO ENTER ANOTHER VOUCHER, PRESS 1; TO RETURN TO A MENU

SELECTION, PRESS 2; IF YOU ARE FINISHED, PRESS 3.

if a voucher is out for review:

VOUCHER NUMBER (voucher number) IS OUT FOR REVIEW.  ANOTHER

VOUCHER REQUEST IS NOT ALLOWED.  TO ENTER ANOTHER VOUCHER,

PRESS 1; TO RETURN TO A MENU SELECTION, PRESS 2; IF YOU ARE

FINISHED, PRESS 3.

July 22, 1992                     3-22

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

if a voucher has already been called in on this project today:

A VOUCHER HAS ALREADY BEEN CALLED IN ON PROJECT

(project number).

ONLY ONE REQUEST PER DAY PER PROJECT IS ALLOWED.

TO ENTER ANOTHER VOUCHER, PRESS 1; TO RETURN TO A MENU

SELECTION, PRESS 2; IF YOU ARE FINISHED, PRESS 3.

if there are no problems and a project auto review has been set:

AUTOMATIC PROJECT REVIEW SET.

ALL VOUCHERS FOR THIS PROJECT REQUIRE REVIEW.

2b.   Confirming entry of a project number.

VRS   continues with:

YOU ARE REQUESTING FUNDS AGAINST PROJECT NUMBER (project

number) FOR (recipient).

Continue with PHASE 3, Entering a Budget Line Item Number and Amount.

July 22, 1992                       3-23

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

PHASE 3 DIALOGUE:  Entering a Budget Line Item Number and Amount.

Once the project number is confirmed, budget line item numbers can be

entered.

VRS   request:

PLEASE ENTER YOUR (1s, 2nd, 3rd etc.) 4 DIGIT LINE ITEM

NUMBER.

User  enters line item number.

if less than 4 digits are entered:

A LINE ITEM HAS 4 DIGITS, LESS THAN 4 WERE ENTERED.

PLEASE ENTER YOUR (1s, 2nd, 3rd etc.) 4 DIGIT LINE ITEM

NUMBER.

if funds were already requested for the designated line item:

FUNDS HAVE ALREADY BEEN REQUESTED FOR ITEM NUMBER (xxxx) ON

THIS VOUCHER.  PLEASE ENTER YOUR (1s, 2nd, 3rd etc.)

4 DIGIT LINE ITEM NUMBER.  IF THERE ARE NO MORE LINE ITEM

REQUESTS, PRESS 2, THEN THE POUND SIGN.

if the line item number is incorrect and does not correspond to the

program area:

LINE ITEM (xxxx) IS INVALID FOR (program area) PROGRAM.

PLEASE ENTER YOUR (1s, 2nd, 3rd etc.) 4 DIGIT LINE ITEM

CODE.  IF THERE ARE NO MORE LINE ITEM REQUESTS,

PRESS 2, THEN THE POUND SIGN.

if BLI first review flag is set to "Y"(es):

ALL INITIAL DRAWDOWNS FOR THIS LINE ITEM REQUIRE REVIEW.

if the funding was not spread for the project:

FUNDING HAS NOT BEEN SPREAD FOR PROJECT (project number).

if the line item has not been budgeted for the project:

ITEM NUMBER (xxxx) IS NOT BUDGETED FOR THIS PROJECT.

if all funds are used for a specific line item:

THERE ARE NO REMAINING FUNDS FOR ITEM NUMBER (xxxx).

July 22, 1992                    3-24

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

if BLI auto review has been set:

ALL REQUESTS FOR THIS LINE ITEM REQUIRE REVIEW.

If there are no problems, continue with PHASE 3.b - Asking for the Line

Item Amount.

3.b   Asking for the Line Item Amount.

VRS   requests

PLEASE ENTER AN AMOUNT FOR (line item title), FOLLOWED BY

A POUND SIGN.

if a zero dollar amount is entered:

A ZERO DOLLAR AMOUNT ENTRY IS NOT ALLOWED.

After a valid amount is entered, a general Available Balance edit is

performed.

if Available Balance on the project is zero:

FUNDS FOR THIS PROJECT ARE FULLY DISBURSED.

for a failed Available Balance edit:

YOUR REQUESTED AMOUNT OF ($$$) EXCEEDS YOUR AVAILABLE

BALANCE FOR THIS PROJECT.  THIS ENTRY WAS NOT ACCEPTED.

PLEASE ENTER YOUR (1s, 2nd, 3rd etc.) 4 DIGIT LINE ITEM

NUMBER.  IF THERE ARE NO MORE LINE ITEM REQUESTS,

PRESS 2, THEN THE POUND SIGN.

3.c   Repeating the Amount Requested.

VRS   responds with

YOU HAVE ENTERED A REQUEST FOR ($$$).  ENTRY ACCEPTED.

If there are any review edits, go to PHASE 3.d - Speaking Any Review Edits.

If there are no review edits, go to PHASE 3.e - Are There Any More Line

Items on This Voucher.

July 22, 1992                      3-25

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

3.d   Speaking Any Review Text.

If the requested amount exceeds a project dollar threshold,

VRS   responds with

THIS REQUEST HAS REACHED A MAXIMUM PROJECT DOLLAR THRESHOLD.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

If the requested amount exceeds Project Percent of Authorized Amount

threshold:

THIS REQUEST HAS REACHED A CUMULATIVE PERCENT THRESHOLD

ESTABLISHED FOR THIS PROJECT.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

3.e   Are There Any More Line Item on This Voucher.

VRS   responds with

PLEASE ENTER YOUR (2nd, 3rd, 4th etc.) 4 DIGIT LINE ITEM

CODE.  IF THERE ARE NO MORE LINE ITEM REQUESTS, PRESS 2,

THEN THE POUND SIGN.  TO CANCEL YOUR LAST LINE ITEM REQUEST,

PRESS 3, THEN THE POUND SIGN.

If the response if "2", go to PHASE 4 - Repeat Line Item Entry.

If the response is "3",

VRS   responds with

YOUR LAST LINE ITEM REQUEST OF ($$$) HAS BEEN CANCELED.

PLEASE ENTER YOUR (1st, 2nd, 3rd etc.) 4 DIGIT LINE ITEM

NUMBER.

IF THERE ARE NO MORE LINE ITEM REQUESTS, PRESS 2, THEN THE

POUND SIGN.

after 16 line items have been entered and accepted:

SIXTEEN LINE ITEM ENTRIES HAVE BEEN ACCEPTED;

TO CONTINUE, PRESS 2, THEN THE POUND SIGN.

TO CANCEL LAST LINE ITEM REQUEST, PRESS 3, THEN THE

POUND SIGN.

July 22, 1992                      3-26

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

PHASE 4 DIALOGUE:  Repeat Line Item Entry.

4.a   Repeat Line Items.

If no entries were accepted on this voucher,

VRS   responds with

NO LINE ITEMS WERE RECORDED ON THIS VOUCHER.

Continue with PHASE 5.b - Asking For Another Voucher.

If entries were accepted, the following is repeated for all budget line

item entered.

FOR PROJECT (project number) YOU HAVE REQUESTED FUNDS FOR:

LINE ITEM (item number 1) FOR (request $1)

LINE ITEM (item number 2) FOR (request $2)

LINE ITEM (item number 3) FOR (request $3)

.

.

etc.

FOR A VOUCHER TOTAL OF (total $$$).

If there are any Voucher-Level Reviews they are spoken here.

See PHASE 5.b - Voucher Level Review Text.

TO PROCESS VOUCHER, PRESS 1.

TO CANCEL VOUCHER, PRESS 2.

Go to PHASE 5 - Voucher Confirmation Text.

July 22, 1992                      3-27

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

4.b   Voucher-Level Review Text.

If the voucher amount exceeds a Program Area Dollar threshold,

VRS   responds with

THIS VOUCHER HAS REACHED A MAXIMUM DOLLAR THRESHOLD

ESTABLISHED FOR THIS PROGRAM AREA.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

CUMULATIVE PROJECT DISBURSEMENTS HAVE REACHED A REVIEW

THRESHOLD ESTABLISHED FOR THIS PROGRAM AREA.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

THIS REQUEST HAS REACHED A ONE MONTH REVIEW THRESHOLD

ESTABLISHED FOR THIS PROGRAM AREA.

THIS VOUCHER WILL REQUIRE A (review office) HUD REVIEW.

July 22, 1992                      3-28

_____________________________________________________________________

EXHIBIT 3-2  SAMPLE LOCCS VRS BUDGET LINE ITEM DRAWDOWN

PHASE 5 DIALOGUE:  Voucher Confirmation Text.

5.a   Speaking the Confirmation Text.

If the caller selects "1" to Process the Voucher,

VRS   responds with

VOUCHER ENTRY CONFIRMED.

If this voucher required a review:

THIS VOUCHER WILL NOT BE PAID WITHOUT REVIEW AND APPROVAL BY

(review office) HUD PERSONNEL.  PLEASE CALL YOUR HUD OFFICE

TO ASSIST IN THIS REVIEW PROCESS.

If the caller selects "2" to Cancel the Voucher:

THIS VOUCHER HAS BEEN CANCELED.

Continue with PHASE 4.b - Asking for Another Voucher.

5.b   Asking for Another Voucher.

TO ENTER ANOTHER VOUCHER, PRESS 1.

TO RETURN TO A MENU SELECTION, PRESS 2.

IF YOU ARE FINISHED, PRESS 3.

If the response is "1", go to PHASE 1.a - Asking for a Voucher

Number.

If the response is "2", go to a Menu Selection.

If the response is "3",

VRS   responds

THANK YOU FOR USING HUD'S VOICE RESPONSE SYSTEM, PLEASE

HANG UP NOW. (click)

July 22, 1992                      3-29

_____________________________________________________________________

SECTION 4.  RETURN OF FUNDS - WIRE TRANSFER PROCEDURES

The grantees/recipients are required to utilize the Treasury Financial

Communications System (TFCS) to return funds in excess of $2,000 to HUD

and the Department of Treasury.  In order for funds and deposit messages

to be routed efficiently, all wire transfer messages must be sent to

conform with the structured Third Party format described below; otherwise,

the message will be rejected.

It is very important to contact the HUD Program Office before returning

any funds.  The HUD staff will confirm whether funds should be returned

and whether the grantee/recipient has proper wire instructions to give to

its bank.

All funds are returned through the grantee/recipient designated depository.

This bank must be able to participate in the TFCS.  If the bank is not a

member of the TFCS, it must have a correspondent bank relationship with a

member bank.

The correspondent bank must then forward the necessary information to the

member bank and the member bank will do the actual wire to Treasury.

An example of the required funds transfer message information is as

follows:

(1)     TREASURY DEPARTMENT CODE:  021030004

(2)     AMOUNT:  $25,000.00

(3)     TREASURY DEPT NAME,

(4)     PRODUCT CODE,

(5)     BENEFICIARY CODE,

(6)     IDENTIFIED CODE,

(7)     AGENCY LOCATION CODE

NOTE:  This will vary from one Region to another and should

be provided by HUD.

(3)  (4) (5) (6) (7)

e.g.    TRES NYC/CTR/BNF=HUDSFCA/AC-86011201

OBI=

(8)     * THIRD PARTY INFORMATION:  DRUG EXCESS DRAWDOWN GRANT

B87MC060007 S.F.CA

ACCT 860162 $23,000 ACC 861435

$2,000.00

*  The THIRD PARTY INFORMATION should begin immediately after "OBI=."

There is no slash between OBI and the THIRD PARTY INFORMATION.

July 22, 1992                      4-1

* U.S. G.P.O.: 1993-342-362:80013