U.S. Department of Housing and Urban Development

H O U S I N G

_______________________________________________________________________

Special Attention of:                    Notice   H 93-46 (HUD)

All Regional Administrators,

Directors, Office of Regional              Issued:  7/1/93

Housing; Managers, Category A              Expires: 7/31/94

and Category B Offices; and                _______________________________

Field Office Housing Development           Cross References:

Division Directors, Category A

Category B Offices                         Handbook 4571.2 Disabled

Notice HUD 93-45

_______________________________________________________________________

Subject:     Revised Fiscal Year 1993 Policy for Section 811

Application Processing and Selections, Revised

Processing Schedule

1.   PURPOSE.

This Notice provides a revised processing schedule for

Section 202 and 811 applications (Attachment 1),

Congressional Notification Memorandum Format (Attachment 2),

and instructions to Regional and Field Offices regarding the

elimination of Headquarters role in the selection process of

Fiscal Year 1993 Section 811 applications.  This action is

necessary to adhere to the Department's goal of announcing

selections by September 30, 1993.  Headquarters will conduct

a post-audit evaluation of Regional Office funding decisions

in early Fiscal Year 1994 before deciding whether or not to

make these revised procedures permanent.  This Notice should

be used in conjunction with the Interim Rule (Part 890) as

revised May 5, 1993 at 58 Federal Register 26816.  The 1993

Notice of Fund Availability (published May 5, 1993) at 58

Federal Register 26824, and Handbook 4571.2 Section 811

Supportive Housing for Persons with Disabilities.

In addition, this Notice waives and or modifies the

following paragraphs of Handbook 4571.2: 1-12, 3-6, 3-7,

3-8, 3-14, 3-52, 3-56, 3-57, 3-58, 3-60, and 3-62.  The

modifications and waivers are detailed in this Notice.

2.   GENERAL OVERVIEW:

The modifications outlined in this Notice eliminate the need

for rating and technical review documents being forwarded to

Headquarters for review and ultimate final selection of

applications.

___________________________________________________________________________

HMEE : Distribution: W-3-1, W-2(H),W-3(H)(FHEO)(ZAS)(OGC)(PD&R), R-1, R-2,

R-3, R-3-1, R-3-3, R-6, R-6-1, R-6-2, R-7, R-7-1,

R-7-2, W-4(H), R-3-1(H)(RC), R-8, R-8-1

Previous Editions Are Obsolete                               HUD 21B(3-80)

GPO 871 902

_____________________________________________________________________

2

Selection lists and lists of unfunded but approvable

applications will not come to Headquarters prior to

completion of the selection and announcement process.

Regional Offices shall submit to Headquarters one final

selection list.

The responsibility for coordinating Congressional

notification of selected applicants with the Office of

Congressional and Intergovernmental Affairs has been

transferred from Headquarters to the Regional Offices.  See

Attachment 2 for current Congressional notification

memorandum format.  A completed sample notification is also

included in Attachment 2.

Responsibility for notification to State Point of Contact of

nonaccomodation has been transferred from Headquarters to

the Regional Offices.

3.   SPECIFIC PARAGRAPHS OF HANDBOOK 4571.2 WHICH ARE BEING

WAIVED TO ACHIEVE THE ABOVE ARE:

1-12. A. 5.  Delete "and submit selection recommendations to

Headquarters".  Substitute "Regional offices are responsible

for funding selections."

1-12. A. 6.  Delete Paragraph

3-6.  Delete Paragraph.

3-7.  Delete Paragraph.

3-8. C.  Delete "recommended to Headquarters".  Substitute

"considered".

3-8. E.  Delete Paragraph.  Substitute "If there are adverse

comments on applications:".

3-8. E.1.  Delete "and attach a copy of the comments".

3-8. E.2.  Delete "Headquarters".  Substitute, "Regional

Office".

3-14.  Delete "and a copy of the notification shall be

mailed to the Housing for Elderly and Handicapped People

Division in Headquarters".

_____________________________________________________________________

3

3-52.  Delete Paragraph.

3-56. B. 3d.  Delete Paragraph.

3-56. C.  Delete Paragraph.

3-56. E.  Delete Paragraph.  Substitute, "If the Regional

Office review reveals that a Field Office has violated or is

inconsistent with any outstanding instructions, the Regional

Office shall take corrective action prior to final

selections.  Such items should be noted and maintained in

the application file."

3-57. A.  Delete Paragraph.  Substitute, "Regional Offices

shall submit to Headquarters one final selection list with

transmittal memorandum in accordance with the revised

schedule found as Attachment 1 of this Notice.  Offices

shall use the data diskette provided by Headquarters.  The

list shall include final selections in rank order for

Category A and Category B.  The transmittal memorandum shall

identify any unused funds for recapture by Headquarters.

NOTE:  In no case may projects with technical deficiencies

(such as unacceptable service plan description, ineligible

Sponsor, etc.) be considered by Field or Regional Office

panels for selection."

3-57. B.  Delete "Regional Office must submit to

Headquarters".  Substitute, "the Regional Office shall

maintain the following in the application file for post

audit review".

3-57. C.  Delete Paragraph.

3-57. D.  Delete Paragraph.  Substitute, " Any outstanding

State comments (EO 12372) not to be accommodated and/or

local adverse comments on any application on the final

selection list must be noted and maintained in the

application file for post audit review."

3-57. E.  Delete Paragraph.

3-57. F.  Delete Paragraph.

3-58. A.  Delete Paragraph.  This Paragraph is waived for

the selection process only.  These functions will be

evaluated at the post audit review.

_____________________________________________________________________

4

3-58. B.  Delete Paragraph.

3-58. C.  Delete Paragraph.

3-60. A. 1.  Delete "The Office of Elderly and Assisted

Housing"  Substitute, "Regional and Field Offices".  See

Attachment 2 for current memorandum format.

3-60. B.  Delete Paragraph.

3-62.  Delete "NOTE:"  Substitute, "NOTE:  Nonselection

letters may be released following notification to selected

applicants".

_____________________________________

Assistant Secretary for Housing

- Federal Housing Commissioner

_____________________________________________________________________

5

Attachment 1

202/811 REVISED APPLICATION PROCESSING SCHEDULE

7/8/93    APPLICATION DEADLINE DATE

7/16/93   INITIAL SCREENING COMPLETED AND DEFICIENCY LETTERS

MAILED TO SPONSORS

7/30/93   EXPIRATION OF 14 DAY PERIOD FOR SUBMISSION OF MISSING

APPLICATION ITEMS

8/20/93   COMPLETION OF TECHNICAL PROCESSING AND OF SPONSOR

NOTIFICATION OF TECHNICAL REJECTS

9/3/93    END OF 14 DAY APPEAL PERIOD FOR TECHNICAL REJECTS

9/7/93    CONVENE FIELD OFFICE RATING PANELS

9/10/93   FIELD OFFICES SEND LISTS OF SELECTIONS AND OTHER

APPROVABLE APPLICATIONS TO THE REGIONAL OFFICES

9/17/93   REGIONAL OFFICES COMPLETE FUNDING SELECTIONS AND

INITIATE FUND RESERVATION ACTIONS.  FINAL SELECTION

DATA DISKETTE AND TRANSMITTAL MEMORANDUM SUBMITTED

TO HEADQUARTERS

9/20/93   REGIONAL OFFICES SUBMIT CONGRESSIONAL NOTIFICATION

MEMORANDUM TO OFFICE OF CONGRESSIONAL AND

INTERGOVERNMENTAL AFFAIRS, HEADQUARTERS

9/30/93   FUNDING ANNOUNCEMENTS COMPLETED

_____________________________________________________________________

6

ATTACHMENT 2

DATE:

MEMORANDUM FOR:  Deputy Assistant Secretary for Congressional

Relations, LC

FROM:

ACTION:

DEADLINE/SPECIAL CIRCUMSTANCES:

PROJECT DESCRIPTION:

PROJECT HIGHLIGHTS:

STATUS:

GRANTEE CONTACT (name/telephone):

CONGRESSIONAL DELEGATION:

SUMMARY OF NOTIFICATION ACTION:

Congressional Call Completed to: _____________________________________

Date: ____________________________

Press Release Needed:    Yes _______    No _______

HUD Regional or Field Contact (name/telephone):

_____________________________________________________________________

7

ATTACHMENT 2

(SAMPLE)

DATE:  January 29, 1993

MEMORANDUM FOR:  Deputy Assistant Secretary for Congressional

Relations, LC

FROM:  Acting Deputy Assistant Secretary for Grant Programs, CG

ACTION:  Project Approval (Number B-93-MC-42-0017)

DEADLINE/SPECIAL CIRCUMSTANCES:

PROJECT DESCRIPTION:

A Community Development Block Grant Entitlement for Fiscal

Year 1993 in the amount of $1,513,000 for Williamsport, PA.

PROJECT HIGHLIGHTS:

The City's Fiscal Year 1993 Community Development Block

Grant Program includes activities such as:  street resurfacing

and reconstruction, housing rehabilitation, public facilities and

improvements, and public services, all of which are designed to

benefit low/moderate income persons.

STATUS:

All administrative, regulatory and statutory requirements

have been met.

GRANTEE CONTACT (name/telephone):

CONGRESSIONAL DELEGATION

Senator Harris L. Wofford, Jr. (D); Senator Arlem Spector

(R); Congressman Joseph M. McDade (R).

SUMMARY OF NOTIFICATION ACTION:

Congressional Call Completed to: _____________________________________

Date: __________________________

Press Release Needed:    Yes _______    No _______

HUD Regional or Field Contact (name/telephone):