U. S. Department of Housing and Urban Development

Office of Public and Indian Housing

Special Attention of:

Notice: PIH 96-91 (IHA)

ONAP Administrators;

Facilities Planning                  				Issued: December 10, l996

& Development Directors; Finance &   		Expires: December 31, l997

Budget Directors; and Indian

Housing Authorities (IHAs)           			Cross Reference: 24 CFR Part 950

Subject: Closeout of Indian Housing Development Projects

1. Purpose: This Notice provides policies and procedures on the

closeout of Indian Housing Development projects. These policies

and procedures address reopened projects, reformulation, and

overdue Actual Development Cost Certificates (ADCCs).

2. Background: In anticipation of the programmatic changes which will

occur with the implementation of the Native American Housing

Assistance and Self-Determination Act of 1996, it is important

that the project accounting records for Indian Housing Development

projects be as complete as possible. To that end this Notice

stresses the importance of closing out projects and issuing Actual

Development Cost Certificates.

In past years, Congress appropriated funds to amend the Annual

Contributions Contract (ACC) of individual Indian Housing development

projects. In the process of expending these funds, projects with

previously approved ADCCs were reopened so that design deficiencies

could be addressed. In some cases, projects with ADCCs issued prior

to October 1, 1988, were reopened to expend funds presumed to be

remaining under the ACC. Now, with the elimination of new

appropriations for amendment funds and the recapture of funds

reserved for a project which exceed the ADCC amount, there is no

reason to reopen projects with approved ADCCs.

Guidance is also being provided for the reformulation of projects

previously included in the Indian Housing Development Handbook,

7450.1 REV-1, CHG-1, which was cancelled on January 23, 1995.

The area Offices of Native American Programs (ONAPs) have a backlog

of projects with overdue ADCCs. Guidance is being provided on the

timely closeout of these projects. The provisions for noncompliance

with ADCC procedures as specified at 24 CFR 950.285 are reiterated to

highlight the options available to the area ONAPs to force the

closeout of overdue projects. Housingauthorities with overdue ADCCs

will have a six month window of opportunity so that funds remaining

in the projects may be expended. Six months after issuance of this

Notice any project with an overdue ADCC will not be eligible to

expend any remaining funds and area ONAP offices will not have the

authority to approve transfers of funds or reformulations.

:       Distribution:   W-3-1, HUD 21B(3- 80)

Previous Editions Are Obsolete

GPO 871 902 3

3. Applicability: All active Indian Housing projects shall be covered

by the provisions of this Notice.

4. Reopening Projects: Projects with approved ADCCs may no longer be

reopened.

a. Amendment Funds - Any project which needs rehabilitation or

correction of design deficiencies must use the Comprehensive

Improvement Assistance or Comprehensive Grant programs since

amendment funds are no longer available.

b. Projects with ADCCs approved on or before September 30, 1988 -

Based on the provisions of debt forgiveness which became

effective October 1, 1986, execution of an ADCC also revised

the ACC causing recapture of any remaining funds. Through an

agreement reached with the Office of Finance and Accounting,

exceptions to this ruling were approved through September 30,

1988. These actions allowed projects with ADCCs approved on or

before September 30, 1988, to be reopened to expend funds up to

the previous amount approved under the ACC. As of the date of

this Notice, projects with ADCCs approved on or before

September 30, 1988, may no longer be reopened. Any funds

originally reserved for these projects have been recaptured.

c. Corrections - The only circumstance where an original ADCC

should be revised is to correct an error in the calculation of

the ADCC. Approval from Headquarters must be obtained prior to

correcting an ADCC to ensure that any additional funds needed

will be available.

5. Reformulation:

a. Reformulation is defined as dividing a project into two or more

projects or combining two or more projects into one project, or

transferring funds from project to another.

b. Reformulation is intended to provide housing authorities with

the flexibility to adapt to site availability and/or other

problems, simplify the housing authority's accounting of

development funds, and to utilize housing funds to the maximum

extent feasible.

c. Policies and procedures for requesting and processing

reformulations.

1. Reformulated projects use the reservation date of the

original project. If projects with different reservation

dates are combined, the oldest reservation date should be

used.

2. Development costs incurred at the time of reformulation

should be charged to the project associated with the costs.

Development costs which are not clearly identifiable with

one project (e.g., non-technical salaries) should be

allocated as fairly as possible (e.g., per unit basis).

3. Reformulation requests must be submitted to the area ONAP

not later than 12 months after the Date of Full Availability

(DOFA) (defined at 24 CFR 950.270(c)(1)) or within 6 months

of the date of this Notice, whichever is later.

4. An originating project must have a minimum of $25,000

available for reformation.

5. Funds for reformulation may not include amounts which must

be set aside to cover DOFA interest expense.

6. Reformulation requests must include the following

documentation:

a) A description of and the reason(s) for the proposed

reformulation.

b) Revised Development Cost Budgets, form HUD-53045-A, or

HUD-52484, for the projects to be reformulated.

c) A certification that the Board of Commissioners has

approved the reformulation request.

7. The area ONAP will review the request, and if all required

documentation is submitted and the request meets the

requirements of this Notice, the request will be approved by

the area ONAP, Director of Facilities, Planning, and

Development.

8. The area ONAP will forward to the housing authority any

necessary amendments to ACCs for execution by the Board of

Commissioners.

9. The area ONAP will execute the appropriate Project

Accounting Data, forms HUD-52540, and ACCs and forward these

documents to the Field Accounting Division for processing.

6. Overdue ADCCs: In order to alleviate the backlog of projects with

overdue ADCCs, the following guidelines and procedures have been

established.

a. Housing authorities that have not submitted to the area ONAP an

Actual Development Cost Certificate, form HUD-52427, within 24

months of DOFA should take the following actions:

1. Immediately expend remaining funds on allowable expenses of

the development project and submit the Actual Development

Cost Certificate, form HUD-52427, and final Statement of

Actual Development Cost, form HUD-53045-A, or HUD-52484, to

the area ONAP.

2. Use the provisions of Notice 96-56 to expend funds in excess

of $5,000 for modernization or operations. The funds should

be obligated and drawn down and the Actual Development Cost

Certificate, form HUD-52427, and final Statement of Actual

Development Cost, form HUD-53045-A, or HUD-52484, submitted

to the area ONAP within 6 months from the date of issuance

of this Notice.

3. Use the provisions of this Notice to reformulate funds in

excess of $25,000. The reformulation process must be

complete and the Actual Development Cost Certificate, form

HUD-52427, and final Statement of Actual Development Cost,

form HUD-53045-A, or HUD-52484, submitted to the area ONAP

within 6 months from the date of issuance of this Notice.

b. The area ONAP will execute an Actual Development Cost

Certificate, form HUD-52427, in accordance with 24 CFR 950.285:

1. This will occur when the housing authority has not submitted

to the area ONAP an Actual Development Cost Certificate,

form HUD-52427, within 24 months of DOFA and, according to

the latest Semi-annual Development Cost Statement, form HUD-

43045-A, or HUD-52484, has expended funds to within $4,999

of the amount(s) reserved. Housing authorities will be

notified by the area ONAP that all development activities

have been completed and that no additional costs may be

incurred for the project. The area ONAP will then proceed

with fiscal close-out of the project.

2. Immediately following the six month window of opportunity

allowed by this Notice, housing authorities with overdue

Actual Development Cost Certificates, form HUD-52427, will

be notified by the area ONAP that all development activities

have been completed and that no additional costs may be

incurred for the project. The area ONAP will then proceed

with fiscal close-out of the project.

c. Each area ONAP will provide a listing of projects with overdue

ADCCs to Headquarters, along with a schedule for eliminating

the backlog by September 30, 1997. The listing should also

include projects which have been reopened and must be closed

again. A reporting format will be provided under separate

cover.

7. Routine Processing of ADCCs:

a. Projects which reach DOFA after the issuance of this Notice

must comply with the following schedule:

1. Reformulation requests must be submitted by to the area ONAP

not later than 12 months after DOFA.

2. The housing authority must submit to the area ONAP a

Certificate of Actual Development Cost, form HUD-52427,

within 24 months of DOFA.

3. Audit verification of the actual development cost must be

submitted to the area ONAP within 36 months of DOFA.

b. If the housing authority fails to submit a Certificate of

Actual Development Cost, form HUD-52427, or audit within the

timeframes prescribed in item 7a above:

1. The area ONAP will make a determination that all development

activities have been completed and inform the housing

authority that such action has been taken and that no

additional costs may be incurred for the development.

2. The area ONAP will then proceed with the fiscal close-out of

the development.

Kevin Emanuel Marchman,

Acting Assistant Secretary