U.S. Department of Housing and Urban Development

Community Planning and Development

Special Attention of:

Notice:  CPD 97-13

All Secretary's Representatives

All State Coordinators              Issued:  November 19, 1997

All CPD Division Directors         Expires:  November 19, 1998

All HOPE 3 Program Grantees

Cross Reference:

SUBJECT:  HOPE 3 Program - Procedures for Closing Out HOPE 3

Program Implementation Grants

I.   Introduction

The purpose of this notice is to provide instructions for closing

out Homeownership for People Everywhere (HOPE 3) Program

Implementation Grants authorized by the National Affordable

Housing Act of 1990, as amended by the Housing and Community

Development Act of 1992.  The HOPE 3 Program regulations provide,

at 24 CFR  572.210(g), that recipients will comply with closeout

procedures as issued by HUD.  Closeout of HOPE 3 Implementation

Grants will provide a systematic process of veryifying that major

program requirements have been met as specified in the program

regulations at 24 CFR Part 572.  These procedures apply to grants

where the grantee has provided at least 70 percent of the

homeownership opportunities in the HUD-approved application for

the HOPE 3 Implementation Grant or the number of homeownership

opportunities subsequently approved in an amendment to the

application.  Grants not meeting this criterion will be closed on

a case-by-case basis with the assistance of Headquarters, Office

of Affordable Housing staff.

II.     Grant Closeout Procedures

A.   Criteria for Closeout.  A HOPE 3 Implementation Grant will

be closed out when HUD determines, in conjunction with the

grantee, that the following criteria have been met:

CGHP:  Distribution: W-3-1, W-2,

(1)  Property Transfer and Project Completion Reports for

all properties utilizing grant or match funds from the

grant to be closed out have been submitted and entered

in the HOPE 3 Program's Cash and Management Information

(C/MI) System, and discrepancies in C/MI System data,

if any,  have been resolved.

(2)  With respect to rehabilitation activities, the work to

be assisted with HOPE 3 grant or match funds, or

contributed as match, has actually been accomplished

and the properties have been transferred to homebuyers.

(NOTE:  Where the homebuyer or another party remains

responsible to complete some required rehabilitation

with non-HOPE 3 funds, the grant may be closed out,

although the grantee must monitor completion of such

work.)

(3)  Other activities of the grantee under the grant

agreement and applicable laws and regulations have been

carried out satisfactorily, or, the grantee is in

compliance with any corrective and remedial actions

imposed by the Field Office as specified in 24 CFR

572.225.

(4)  All costs, except those related to closeout costs,

contingent liabilities or replacement reserves as

specified in the closeout letter, to be paid with HOPE

3 grant and match funds have been paid and any other

necessary matching contributions have been provided.

(5)  A final grant amount has been determined by HUD after

any adjustment for unallowable costs, and any amount of

previously disbursed HOPE 3 funds found not allowable

has been returned to HUD by the grantee.

B.   Closeout Action.

(1)  When it is determined that the criteria for closeout

have been met, the Field Office shall request a final

Annual Performance Report from the grantee.  The final

APR shall include an accounting of all sale and resale

proceeds and program income earned and expended during

the grant period.  The accounting of resale proceeds

shall include proceeds returned to HUD as well as

proceeds retained by the grantee.  Grantees must submit

the final APR within 90 days of the Field Office

request.

(2)  Based on the information provided in the performance

report and other relevant information (such as

information contained in the Program's Cash and

Management Information System), the Field Office, in

consultation with the grantee, will prepare a letter agreement

for closeout in accordance with paragraph (C) of this

section.  See Attachment A for a Model Letter Agreement

for Closeout.

(3)  After receipt of the letter agreement executed by the

grantee, HUD will cancel any unallowable portion of the

awarded grant, determined under Paragraph II. A.  Any

unexpended grant funds disbursed from the U.S. Treasury

which are in the possession of the grantee, except for

costs identified in Paragraph C. 1. below,  shall be

refunded to HUD.  (See Section V. of this Notice.)

(4)  Any funds paid with HOPE 3 Implementation Grant funds

which have not been audited shall be subject to

coverage in the grantee's next single audit performed

in accordance with 24 CFR Part 44.  The grantee may be

required to repay HUD any disallowed costs based on the

results of the audit.

C.   Letter Agreement for Closeout.

Any obligations remaining as of the date of closeout shall

be covered by the terms of the closeout agreement.  See

Attachment A for a model closeout letter agreement.  A HOPE

3 grant shall not be closed out subject to conditions other

than those provided for in the attached model letter

agreement.  The letter agreement shall be prepared by the

HUD Field Office in consultation with the grantee.  The

Field Office shall prepare an original and three copies of

the letter agreement.  Upon execution of the letter

agreement by the CPD Field Office Director, the agreement

shall be forwared to the grantee.  When the terms of the

agreement are accepted by the grantee, the original and two

copies of the agreement executed by the grantee must be

submitted to the Field Office within 30 days of the date of

execution by the CPD Field Office Director.  If the

agreement is not executed and returned to the Field Office

within 30 days, the Field Office and grantee may need to

renegotiate the terms of the agreement, since the program

income, sales proceeds and resales proceeds figures may be

out of date.  See Paragraph III below for instructions on

distribution of the executed closeout letter.  As shown in

the attached model, the closeout letter agreement shall

identify the grant being closed out, and include provisions

with respect to the following:

(1)  Identification of any closeout costs, contingent

liabilities or replacement reserves,  subject to

payment with HOPE 3 grant funds after the closeout

agreement is signed;

(2)  Identification of any grant funds to be canceled by

HUD.

(3)  Identification of any sale or resale proceeds, and,

where applicable, program income in the possession of

the grantee at the time the closeout agreement is

signed;

(4)  Description of the grantee's responsibility after

closeout for compliance with all program requirements,

certifications and assurances in using sale or resale

proceeds or program income on deposit at the time the

closeout agreement is signed and in using any other

remaining HOPE 3 funds available for closeout costs and

contingent liabilities.  HOPE 3 sales proceeds and

program income on hand at time of closeout must be used

for costs eligible under 24 CFR 572.135(a) and (c)

(sales proceeds) and (d) (program income).  HOPE 3 sale

or resale proceeds and program income received after

closeout may be used for the activities described in 24

CFR 572.135, may be contributed to the HOME Investment

Partnerships Program (HOME) as a cash matching

contribution in accordance with the applicable HOME

program rules, or may be used for other affordable

housing activities approved by HUD and specified in the

closeout agreement.  N0TE: 50 percent of net resale

proceeds must continue to be returned to HUD.

(5)  The agreement shall authorize monitoring by HUD, and

shall provide that findings of noncompliance may be

taken into account by HUD, as unsatisfactory

performance of the grantee, in the consideration of any

future grant awards.

D.   Termination of Grant

Grant assistance provided under 24 CFR 572 may be terminated

in whole or in part before the completion of the assisted

activities, in accordance with the provisions of 24 CFR Part

84 or Part 85, as applicable.

The

new obligations for the terminated portions after the

effective date, and shall cancel as many outstanding

obligations as possible.  HUD may allow full credit to the

grantee for those portions of the obligations which could

not be canceled and which had been properly incurred by the

grantee in carrying out the activities before the

termination.   Proposals to terminate grants must be

reviewed and approved by the Office of Affordable Housing

Programs.   At a minimum, grant termination proposals

forwarded to Headquarters for review should include a

summary of the activities approved in the application, the

status of the grant, including units acquired and

transferred, match contributed, the reason(s) for the

termination, etc., and the Field Office's recommendation for

actions to be undertaken by the grantee to terminate the

grant.

III.    Distribution of Grant Closeout Documents

Upon receipt of the original and two copies of the executed

agreement from the grantee, the Field Office shall retain

the original copy as the Field Office official file copy,

forward one copy of the closeout agreement to the Field

Accounting Division (FAD) and a copy to the Office of

Affordable Housing Programs, CPD, 451 7th Street, S.W., Room

7158, Washington, DC 20410, Attention HOPE 3 Program.  In

instances where HUD must cancel any undisbursed portion of

the awarded grant (see paragraph II. B. (3) above), Field

Offices must include a request to recapture the undisbursed

funds with the FAD's copy of the Closeout Agreement.

IV.  Recordkeeping Responsibilities

The Field Office will keep all records concerning HOPE 3

Program grants for three  years from the date of closeout.

Each grantee shall retain records that clearly document its

performance for a period of three years from the date of

closeout of the HOPE 3 Implementation Program Grant.

Records with respect to sale and resale proceeds shall be

maintained for as long as such proceeds are received and

shall be retained for 3 years after the final proceeds have

been received.  The date of closeout is the date the

closeout agreement is executed by the Field Office CPD

Director.

V.   Procedures for Returning Resale Proceeds and Other Funds to

HUD for Remittance to the U.S. Treasury

A.   Remitting Funds in Amounts Less Than $2,000.  Funds being

remitted that are in amounts less than $2,000 may be

returned using the Department of Treasury Financial

Communications System (TFCS) described in this section or by

sending a check payable to the Department of Housing and

Urban Development.  If funds are being remitted by check,

recipients should send the check to the appropriate HUD

Field Accounting Division (FAD) at the address shown in

Attachment B.  The recipient should indicate the grant

number, tax identification number, and property number, if

applicable, on the check and include the following

information in a cover letter accompanying the check:

(1)  Grantee Name

(2)  A statement that the funds are being remitted for the

HOPE 3 Program

(3)  HOPE 3 grant number

(4)  Tax Identification Number (TIN)

(5)  Explanation of remittance, e.g., net resale proceeds,

disalllowed costs, etc.

A copy of the letter should be sent to: HOPE 3 Program, P.O.

Box 23997, L'Enfant Plaza Station, Washington, DC  20026.

B.   Remitting funds in amounts greater than $2,000.  Funds being

remitted in the amount of $2,000 or greater should be wired

to the U.S. Department of Treasury Financial Communications

System (TFCS).  In order for funds and deposit messages to

be routed efficiently, all wire transfer messages must

conform to the sturctured format described below:

(1)  ABA Number 021030004

(2)  Receiver Information:  TREAS NYC/CTR/BNF=/AC-(select

appropriate HUD agency location code from

Attachment A)

(3)  Third Party Information:  HOPE 3 PROGRAM (Name of Recipient)

Recipient Grant Number, Recipient Tax

Identification Number

(4)  Explanation, e.g., net resale proceeds, disallowed costs, etc.

(5)  ATTN: HOPE 3-CPD

All wire transfers must be remitted through the HOPE 3

recipient's local financial institution.  If the local

financial institution is not a member of the TFCS, it must

have a correspondent bank relationship with a member bank

that will actually make the wire transfer to Treasury.

ATTACHMENT A

HOPE FOR HOMEOWNERSHIP OF SINGLE FAMILY HOMES PROGRAM

(HOPE 3)

IMPLEMENTATION GRANT

MODEL LETTER AGREEMENT FOR CLOSEOUT

[Date of Letter - date

signed by HUD]

[Authorized Official of Grantee

Name of Grantee

Address of Grantee]

RE:  Letter Agreement for Closeout of HOPE 3

Implementation Grant No.

______________________________.

Dear [Name of Authorized Official of Grantee]:

The purpose of this letter is to set forth the terms and

conditions under which HUD will close out the above referenced

grant.  This letter is prepared pursuant to HUD Notice          ,

HOPE 3 Program - Procedures for Closing Out HOPE 3 Program

Implementation Grants, which is referred to in this letter as the

"Closeout Notice."

A.  The originally approved HOPE 3 grant amount for this

grant was             .   Of that amount, HUD has determined

pursuant to 24 CFR Part 572 and Paragraph 2.A. of the Closeout

Notice that the final allowable grant amount (subject to

paragraphs F. and K. of this letter) is              .

Therefore, grant funds in the amount of $              shall be

canceled by HUD.  The canceled amount represents unexpended grant

funds in the amount of            , and/or unallowable costs in

the amount of          , which have been returned or repaid to

HUD in accordance with Paragraph V. of the Closeout Notice.

B.  Only the following unexpended but allowable HOPE 3 grant

funds may be drawn down from the Grantee's HOPE 3 Treasury

Account and deposited in the Grantee's local account after the

date of this letter.  Such funds shall be drawn down and

disbursed within 30 days of date of the Grantee's execution of

this letter as follows:

Amount

Unpaid Closeout Costs              $

Contingent Liabilities             $

Replacement Reserve Account        $

Total                    $

C.  HOPE 3 Program sales proceeds in the amount of $       ,

and program income in the amount of $       , which were in the

Grantee's possession on or before the date of this letter shall

be used for eligible uses under 24 CFR 572.135(a) and (c) (sales

proceeds) and (d) (program income).  These eligible uses include

(to the extent provided for in the Grantee's HUD-approved HOPE 3

application, including any amendments thereto (the "Approved

Application")) additional homeownership opportunities eligible

under the HOPE 3 Program, improvements to properties under the

HOPE 3 Program, business opportunities for low-income families

participating in the HOPE 3 Program, supportive services related

to the HOPE 3 program, any other activity specifically provided

for in the Approved Application, and the following additional

actvities eligible under the HOPE 3 Program and hereby approved,

as follows:

D.  HOPE 3 Program resale proceeds in the amount of $

in the possession of the Grantee on or before the date of this

letter and HOPE 3 Program sale and/or resale proceeds and program

income received by the Grantee thereafter may be used for any

HOPE 3 eligible activity, any activity described in 24 CFR

572.135, may be contributed to the HOME Investment Partnerships

Program (HOME) as a cash matching contribution in accordance with

the applicable HOME program rules, or may be used for the

following other affordable housing activities:

E.  Fifty (50) percent of net resale proceeds received after

the date of this letter shall be returned to HUD, in the manner

described in Paragraph V of the Closeout Notice.

F.  To the extent that any funds paid with the HOPE 3

Implementation Grant have not been audited, such funds are

subject to coverage in the next single audit performed in

accordance with 24 CFR Part 44.  The grantee may be required to

repay HUD any disallowed costs based on the results of the audit.

G.  The grantee shall retain records that clearly document

its performance under the grant for a period of three years from

the date of this Agreement.  Records with respect to resale

proceeds shall be maintained for as long as such proceeds are

received and for three years thereafter.  The grantee shall

annually provide the appropriate HUD Field Office with

information on the amount of sales and resale proceeds received

and expended, including the amount of resale proceeds returned to

HUD.

H:  If any provision of this Agreement is held invalid, such

holding shall not affect the validity of the remainder of the

Agreement.

I:  This letter agreement may be enforced by HUD by any

means available by law or under 24 CFR Part 572.

J:  This letter agreement shall be executed in four

counterparts, each of which shall be deemed to be an original,

and such counterparts shall constitute one and the same

instrument.

K.  AUTHORIZED OFFICIAL'S CERTIFICATION:  It is hereby

certified on behalf of the Grantee that, to the best of my

knowledge, all approved HOPE 3 Program activities undertaken with

HOPE 3 Implementation Program grant and match funds provided

under the Grant Agreement have been carried out in accordance

with the grant agreement and with all applicable laws,

regulations, and requirements that govern the HOPE 3 Program;

that proper provision has been made by the recipient for the

payment of all unpaid costs and unsettled third-party claims; and

that every statement and amount is true and correct as of this

date.

WARNING:  HUD will prosecute false claims and statements.

Conviction may result in criminal and/or civil penalties (18

U.S.C. 1001, 1010, 1012; 31 U.S.C. 329, 3802).

If you have any questions about this letter, please contact

of this office as soon as possible.  Otherwise, please sign this

letter in the space provided below, indicating the Grantee's

acceptance of the terms and conditions    hereof, with thirty

days of the date hereof.  If this letter is not returned within

thiry days, you will need to provide new sales proceeds, program

income and resale proceeds earned before closeout for paragraphs

C. and D. of this letter.

Sincerely yours,

CPD Field Office Director

ACCEPTED AND AGREED:

,

(Legal Name of Recipient Entity)

BY:

,

(Signature of Authorized Official)

.

(Title)

[Employer Identification Number (EIN)

of Recipient Entity]