U.S. Department of Housing and Urban Development

Public and Indian Housing

Special Attention of:

Secretary's Representatives;             Notice PIH 97-5 (HA)

Public Housing Directors;                Issued: January 21, 1997

Administrators, Area Offices             Expires: January 31, 1998

of Native American Programs;

Public Housing Agencies; Indian

Housing Authorities; Resident

Management Corporation (RMCs); Resident

Councils (RCs); Resident Organization (RO);

Intermediaries (NROs/RROs/SROs)

Subject:   Grant Closeout Procedures

I.   Objective:  The objective of this Notice is to standardized

the procedures to be followed by grantees and local HUD

Office staff in closing out a grant agreement for programs

funded under the Office of Community Relations and

Involvement (OCRI).  The procedures cover partial or

complete termination for cause by HUD as well as normal

closeout with all activities satisfactorily completed by the

grantee.

II.  Background:  Office of Management and Budget Circular A-110,

Attachment K, establishes uniform grant closeout procedures

for nonprofit organizations administering federal grants.

This includes Resident Management Corporations, Resident

Councils, and all other nonprofit organizations receiving

Public and Indian Housing grants.  Circular A-110 has been

codified by the Department under CFR Part 84.71.

Grants administered by Public or Indian Housing Agencies are

governed by OMB Circular A-102 codified in CFR Part

85.50.

receiving the following OCRI/PIH grants:

o  Tenant Opportunities Program (TOP)

o  Drug Elimination grants (PHDEP)

o  Youth Sports grants (YSP)

o  Family Investment Centers (FIC)

o  Youth Apprenticeship Program (YAP)

o  Economic Development/Supportive Services grants (EDSS)

o  Any other current and/or future OCRI administered grants

III. Closeout Procedures:  Closeout is a process by which

the Field Office determines that all applicable

administrative actions and all required work of the project

have been completed by the grantee and HUD.

A.   The Director, Office of Public Housing or the Administrator,

Office of Native American Programs is responsible for all

administrative actions and controls necessary for a timely

closeout of all OCRI grants.

B.   Grantee closeout actions.  Grantee closeout actions are

required to complete the following:

1.  It is the responsibility of the grantee to comply in

full with all closeout requirements and to submit

reports in a timely manner.  The grantee should refer to

all applicable HUD requirements as well as all general

and special conditions contained in the grant agreement.

2.  Within 90 calendar days after the termination date of

the grant, or any approved extension (revised

termination date), or early termination by HUD for

cause, the following documents must be submitted by the

grantee to the Field Office:

a.  Final Financial Status Report, SF-269A.

b.  Final narrative report.

C.   Field Office closeout actions.  The Field Office shall take

the following actions to assure that all closeout

requirements are met:

1.  At least 60 calendar days (45 days for grants terminated

for cause) before the grant termination date, the Field

Office shall review the grant file and remind the

grantee of:

a.  The grant termination date;

b.  Time limits on the expenditure of funds;

c.  Reporting submission requirements; and

d.  Record retention requirements.

2.  No later than 90 calendar days after the grant

termination date, the Director, Office of Public Housing

or Administrator, Office of Native American Programs,

will review the contents of the official grant file

against the closeout requirements and:

a.  Make sure all required reports have been received.

If not, notify grantee of overdue reports and

grant closeout requirements.  Enforcement of

regulatory requirements are detailed in CFR Part

84.62 for nonprofits and CFR Part 85.43.

b.  Perform all closeout actions which can be taken

at that time and identify any remaining

obstacles.

3.  No later than 90 calendar days after receipt of the

final reports, the Field Office shall perform the

following review of the reports:

a.  The amounts on SF-269A must not be in excess of

the budgeted amounts approved for the project

activities.

b.  The final narrative report must reflect

completion of the program with respect to

purpose of the activities authorized.

c.  The amounts of funds approved and drawn down, as

reflected in LOCCS, must be reconciled with the

expenditures as reported on the final SF-269A

submitted by the grantee.

d.  If the SF-269A indicates that excess funds have

been provided to the grantee, the Field Office

shall direct the grantee to immediately remit

excess funds.  The Field Office must then notify

the Field Accounting Division (FAD) that funds

are due from the grantee and the FAD will

establish an accounts receivable for the amount

due.  The funds must be remitted by wire transfer

for amounts equal to or greater than $2,000 or by

check for lesser amounts made payable to U.S.

Department of HUD.

e.  If the SF-269A indicates that the grantee is owed

additional funds, the Field Office shall direct

the grantee (if the grantee has not already done

so) to request the funds using LOCCS/VRS.  The

Office must then approve the draw down in LOCCS

since an automatic review flag is set by LOCCS

once a grant reaches the "Grant End Date" in the

system.

f.  Once the final Financial Status Report (SF-269A)

has been approved, after collecting any accounts

receivable or approving any draw downs due the

grantee, the Field Office shall close out the

grant by entering the "Pre-Audit End Date" in

LOCCS.  Entering this date in LOCCS stops all

reminder letters to the grantee and no longer

allows for any drawdown of funds.

g.  At the next audit of the grantee, the independent

auditor's report must be reviewed by the

financial analyst to determine if there were any

findings related to the grant previously closed

out.  Government auditing standards will

determine the extent of audit procedures

performed on this grant and the reports, if any,

required of the auditor.  If any findings come to

light, the financial analyst shall inform the

Community Relations and Involvement Specialist

(CRI) for follow-up and action.  This includes

setting up a receivable from the grantee for

unallowed costs or paying the grantee for allowed

costs still due.  Both of these actions must be

done through the FAD.  If there are no findings

contained in the report, the CRI shall send a

letter to the FAD instructing them to enter the

post-audit end date without any further

modifications.  LOCCS will automatically

recapture any unused funds.

h.  The FO shall provide a status report to OCRI

within 30 days after the end of each quarter of

all grants which have been closed out.  The report

should include: name of the program; name of the

grantee; year funded; closeout date; and any other

pertinent information.

IV.  File Retention:  Files should be maintained at official file

stations until the grant is officially closed out.  Upon

official closeout, records should remain in the Field Office

for one year and then retired to the Federal Records Center

(FRC) for five additional years.  Records must be

maintained for a minimum of six years after closeout prior

to being destroyed.  Details regarding requirements for

retirement of files to the FRC can be obtained from the

administrative officer of the local Field Office.

/s/

Kevin E. Marchman

Acting Assistant Secretary for

Public and Indian Housing

CC: Walker     Cousar     Chron Copy

PRDT              PRCS     PRSS      PR/PR              PR

Walker/Burkhalter     Burgos    Ashford   Smith/Reeves   Cousar