U.S. Department of Housing and Urban Development

Community Planning and Development

Special Attention of:                        Notice:  CPD 98-6

All Secretary's Representatives          Issued:  May 5, 1998

All State Coordinators                  Expires:  May 5, 1999

All CPD Division Directors

All HOME Participating jurisdictions    Cross Reference:

24 CFR Part 92

Subject:  Commitment and Expenditure Deadline Requirements for

the HOME Program

1. PURPOSE

The purpose of this notice is to provide procedures for

determining whether participating jurisdictions (PJs) have met

the requirements for committing and expending funds in accordance

with the requirements of 24 CFR 92.500(d) of the HOME Program

regulation.  This notice updates the procedures in CPD Notice 9707 ,

9707,

II. BACKGROUND

The HOME Program statute provides that HOME funds are available

to participating jurisdictions (PJs) for commitment to affordable

housing for a period of 24 months and that at least 1 5 percent

of each PJ's allocation must be reserved for investment in

housing to be developed, sponsored, or owned by community housing

development organizations (CHDOs).  These provisions are

implemented by regulation at 24 CFR 92.500(d).

The definition of commitment includes (1) funds that have been

committed to a specific project pursuant to a legally binding

agreement and the project has been set up in the HOME Cash and

Management Information System (C/MIS) or the Integrated

Disbursement and Information System (IDIS), and (2) funds for

which the PJ has entered into a legally binding agreement with a

State recipient, a subrecipient, or a contractor to produce

affordable housing or provide tenant-based rental assistance, or

has entered into a written agreement reserving a specific amount

of funds to a CHDO (see 24 CFR 92.2).

Further, HOME Program funds are available to PJs for expenditure

for affordable housing activities for a period of five years.

The HOME Program regulation at 24 CFR 92.500(d) provides that HUD

will reduce or recapture HOME funds in the PJ's U.S. Treasury

account that are not expended within the five year period. (See

paragraph V below).  Note: Prior to the commitment of HOME

program funds, the environmental review and notification

requirements of 24 CFR 92.35 must be addressed.

CGHF:     Distribution: W-3-1

III. DETERMINING AMOUNTS COMMITTED

In Fiscal Year 1996, many PJs received their grant in two parts.

For PJs which received two separate FY 1996 grants, the

commitment deadline will be two years from the date of

Congressional Notification of the second award. (This date is

found in block 12 of form HUD40093, Funding Approval and HOME

Investment Partnership Agreement).

There are two requirements for commitment which must be reviewed:

total commitments, and commitments to Community Housing

Development Organizations (CHDOs).

A.     Total Commitments

For purposes of determining whether a PJ has met the requirement

for committing Fiscal Year 1996 funds by its deadline, HUD Field

Offices must determine whether the sum of commitments, including

the sum of commitments to CHDOS, from fiscal years 1996, 1997,

and/or 1998 is equal to or greater than the amount of the PJ's FY

1996 allocation.  HUD considers subsequent year commitments

because it would be unfair to a PJ which because of cancellation

of a 1996 funded project, FY 1996 funds remain uncommitted and

subject to deobligation when, in fact, the PJ has already

committed subsequent years' funds.  In determining total

commitments, FY 1996 and later year funds reserved for CHDOS,

state recipients, and/or other entities and funds committed by

the PJ to specific projects are considered when determining

whether the PJ has met its commitment requirement.  However, if

any of the funds reserved to other entities are also committed to

specific projects, the amount of these commitments must be

subtracted from commitments to specific projects to avoid double

counting.  Only FY 1996 funds (and not subsequent years' funds)

reserved for CHDO operating expenses and program administration

may count toward the commitment requirement for FY 1996.

B. Determining Commitments to CHDOs

After reviewing the status of total commitments, Field Offices

must review the status of funds reserved for CHDOS.  At least 15%

of each year's allocation must be reserved for CHDOS.  FY 1996

and later year funds that are reserved to CHDOs are considered to

be committed.  If a PJ has reserved any funds for CHDO capacity

building during the first 24 months after its designation as a

PJ, these funds will be considered committed and will count

toward meeting the CHDO requirement.  Thus, funds (up to the

limit allowed) that were reserved for CHDO capacity building as

of the 24-month deadline will not be deobligated and will remain

available for CHDO capacity building.  After the 24-month

deadline, the PJ may not reserve any additional funds for CHDO

capacity building.

2

C. Data Sources

For PJs that have not been converted to the Integrated

Disbursement and Information System (IDIS), Field Staff may

monitor total commitments by reviewing the monthly C/MIS Status

of Funds Report (C47CAA) to determine the sum of the PJs

cumulative commitments.  This report shows funds committed to

specific local projects by fiscal year source of funds.  It also

shows whether the PJ has reserved funds for CHDOS, State

recipients, and/or other entities.

For PJs that have been converted to the Integrated Disbursement

and Information System (IDIS, Field staff may monitor total

commitments by reviewing the Status of HOME Grants Report

(CO4PR27) which may be generated for HOME PJs within the Field

Office Jurisdiction.  The Status of HOME Grants Report (CO4PR27)

provides information on total commitments and disbursements by

fiscal year source of funds.  It also shows whether the PJ has

reserved funds for CHDOS, State recipients, and/or other

entities.

In instances where the CMIS or IDIS reports indicate that less

than 100 percent of a PJ's FY 1996 HOME funds had been committed

and/or less than 15 percent had been reserved for CHDOs, the

Field Office is to notify the PJ and provide it an opportunity to

report commitments which are not shown on the HOME C/MIS or IDIS

reports.  If the PJ chooses to provide additional information,

please note that the PJ must provide information on all FY 1996

and later year commitments (if applicable and/or needed to

achieve commitment requirements), and not just the balance

uncommitted in the HOME C/MIS or IDIS, since commitments to

specific projects may also be included in legally binding

agreements with State recipients or subrecipients and therefore

would be double counted.

If Field Offices need assistance in accessing the C/MIS C47CAA or

the IDIS C04PR27 reports, please call Charlene Williams in the

Financial and Information Systems Divisions at (202) 708-3226,

extension 4581.

Note:     Field Offices may use the forms provided as

Enclosures 1 and 2 to this Notice, but are not required to,

in determining whether PJs met the commitment requirement.

IV.  DEOBLIGATION PROCESS

If it has been determined that funds must be deobligated, the CPD

Division Director should notify (by cc:Mail or memorandum), the

Office of Affordable Housing Programs, Attention: Charlene

Williams, of the proposed deobligation.  Then the CPD Division in

the Field Office will prepare a Funding Approval and HOME

Investment Partnership Agreement (HUD-40093), as indicated below,

to deobligate any funds that were not committed by the deadline.

This action should be completed no later than 90 days after the

PJ's commitment deadline.  The funds deobligated must be rounded

down to the nearest $1000 (e.g., rather than deobligating

$59,629.72, the amount to be deobligated must be just $59,000).

The HUD-40093 should be completed as follows:

3

Item 8 - Previous Obligation: Enter the amount of FY 1996

HOME funds awarded previously (from the original HUD-40093

for the FY 1996 funds).

8.a - Regular Funds: Repeat the amount entered in item 8.

(All funds obligated previously were regular funds.)

8.b - CHDO Reallocation: Leave blank. (None of the previous

obligation was from CHDO reallocation funds.)

Item 9 - Current Transaction: Enter the total amount of

funds being deobligated by this action. (Either put a minus

sign before the amount or parentheses around the amount to

indicate the funds are being deobligated.)

9.a - Regular Funds: Repeat the amount entered in item 9.

(Since the PJ has only received regular funds, all

deobligated amounts should be reported as regular funds.-

Again, use minus sign or parentheses.)

9.b - CHDO Reallocation: Leave Blank. (The amount of funds

deobligated because the PJ has not met the requirement for

CHDOs is to be reported in item 11.)

Item 10 - Revised Obligation: Subtract the amount entered in

item 9 from item 8 and enter here.

10.a - Repeat the amount entered in item 10.

10.b - Leave blank.

Item 11 - Special Conditions: If any of the funds are being

deobligated because the PJ had not reserved at least 15

percent of its allocation for CHDOs as required by 24 CFR

92.300 and 24 CFR 92.500(d), check box b and indicate in the

space in block 11 the amount of funds that are being

deobligated because they were not reserved for CHDOs or

attach a separate page with this information. (it is

important that we keep separate the regular HOME funds being

deobligated from the funds that have been deobligated

because the PJ had not satisfied the requirement for CHDOs

because the reallocation process is different.)

For the purpose of deobligating HOME funds, four copies of the

HUD-40093 should be prepared and signed as originals.  After the

CPD Division Director signs the Agreement (four copies), one copy

should be provided to the Field Accounting Division (FAD) for

recording the deobligation in the Program Accounting System

(PAS).  One copy should be sent to the PJ; one copy should be

sent to the Office of Affordable Housing Programs, ATTN: Charlene

Williams, Room 7168; and finally, one copy should be kept in the

Field Office grantee files.

4

Upon receipt of the HUD-executed HUD40093, FAD will deobligate

the funds and will return the funds automatically to HUI)

Headquarters for reallocation according to Subpart J of the HOME

regulations.

V. DETERMINING AMOUNTS EXPENDED AND REDUCTION OF GRANT

In accordance with 24 CFR 92.500(d), HUD will reduce or recapture

HOME funds in the HOME Investment Trust Fund by the amount of any

funds in the United States Treasury account that are not expended

within five years after the last day of the month in which HUD

notifies the PJ of HUD's execution of the HOME Investment Trust

Agreement.  In determining whether PJs have met the expenditure

deadline, HUD considers subsequent year expenditures for the same

reasons subsequent year commitments are considered for

determining whether the PJ met the commitment requirements (See

paragraph III above).  For determining whether PJs have met the

expenditure deadline for Fiscal Year 1993 funds, the sum of the

PJs expenditures from Fiscal Year 1993 through 1998 allocations

must equal or exceed the sum of its Fiscal Year 1992 and Fiscal

Year 1993 allocations.

For any PJ not meeting the expenditure deadline, HUD will offset

the PJ's subsequent HOME allocation by reducing the grant in an

amount equal to the amount of funds that was not expended by the

PJ.  After determining the initial allocation for all PJs, the

offset funds will be added to the funds available for allocation

and redistributed to all PJs except those whose allocations are

being reduced.

Within 30 days of the PJ's expenditure deadline, Field Offices

should notify any Pi that did not meet its expenditure deadline

in accordance with 24 CFR 92.500(d). The PJ should also be

notified of the amount which will be deducted from its Fiscal

Year 1999 or subsequent year HOME Program allocation.  Copies of

the notification should be provided to the Office of Affordable

Housing Programs, Attention: Charlene Williams.

NOTE:  In accordance with 24 CFR 92.508(c) HOME

participating jurisdictions must retain records pertaining

to each fiscal year of HOME funds for the most recent five

year period.  HUD Field Staff must retain records in each

PJ's program file to document each PJ's compliance with the

24-month commitment and 5-year expenditure deadline,

including actions taken by HUD to deobligate and/or

recapture HOME Program funds.

5

Enclosure 1

PJ

______________

FY 1996 HOME Funds

To Determine CHDO Requirement:

1.   Amount that must be reserved for CHDOs

to avoid deobligation (15% of Allocation shown on line 4) $______

(Enter also in Part A, line 1 of Enclosure 2)

2.   Amount reserved for CHDOs in C/MIS                        $______

(including funds for CHDO

capacity building)

3.  Amount subject to deobligation for failure to meet

CHDO Requirement (Line 1 minus line 2; however, if  $______

line 2 is equal to or greater than line 1, enter 0)

To Determine Total Commitment Requirement:

4.   Allocation amount                                   $______

5.   Minus funds reserved for program administration     $______

6.   Minus funds reserved for CHDO operating expenses    $______

7.   Amount that must be committed to avoid deobligation $______

(Line 4 minus lines 5 and 6)

(Enter also in Part B, line 1 of Enclosure 2)

8.   Amount of commitments in C/MIS                      $______

(Includes funds reserved for CHDOS, State

Recipients and other entities and funds comitted

to specific local projects.  Note: If funds reserved

for CHDOS, State recipients and/or other entities

are also committed to specific projects, the amount

of these commitments must be subtracted to avoid

double-counting when adding the funds reserved to

the funds committed to specific local projects for the

PJ's overall program.)

6

Amount subject to deobligation for failure to       $______

meet total commitment requirement (Line 7 minus

line 8; however, if line 8 is equal to or

greater than line 7, enter 0)

7

Enclosure 2

PJ

______________

Summary of FY 1996 HOME Funds

Report of HOME Funds Under Binding Commitment

Participating jurisdiction_____________

Deadline for Committing Funds________

FY 1995 Allocation________

Amount of HOME Funds Committed

Part A -CH DO Commitment Requirement

1.   FY 1996 CHDO reservation requirement                $______

(From line 1 of Enclosure 1)

2.   Total of HOME funds reserved for CHDOs              $______

3.   Balance to be deobligated

(Line A.1 minus line A.2; however, if line A.2 is

equal to or greater than line A. 1, enter 0)

$______

Part B - Total Commitment Requirement

1.   FY 1996 commitment requirement                      $______

(From Line 7 of Enclosure 1)

2.   Total of HOME funds committed by legally

binding agreements

$______

3.   Balance to be deobligated

(Line B.1 minus line B.2; however, if line B.2

is equal to or greater than line B.1, enter 0)

$______

Certification by Participating jurisdiction:

To the best of my knowledge, the information reported in Parts A

and B above is accurate.

Authorized Official:

Title:

Signature:_______________________

Date:__________________________

7

Part C - To be completed by HUD

1.   To be deobligated and reallocated by competition for CHDOs  $______

(From line A.3)

2.   To be deobligated and reallocated by formula        $______

(Line B.3 minus line C.1)

8