OVERVIEW OF CONVERSION PROCEDURE

Conversion from Project-Based Contract to Rental Voucher

Assistance

Note:  This funding process will be revised shortly by a new PIH/Housing notice on tenant-based assistance relating to all Housing conversion actions for FY 2000.

Processing Timelines

The greatest challenge to a successful transition to voucher assistance is time.  The purpose of these timelines and the processing steps is to identify the various tasks that must occur to complete the process in the context of the dates by which they should be completed.

Please keep in mind these timelines are provided as a rough guide only.  While the steps are identified in the general sequence they may occur, some steps are conditioned on completion of the preceding steps, whereas others may be completed concurrently or even earlier than some of the preceding steps.  The description of each step is followed by a code that identifies the entity primarily responsible for completing the step (e.g., OMH-2 indicates that the step in question is the second step for which the Field Office Multifamily staff has primary responsibility).  All parties are encouraged to complete their respective tasks at the earliest opportunity possible.

Abbreviations

The following abbreviations are used:

OMH – Office of Multifamily Housing staff (Field Office unless otherwise noted)

OPH - Office of Public Housing staff (Field Office unless otherwise noted)

FMC - Section 8 Financial Management Center staff

PHA - Public Housing Agency staff

HQ  - HUD Headquarters (Program area follows)

TD  - Target Date (the date when a family may suffer a rent increase or displacement unless the Housing conversion action is completed and the eligible families are under Section 8 tenant-based HAP contracts)).

The target dates for the various Housing conversion actions are as follows:

- Preservation prepayment -- The date the owner can first increase the rent after the prepayment, generally 60 days after effective date of prepayment.

- Straight Opt-out -- Expiration date of the project-based contract.

- Enforcement Action -- Termination or expiration of project-based contract.

- PD Sales --  The date of the sale of the property.

Timeline 1

This timeline applies to all Opt-outs and Preservation Prepayments.  The timeline also applies to PD Sales where the units meet program requirements.

Steps               1 - 14  15-17   18...

ß|----|----|-----|----|-------|-------|--------|-à

210   180   150  120     90      60       TD

Days

Timeline 2

This timeline applies to all HUD Enforcement Actions.  It also applies to PD Sales where units do not meet program requirements.

Steps     1 - 14  15 - 17        18...

ß|----|-----|-------|------|-------|-------|-----|à

Days  210   180     150    120     90      60

Steps

1.  Field Office OMH determines that housing vouchers are needed for a Housing conversion action.  Field OMH advises Field OPH of the number of occupants and family composition using the current Form HUD-50059s (or other information from the owner in cases where Form HUD-50059s do not apply).  Provides copies of project fact sheet and Form HUD-50059s or other tenant profiles to OPH.  This step must occur at least 120 days prior to the TD for opt-outs and preservation prepayments, and at least 180 days before the TD for HUD enforcement actions. (OMH-1)

2.  Upon receiving notice from Field OMH, Field OPH determines the appropriate PHA to administer the tenant-based assistance. Contacts PHA and extends invitation to the PHA.  Upon PHA acceptance of offer, Field OPH completes memorandum for special fee funding that is jointly signed by OMH director.  Submits memorandum to PIH HQ, PAHD, Funding Division. (OPH-1)

3.  Field OPH then provides copies of the Form HUD-50059s and/or tenant profiles to the PHA and requests that the PHA  submit an application with the unit distribution based on tenant profile and PHA subsidy standards as soon as possible. (OPH-2)

4. PHA informs Field OPH of bedroom distribution.  The PHA submits the application (Form HUD-52515) to Field OPH as soon as possible. (PHA-1)

5. Field OPH determines budget authority requirements for tenant-based funding in consultation with Field OMH. Use the Preservation Funding Worksheet for Preservation prepayments and opt-outs to request enhanced voucher funding, for all other conversion actions use the New Increment Funding Worksheet for Housing Vouchers.  In case of an opt-out (not connected with a preservation prepayment) please indicate that this is not a preservation conversion action.  Provides completed worksheet to Field OMH. (OPH-3)

6.  Field OMH notifies HQ OMH of funding needs and the PHA identified by Field OPH through memo/email and Funding Worksheet.  (OMH-2)

7.  As necessary, Headquarters OMH reallots budget authority to Headquarters OPH through Budget Office. (HQMF-1)

8. Headquarters OPH reviews special fee memorandum and assigns budget authority for the fee.  Transmits Form HUD-185 to the Financial Management Center. (HQPH-1)

9.  FMC reserves special fee funds.  Prepares special fee ACC documents and transmittal letter.  Executes special fee ACC and sends to PHA with copy of letter to Field OPH. (FMC-1)

10.  PHA should review owner income certifications to determine if acceptable.  PHA is encouraged to begin income examination and verification process as necessary. (PHA-2)

11.  Headquarters OPH reviews Funding Worksheet.  Contacts Field OPH to obtain corrections if necessary. (HQPH-2)

12.  Headquarters OMH authorizes HQ OPH to assign Section 8 funds to Field OPH. (HQMH-2)

13. Headquarters OPH assigns budget authority for the tenant-based assistance to FMC (form 185 Fund Assignment, HUDCAPS record). (HQPH-3)

14. PHA must submit application if they have not done so already (Form HUD-52515 and certifications). (PHA-3)

15. Field OPH reviews and approves the PHA application; transmits the application approval letter to the PHA with a copy to FMC. (OPH-4)

16. Upon receiving approval letter from FO PH and budget authority from HQ (HUDCAPS), FMC reserves/contracts the tenant-based funds. (FMC-2)

17.  FMC prepares the ACC documents and the ACC transmittal letter, forwards transmittal letter and ACC documents to PHA with copy of letter to Field Office OPH. (FMC-3)

18.  PHA issues vouchers to eligible families.  If at all possible, issue vouchers no later than 60 days before TD. (PHA-4)

19.  PHA prepares and submits Budget Revision to FMC. (PHA-5)

20.  FMC processes Budget Revision. (FMC-5)

21.  Family decides whether to stay in place or move.  Family submits request for lease approval to PHA.  PHA reviews rents and inspects units.  If unit is approved, executes HAP contract.  NOTE:  If family is staying in-place, effective date of voucher HAP contract may not commence before TD.

(PHA-6)

22.  PHA submits justification for amount of special fee actually claimed to FMC as part of the PHA fiscal year-end settlement (submit with Form HUD-52681 and Form HUD 52595.) (PHA-7)

23.  FMC reconciles approved fee amount during year-end settlement process. (FMC-6)