CLOSE-OUT PROCEDURES

MAIN STREET GRANTS

# Introduction

The following outlines the steps to be followed to officially close a Main Street grant.  Close-out means that:  (1) no additional Main Street grant funds may be disbursed; (2) HUD has determined that the expenditure of Main Street grant funds was made for allowable activities; (3) activities undertaken with Main Street grant funds were completed as required by the Main Street Grant Agreement and approved Main Street Development Plan, i.e., the grant application as amended by the last approved Development Proposal; and (4) all Federal requirements were satisfied.

When may a Main Street Grantee close out a grant?  A Grantee may begin the close-out process when all Main Street grant funds have been expended and all activities funded with Main Street grant funds have been completed.  At that time, a Grantee may still be completing activities under the Main Street Development Plan that are funded with non-Main Street grant funds.  .

A Grantee needs to continue to report in the Grant Management System/Quarterly Report (GMS) until ALL activities in the approved Development Plan (not just those that are funded by Main Street grant funds) are complete.  All activities may be complete at the time all Main Street grant funds are expended.  However, some activities, funded with leveraged funds, may continue for a period of time.  HUD’s preliminary close-out approval (Step 3) and final Main Street grant funding close-out approval (Step 5) will state whether the Grantee needs to continue to report in the GMS and what activities are incomplete and still need to be reported on.

# STEP 1:  Termination of Disbursements Letter and Preliminary Close-Out Materials

To begin the close-out process, within 90 calendar days after completion of all Main Street funded program activities and the expenditure of all Main Street grant funds, the Grantee must send a “Termination of Disbursements Letter” (TDL) and “Preliminary Close-Out Materials” to HUD’s Office of Public Housing Investments (OPHI).  The letter and materials should be addressed to the Deputy Assistant Secretary, with a copy sent to the appropriate Main Street Grant Manager.  At OPHI’s option, the Grantee may delay initiation of the close-out procedures until the resolution of any HUD monitoring findings.  If OPHI exercises this option, the Grantee must promptly resolve the findings.

- Termination of Disbursements Letter (TDL) (see Attachment 1 to this protocol)

The Grantee must submit a TDL, which states that:

  - The Grantee has completed all activities to be performed using Main Street grant funds;

  - All requirements of the Grant Agreement have been met (note this includes quarterly reporting requirements);

  - All obligated Main Street grant funds have been disbursed;

  - The Grantee will abide by any continuing Federal requirements; and,

  - The Grantee will complete non-Main Street funded activities that are part of the approved Development Plan and will continue to report in the Main Street Grants Management System/Quarterly Progress Report (GMS) until all Main Street activities have been completed.

- Preliminary Close-Out Materials

The Grantee must submit the following Preliminary Close-Out Materials along with the Termination of Disbursements Letter:

- Final HOPE VI Budget (Enclosure 1 to the TDL)

The Grantee must submit a HOPE VI Budget, form HUD-52825-A, (Press Control and click  HERE to obtain.), executed by the Grantee’s authorized official or employee, which shows all final expenditures for the Main Street grant by Budget Line Item (BLI).  The budget should be marked “FINAL.”

- Actual HOPE VI Cost Certificate (Enclosure 2 to the TDL)

The Grantee must submit an Actual Main Street Cost Certificate (AHCC), form HUD-53001-A.  (Press Control and click HERE to obtain.)  This form serves as the document that officially closes out the grant in LOCCS.  The AHCC must be signed by the Grantee’s authorized official on the line indicated.

- Certificates of Occupancy (Enclosure 3 to the TDL)

The Grantee must submit a Certificate of Occupancy (CofO), or the local equivalent, for each Main Street Affordable Housing Unit that has been developed under the Main Street grant.  The CofO's demonstrate that the units have been developed and are ready for occupancy.

- Affordable Use Restriction Documentation (Enclosure 4 to the TDL)

The Grantee must submit a written extract from the property manager’s standard operating procedure for the Main Street housing project.  The extract must state that the initial resident or family will have a family income no greater than the amounts stated for very low- or low-income families in HUD’s “Tables for Section 8 Income Limits,” located HERE.  The extract should also contain information as to whether the resident’s or family’s income was, or will be, adjusted for medical costs and other deductions that are allowed for public housing residents.

# Step 2:  OPHI Review of Preliminary Close-Out Materials

Upon receipt of the required TDL and Preliminary Close-Out Materials from the Grantee, OPHI will review the materials to assure compliance with the Main Street Grant Agreement and the Close-Out Procedures for Main Street Grants.  The Grantee will be expected to cooperate with this review by making available any records requested by OPHI.  OPHI shall review the materials to confirm that:

- The TDL includes the statements required by Step 1.A above.

- The amounts on the final Main Street Budget and the AHCC agree as to funds approved, obligated, and expended.  If necessary, adjustments will be made in LOCCS to reflect actual expenditures.

- The amount of funds approved and disbursed on the AHCC agrees with HUD records in LOCCS.

- If Line 1.E. of the AHCC indicates that HUD has disbursed more funds than the Grantee expended, then the Grantee will immediately remit to HUD the excess funds, without waiting for the final audit.  If the amount to be returned is $2,000 or less, the Grantee must prepare a check payable to HUD, note the Grant Number on the check, and mail the check to OPHI, to the attention of the appropriate Main Street Grant Manager.  If the amount is over $2,000, the Grantee must wire transfer the funds to HUD in accordance with instruction set forth in the Financial Management Handbook 7485.1, as revised.  Prior to wiring, the Grantee should consult further with the appropriate Main Street Grant Manager for more specific instructions.

# Step 3:  Preliminary Close-Out Approval

When OPHI has determined that the amount of Main Street grant funds disbursed, obligated and expended are equal in LOCCS, the HUD Grant Manager shall:

- Have the AHCC approved for final audit by having the Division Director of the Office of Urban Revitalization (OUR) sign the top line under the “For HUD Use Only” section of the AHCC.

B.  Have the final Main Street Budget approved by having the OUR Division Director sign the HUD-52825-A.

C.  Have an OPHI staffer with LOCCS edit access enter a Pre-Audit Date into LOCCS, which shall be the date on which OPHI first signed the AHCC and approved it for audit.  This action will prevent any further disbursements from LOCCS.

D.  Create and forward for signature a Preliminary Close-Out Approval Letter (see Attachment 2 to this protocol) to the Grantee which does the following:

  - Transmits the preliminarily approved AHCC and the final HOPE VI Budget;

  - Indicates that the Grant has been preliminarily closed out;

  - Instructs the Grantee to proceed with and submit the final audit;

  - Instructs the Grantee to submit an executed Federal Financial Report, OMB form SF-425; and,

  - Indicates whether the Grantee needs to complete non-Main Street funded activities that are part of the approved Development Plan and continue to report in GMS until all Main Street activities have been completed.  At the time of Preliminary Close-Out Approval, activities financed with non-Main Street grant leveraged funds/in-kind services may still be under way and/or not yet begun, but all Main Street grant-funded activities are complete.

    - HUD’s Preliminary Close-Out Approval Letter will outline which activities, if any, are still on-going and instruct the Grantee to continue to report on these activities in GMS.  If all activities are complete per the Development Plan, and not just Main Street grant-funded activities, this letter will inform the Grantee that they no longer need to report in GMS.

    - If all Development Plan activities have been completed, the Grant Manager will need to confirm with the OUR GMS Government Technical Monitor (GTM) (currently Lar Gnessin) as to whether all information in GMS is complete.  The OUR GMS GTM will confirm with the GMS contractor whether all information is complete.  If appropriate, the HUD Grant Manager will include the email confirming that no additional information is needed in GMS in the preliminary closeout signature package.

# Step 4:  Final Audit and Review

Each Grantee is required to conduct and submit an audit of the Main Street grant in accordance with the requirements of 24 CFR 85.26 and OMB Circular A-133.  Each Grantee is also required to submit a Federal Financial Report.

The final Federal Financial Report, OMB Form SF-425 (Press Control and click HERE to obtain), contains a cumulative summary of all expenditures and indicates the exact balance of unexpended funds, if any.  The form must be submitted with the final audit.

The expenditure of grant funds must be in compliance with OMB Circular A-87, Cost Principles for State, Local and Indian Tribal Governments, at 2 CFR, Part 225 (Press Control and click HERE to obtain.) and the audit must be performed by an independent auditor in accordance with generally accepted government auditing standards covering financial audits.  The audit may be conducted separately or as part of an agency-wide audit (Single Audit Act).  However, if conducted as part of an agency-wide audit, the Main Street portion of the audit must be reported separately.  When contracting for an auditor, the Grantee should require that statements of actual Main Street costs, certified by the Grantee and submitted to HUD during the audit period, be included in the audit’s scope and attached as supplemental information to the audit report.  The Grantee must ensure that the auditor has a copy of the AHCC for review.  Unless the auditor states otherwise in the audit report, the Grantee certified costs will be considered acceptable by HUD.  The total expenditure amount in the audit must include a level of detail that will allow HUD to match audit results to LOCCS and the final HOPE VI Budget form, HUD-52825-A.  This will allow HUD to make the determination that grant funds were spent on allowable activities.

The Grantee must submit a copy of the audit and the Federal Financial Report, OMB form SF-425, to the HUD Grant Manager.  The HUD Main Street Program Manager in OPHI (currently Lar Gnessin) will review the audit report to determine if any findings have been identified with respect to the Main Street grant funds.  OPHI will work with the Grantee to close the finding(s).  If the audited AHCC and/or SF-425 indicate that Main Street grant funds were expended for ineligible activities or in inappropriate amounts, the Grantee may be required to return such funds to HUD in the manner prescribed in Step 2, Paragraph D, above.

The audit reviewer will determine that:  1) the expenditure of grant funds was allowable; 2) the activities to be completed using Main Street grant funds were completed as required by the Grant Agreement; and 3) all Federal requirements were satisfied during the implementation of those activities.

# Step 5:  Final Main Street Grant Funding Close-Out Approval

Once the audit is reviewed and the above determinations can be made, the OPHI staffer who reviewed the audit will sign the AHCC on line 2 under “For HUD Use Only” to certify that the audited costs agree with the costs shown on the AHCC.  The close-out package for the OUR Division Director’s signature should then be created by the HUD Main Street Grant Manager.

In addition to signing the Final Close-out Letter, the OUR Division Director will sign the last line of the AHCC under “For HUD Use Only” to indicate final approval of the AHCC.

The HUD Main Street Grant Manager should put together a package for the Director’s signature that contains the following:

- Final Main Street Grant Funding Close-Out Approval Letter to the Grantee (see Attachment 3) indicating that the Main Street funded portion of the grant is closed;

- The original AHCC, to be signed by the Division Director.

At the time of Final Main Street Grant Funding Close-out, activities financed with non-Main Street grant leverage funds may still be under way and/or not yet begun, but all activities funded with Main Street grant funds are complete.

If this is the case, the letter needs to indicate whether the Grantee needs to complete non-Main Street funded activities that are part of the approved Development Plan and continue to report in GMS until all Main Street activities have been completed.  HUD’s Final Main Street Grant Funding Close-Out Approval Letter will outline which activities, if any, are still on-going and instruct the Grantee to continue to report on these activities in GMS.

If all activities are now complete per the Development Plan, and not just Main Street grant-funded activities, this letter will inform the Grantee that it no longer needs to report in GMS. As in Step 3(D), prior to finalizing the letter, confirm that the grantee has put all information into GMS and include the email confirming this in your package.

In your final close-out approval package, please include a copy of the signed and dated preliminary closeout letter.

Once the Division Director has signed the letter and the AHCC, the following should be sent out:

- Original signed letter and a copy of the AHCC goes to the grantee.

- Copy of the letter and the original, fully executed AHCC goes to the Main Street Grant Manager.

- The Grant Manager should make sure that the AHCC is sent to HUD’s Office of Financing and Accounting (OFA) in Ft. Worth.  The Grant Manager can either mail the original copy or send OFA a fax/scanned copy.

- If the original AHCC is not sent to OFA, it should be filed in the blue docket folder with the close-out documents.  If the original AHCC is sent to OFA, a copy of the AHCC should be filed in the blue docket folder with the close-out documents.

OFA will attach the AHCC to its copy of the Grant Agreement.  The AHCC will amend the Grant Agreement in the event that the amount of Main Street grant funds actually expended on the project is less than the original amount of the Main Street grant.  Any funds remaining in the grant will be recaptured by HUD.  Recaptured funds will automatically be reflected in

BLI 9900, Post Audit Adjustment, once the grant is closed.  OFA will enter a Post-Audit Date in LOCCS.  The grant will then be officially closed as far as HUD’s accounting systems are concerned.

Step 6:  Final Main Street Plan Close-Out Approval

If grant activities have continued following HUD’s transmission of the Final

Main Street Grant Funding Close-Out Approval Letter, the Grantee must inform HUD when ALL activities authorized under the approved Development Plan have been completed, including all activities funded with non-grant funds.  The Grant Manager will verify that all grant activities have been completed in accordance with the Development Plan and request the GMS contract GTM to verify that all required data has been correctly entered into the GMS (include email from the GMS contract GTM in your package).  Once this is verified, OPHI will send a Final Main Street Plan Close-Out Approval Letter to the Grantee (see Attachment 4) stating that all activities under the approved Development Plan are complete, the Grant is considered closed out by OPHI, and that the Grantee may stop reporting into GMS.

In your package, include the signed and dated preliminary and final closeout letters previously sent to the grantee.

To the Grantee:  For further information on closing out a Main Street grant, contact your HUD Grant Manager.

To the HUD Grant Manager:  For further information on closing out a Main Street grant, contact the HOPE VI Main Street Program Manager.