U.S. Department of Housing and Urban Development

H O U S I N G

_______________________________________________________________________

Special Attention of:                        Notice   H 94-71 (HUD)

All Secretary's Representatives;

Directors, Offices of                        Issued:  9/15/94

Regional Housing; Directors,                 Expires: 9/30/95

Regional Accounting Division;                ______________________________

State and Area Coordinators;                 Cross References:

Administrators, Offices of Native American   H-93-35

Programs; Housing Management Division        H-94-21

Directors; Public Housing Management         H-94-41

Division Directors; Farmers Home

Administration State Office Directors

_______________________________________________________________________

SUBJECT:  THE EXTENSION, AMENDMENT AND CLOSE-OUT PROCESS FOR

CONGREGATE HOUSING SERVICES PROGRAM (CHSP) GRANTS

I.  PURPOSE:

This Notice provides updated instructions and expanded

responsibilities for HUD/FmHA Government Technical

Representatives (GTRs) and Government Technical Monitors (GTMs)

and processes for the extension, amendment and close-out of

grants awarded for HUD and FmHA projects under the CHSP.  It also

assigns Grant Officer responsibility to the HUD State and Area

Offices.

With the issuance of this Notice, all CHSP processing

has been delegated to the State and Area Offices, except the

release of funds by the Funds Reservation and Contract Authority,

(HUD-185).

II.  BACKGROUND:

The Congregate Housing Services Program Act of 1978

authorized the funding of three to five year renewable grants for

the provision of supportive services to maintain independent

living for frail elderly, non-elderly handicapped and temporarily

disabled persons.

Section 802 of the National Affordable Housing Act (42

USC 8011) as amended by Sections 604 of 42 USC 8011 and 672 of 42

USC 13631 of the Housing Community Development Act of 1992

(P.L.102-550) revises and expands the CHSP.  Funding for HUD and

FmHA projects is awarded through competitive selection for a five

year contract period which is renewable subject to funding

availability and grantee compliance with program requirements.

___________________________________________________________________________

HMEES : Distribution:  W-3-1,W-2(H),W-3(H)(FHEO)(ZAS)(PD&R),W-4(H),R-1,R-2,

R-3-1(H)(RC),R-3-2,R-3-3,R-6,R-6-2,R-7,R-7-2,R-8

Previous Editions Are Obsolete                              HUD 21B (3-80)

GPO 871 902

_____________________________________________________________________

The statute "grandfathers" grantees funded under the

CHSP Act of 1978 into the revised program and allows them a six

year period to meet the requirements of the new program.  These

grants are in the third and fourth year of the six-year

transitional period.  These grants are generally extended for 12

months or longer pursuant to instructions contained in a HUD

Notice issued annually.

This Notice together, with Notice H-94-21, "Monitoring

Responsibilities of Government Technical Representatives (GTRs)

and Government Technical Monitors (GTMs) Under the Congregate

Housing Services Program", replaces Chapters 2 and 4 of Handbook

4640.1, "Monitoring and Technical Assistance Handbook for the

Congregate Housing Services Program".

NOTE:     HUD Headquarters recognizes that any instructions

referenced herein for the responsibilities of the

Field Accounting Division (FAD) and certain State

and Area Office responsibilities in processing

CHSP grants may have to be modified in Fiscal Year

1995, depending on the reorganization and the

manner in which the transition to the field

organization takes place.  If necessary, there

will be appropriate modification to the procedures

stated in this Notice.

III.  DELEGATION OF CHSP GRANT PROCESSING TO HUD STATE

AND AREA OFFICES:

The administration of the CHSP grant process for HUD

and FmHA projects has been delegated to the State or Area Office

Director of Housing or Director of Multifamily, as appropriate,

with the assistance of the Directors of Public Housing/Native

American Programs Housing Management as needed.

The CHSP Grant Officer responsibility has been

delegated to the HUD Director of Housing or the Director of

Multifamily, as appropriate.

This responsibility is redelegable, if necessary, but

must remain within the Multifamily Division.

THE CHSP IS A HOUSING PROGRAM.  THE CHSP GRANT OFFICER

RESPONSIBILITY MAY NOT BE DELEGATED TO THE OFFICES OF PUBLIC

HOUSING OR NATIVE AMERICAN PROGRAMS.

The CHSP Grant Officer ALSO may NOT serve as a

Government Technical Representative or Monitor (GTR/GTM).

2

_____________________________________________________________________

The following Grant Officer functions are CHSP

specific:

-    approving and executing all grant documents, and

any deviations therefrom and amendments thereto

for both HUD and FmHA grants; (negotiating budgets

may be delegated to CHSP GTRs).

-    Disseminating written instruction/information to

grantees; and,

-    the general administration of all grant awards

including monitoring the technical progress of the

grant with the HUD/FmHA GTR's assistance (see

Notice H-94-21 on CHSP monitoring requirements).

IV.  ANNUAL AND OTHER EXTENSIONS OF CHSP GRANTS:

A.   GENERAL:

CHSP grants are normally extended indefinitely

under the same grant instrument and grant number.  However, grant

extension processing procedures for grants funded under the CHSP

Act of 1978 may vary from those for grants initially funded under

Section 802 of the NAHA of 1993 because differences in the grant

extension periods necessitate different grantee submission

requirements.

CHSP grants are extended on a cost or no-cost

basis (or some combination thereof) for a specified period of

time, generally 12 months or longer.  Cost extensions are for new

dollars when additional funding is required to meet the

associated grant costs; no-cost extensions utilize the grantee's

unexpended dollars from the prior grant period to meet associated

grant costs without the provision of additional new funding.

Cost/no-cost extensions use both leftover and new dollars.  All

extensions will be in increments  set by HUD Headquarters.

Grantees are normally instructed to request an

extension at the current operating level plus an inflationary

allowance.  Additional funding above the inflation allowance may

be requested with appropriate justification.

B.   PROCESS FOR ASSIGNING AND RESERVING EXTENSION

DOLLARS FOR PROJECTS FUNDED UNDER THE CHSP ACT OF

1978:

The GTR(s) must estimate the total amount of

dollars required to extend the grants in that office for each

year, based on currently approved grantee budgets.  The base

3

_____________________________________________________________________

request is for continuation of the grants which will expire

during the calendar year, plus a HUD-approved inflationary amount

of approximately five percent (5%).

As CHSP is a Housing program, the Housing staff

must be responsible for submitting an aggregated fund assignment

request for both Housing and Public Housing/Native American CHSP

grants in that office to Headquarters.

The fund assignment process should proceed as

follows:

1.   Housing GTR(s) should jointly decide the

dollar estimate needed for the year by

totaling the annual dollar amounts of all of

his/her currently approved grantee budgets

and multiplying this sum times the

inflationary amount cited in the HUD annual

extension Notice.

2.   The Public Housing/Native American Programs

GTR(s) should provide this information as

appropriate to Housing.

3.   Housing will then prepare a memorandum from

the Director, Multifamily Housing Division to

the Services Branch, Office of Elderly and

Assisted Housing at Headquarters, to request

the Funds Reservation and Contract Authority

(HUD-185) for estimated dollars needed for

the extension of all CHSP grants in that

Field Office for the year.  This memorandum

will list each grantee by name, grant number

and new dollars estimated.

4.   The Services Branch will request the

Headquarters Funding Control Division to

issue the appropriate HUD-185 assigning funds

to that State or Area Office within 30 days

of request.

5.   Housing staff must forward the HUD-185 to the

Field Accounting Division (FAD) to be filed.

NOTE:     GTRs MUST complete this process

during the first quarter of the

fiscal year so that CHSP funds FOR

THE YEAR are assigned to offices

BEFORE individual grant extension

packages are scheduled for receipt

and processing.

4

_____________________________________________________________________

C.   EXTENSION OF GRANTS FUNDED UNDER THE 1978 ACT:

1.   General:

Grants funded under the 1978 CHSP Act are

generally extended for one or more years at a

time.  Each grantee must submit a complete

application for extension request to the GTR

for the continuance of funding for an

additional year; or, for multi-year

extensions, follow the instructions for

processing post-Fiscal Year 1993 grants in

Section D below.

2.   Grantee Actions for 12 Month Extensions:

Grantees must submit the extension package to

the HUD State or Area Office at least 60 days

before the expiration date of the current

grant period.

The grantee's extension request will contain

at least the following components, in such

form as HUD Headquarters may require in the

Field Notice for that year.

-    Transmittal Letter

-    Application For Federal Assistance

(SF-424)

-    Budget Forms

-    Narrative documentation is also required

for major changes in the program service

levels or increases above the approvable

inflationary level.

-    Documentation Of Match For Next Funding

Period, if appropriate.

-    HUD-2880

-    Certifications, As Appropriate

-    Any Other Items Required

3.   Grantee Actions for Multi-year Extensions:

When multi-year grant extensions are in

place, grantees should not submit a complete

application for extension.  They must only

5

_____________________________________________________________________

complete the processing in Section D below to

advise HUD whether the funds approved for the

coming year are sufficient or must be

modified.

4.   HUD State and Area Office Actions for 12

Month Extensions:

The HUD GTR must:

a.   Review the extension materials for

accuracy and consistency with Notice

instructions and request

corrections/resubmissions from grantees

as appropriate.  Compare materials with

most recently submitted annual report

(HUD-90006) for consistency.  Fourteen

(14) calendar days are allowed for

grantees to submit

clarifications/corrections.

b.   Prepare a short transmittal memorandum

to the Grant Officer requesting approval

and/or explaining any other relevant

details; and, attach the Congregate

Housing Services Program Grantee Review

Form (HUD-90003) (if done within the

prior two year period) to the approvable

grantee extension package.  REMINDER:

GTR MUST retain a copy of the extension

package for the GTR's files.

c.   Prepare the Funds Reservation and

Contract Authority (HUD-718) (see sample

and instructions at Appendix 1).

d.   Prepare the Grant Assistance Award

Amendment (HUD-1044) (see sample and

instructions at Appendix 2).

e.   Retain the grantee extension package and

forward to the FAD the HUD-718 (original

and 1 copy) and a brief memorandum

requesting the reservation of funds.

NOTE:     The FAD cannot process the HUD-718

to reserve the extension dollars

for individual grants unless the

fund assignment has been previously

processed as required at Section IV

B of this Notice.

6

_____________________________________________________________________

After the FAD enters the dollar

amount into the Project Accounting

System (PAS) and certifies the

availability of funds by signing

item 10 of the HUD-718, the FAD

retains the original HUD-718 and

returns a copy to the GTR.

f.   The GTR then signs the transmittal note

and forwards the grantee's transmittal

letter, budget forms and documentation

of match, a copy of the signed HUD-718

and the HUD-1044 to the Grant Officer.

g.   The Grant Officer retains the grantee

documents as file documentation and

sends the HUD-1044 and attachments to

the grantee for signature.

h.   The authorized official of the grantee

signs the HUD-1044 and returns it to the

Grant Officer by overnight mail.

i.   The Grant Officer signs the HUD-1044,

thereby executing the grant document and

obligating the funds, retains the

original in the Grant Officer files;

and, distributes conformed copies as

follows:

-    One conformed copy to the grantee.

-    A copy to the GTR and the FAD

NOTE:     All GTRs must maintain a working

file for each grantee.  However,

the Grant Officer's official file

shall be the file which is referred

to if disputes arise.

5.   HUD State and Area Office Actions for Multi-year

Extensions:

When Section C(3) above applies, HUD office

should complete the processing instructions

in Section D below.

7

_____________________________________________________________________

D.   EXTENSION OF GRANTS INITIALLY FUNDED IN FISCAL

YEAR 1993 OR LATER:

1.   General:

HUD and FmHA grantees initially funded since

Fiscal Year 1993, were awarded grants for a

five year period which allows for a

simplified annual extension procedure.  This

procedure is necessary to allow the HUD State

or Area Office to enter the next annual

increment of HUD funds into LOCCS/BLI (see

Notice H-94-41).

2.   Grantee Actions:

Grantees must notify the HUD State or Area

Office or the FmHA State Office 60 days

before the end of each annual funding period

whether the budget amount approved in the

grant agreement for the coming year is

sufficient to support program activities; or,

that it must be modified to allow for a shift

in budget line items which will not change

the budget total; or, to provide additional

funding as allowed by existing procedures.

Notification is either by written advisement

to the GTR that a change is not required or

the submission of a written request to change

budget line items or amend the grant

agreement with a revised budget,

documentation and additional match/fees as

appropriate to support the need for the

funding increase.

The grantee must also submit the fourth

quarter Financial Status Report, SF-269, to

document actual expenditure of HUD funds,

match and fees consistent with HUD Notice

H-94-41.

3.   HUD State/Area Office/FmHA State Office

Actions:

a.   For Grants Which Do Not Require Budget

Increases:

When the grantee advises that the annual

grant amount for the coming year is

sufficient and no change is needed; and,

the fourth quarter's SF-269 is

8

_____________________________________________________________________

determined to be in compliance with

program requirements, and consistent

with the most recent by submitted

HUD-90006 the HUD GTR must enter the grant

amount for that year into LOCCS/BLI for

both HUD and FmHA grants, (see LOCCS

Notice H94-41 for entry instructions).

b.   For Grants Which Require a Change In

Budget Line Items:

The grantee may shift dollars among

existing individual budget line items,

WITHOUT PRIOR APPROVAL, if such changes

are less than ten percent (10%) of the

affected line items; and, do not change

the total dollar amount of the grant.

The grantee should document any

revisions for his files and provide a

copy to the GTR.  The GTR should enter

any revisions into the LOCCS, as

appropriate.

The grantee MUST provide written

justification and receive prior approval

from the Grant Officer BEFORE deleting

or adding individual budget line items

to the grant.

NOTE:     IT IS IMPERATIVE THAT GRANTEES

AND GTRS BE AWARE OF HUD

REGULATORY PROVISIONS AT 24

CFR PART 85.30 FOR STATE,

LOCAL AND INDIAN TRIBAL

GOVERNMENTS, AND 24 CFR PART

84.25 FOR NON-PROFITS WHICH

IMPLEMENT OMB REQUIREMENTS

GOVERNING BUDGET AND PROGRAM

CHANGES.

c.   For Grants Which Require Budget

Increases

REMINDER:  The GTR must contact Funding

Control to ask whether funds are

available before proceeding.  The GTR

must process the HUD-185 and the HUD-718

to assign and reserve the additional

funds before processing the SF-1044.

9

_____________________________________________________________________

Any additional funding must also have a

Corresponding amount of grantee match;

i.e., if the total budget increase is

$10,000 for that year at least $5,000

must be match, $1,000 must be

participant fees, and no more than

$4,000 may be HUD funding.

When the grantee submits a revised

budget, justification for the increase

and the fourth quarter SF-269, the

HUD/FmHA GTR then processes the request

to amend the grant as instructed in

Section IV C of this Notice and sends it

to the grantee for signature.

The grantee must sign the grant

amendment in block 19 and return it to

the Grant Officer by overnight mail.

After receipt of a conformed grant

amendment from the Grant Officer, the

HUD Housing GTR enters the revised

budget amount into LOCCS/BLI (for both

HUD and FmHA grants).

The original executed amendment is filed

in the Grant Officer's official file.  A

conformed copy of the grant award is

sent to the FAD, the grantee and both

HUD and FmHA GTRs, where appropriate.

V.   CHSP GRANT AMENDMENTS:

A.   GENERAL:

If HUD approves the grantee's request for

modification of a CHSP grant it may be modified at any time.

Amendments that result in a material change must be executed by

both the Grant Officer and the grantee.

Examples of material changes that require a grant

amendment executed by both parties include but are not limited to

the following:

-    addition of funds from the CHSP reserve, if

available

-    addition or deletions of line items; and,

10

_____________________________________________________________________

-    changes of more than ten percent in the

budget line items of the total approved

budget amount for grants over $100,000 (for

non-profit grantees see OMB Circular A-110

soon to be implemented at 24 CFR Part 84.25;

for state, local or Indian Tribal government

grantees, see 24 CFR Part 85.30).

-    changes from the original budget estimate

that will change the amount of grantee match,

participant fees or HUD's grant share.

-    Changes in the grantee's program scope,

objectives or timetable.

Administrative amendments, such as changes in the

GTR, may be issued unilaterally by the Grant

Officer.

NOTE:     Grant termination for cause may be

done unilaterally by HUD in accordance

with HUD requirements (see recapture of

funds in Section VII below).

B.   GRANTEE ACTIONS:

Requests for grant amendments must be in writing.

The request must contain:

-    an explanation of what the modification is;

-    a justification; and,

-    dollar amounts, including revised budgets

using the Summary Budget (HUD-91180-B),

Annual Program Budget (HUD-91178-A), the

Statement of Work Summary (91180-B) and any

other information required by HUD.

NOTE:     The GTR should check with Funding

Control to see if funds are available

before processing any requests for

additional funding (i.e., the HUD-718).

If HUD's grant is increased, the

grantee's match and participant fees

must be increased in accordance with

HUD/FmHA requirements.

11

_____________________________________________________________________

C.   HUD STATE/AREA OFFICE/FmHA STATE OFFICE ACTIONS:

The GTR must begin processing the grantee's

amendment request within 10 work days of receipt from the CHSP

grantee.  The GTR should review the request for the following:

-    the requested amendment is permissable under

the CHSP.

-    the grantee has new match letters from third

parties certifying additional match amounts

for each new/expanded service and sufficient

participant fees as required under the CHSP.

-    the justification provided meets the CHSP

requirement.  An example of acceptable

justification would be documented larger

salary increases for other employees of the

facility or high increases in the cost of

food or services billed to the CHSP by third

party providers.

Unacceptable increases would be cost increases

based on generally increased spending above the prior year's

approved budget level or additional participants serviced above

the maximum number stated in the grant agreement.

For a FmHA project, the FmHA GTR will review the

grantee's request, prepare the SF-718, if appropriate, and the

SF-1044 amendment and forward the package to the HUD State/Area

Office Director of Housing or Director of Multifamily, as

appropriate, for further processing and approval.

Since an amendment to the grant for additional

dollars requires a request for the assignment of additional

funds, Housing should prepare a memorandum to Headquarters to ask

for the additional dollars according to the fund assignment

processing instructions in Section IV.B.

Upon receipt of the HUD-185 from Headquarters, the

Multifamily Asset Management Branch should initial the HUD-718

and forward the HUD-185 and the HUD-718 to the FAD for approval.

(see Appendix 1).

NOTE:     If a grantee exhausts its funds before

the end of the grant period (i.e., the

grantee and/or one or more sites has not

kept within the budget, resulting in

overspending), HUD/FmHA has no

obligation to make up the shortfall with

additional funds.

12

_____________________________________________________________________

VI.  CHSP GRANT TERMINATIONS:

A.   VOLUNTARY WITHDRAWALS:

Grantees, or newly selected applicants to the

CHSP, may request to withdraw for a variety of reasons, such as

the lack of real need once the program is started, inability to

sustain the required match, or decreasing need for the CHSP due

to the availability of other sources of supportive services.

1.   Grantee Actions:

Withdrawal BEFORE Execution of the CHSP Grant

Award.

If the grantee accepts the grant award but

withdraws before execution of the grant,

he/she must submit a written request.  The

request must be on organization letterhead

and addressed to the HUD/FmHA GTR.  The

letter should contain a request to withdraw

from the CHSP and an explanation of the

reason for the withdrawal.

Withdrawal AFTER Execution of the CHSP Grant

Award.

If the grantee voluntarily withdraws after

executing the grant award, he/she must submit

a written request for withdrawal.  The request

should clearly state the reasons for

withdrawal, any other information regarding

the disposition of funds or equipment, etc.,

purchased under the grant, and any other

documentation required by HUD.

In this instance, the grantee must conform to

relevant Federal closeout requirements and

the Grant Officer must execute the SF-1044 to

closeout the grant award even if supportive

service delivery was not implemented.

2.   HUD State/Area Office/FmHA State Office

Actions:

After discussion with the grantee, where

appropriate, and the HUD/FmHA GTR's

supervisor (and FmHA Headquarters, if

appropriate), the HUD/FmHA GTR shall submit a

brief memorandum to the Grant Officer

transmitting the grantee's withdrawal request

13

_____________________________________________________________________

and requesting approval, a HUD-1044 to

closeout the grant and an unsigned HUD-718 to

deobligate grant dollars.  NOTE:  After the

Grant Officer has signed the HUD-1044, the

HUD-718 may be signed to recapture the funds.

The Grant Officer shall:

-    Notify the grantee of acceptance of the

withdrawal in writing, with a copy to

the GTR;

-    Execute the HUD-1044 to closeout the

grant. (Must be completed by the Grant

Officer BEFORE the FAD recaptures funds,

see below); and,

-    Request the FAD to recapture any

remaining dollars into the appropriate

account AFTER the Grant Officer has

officially deobligated and removed them

from the grant.  (see Section VI B on

procedures for recaptures).

The GTR shall request the Grant Officer to

request the Office of the Inspector General

to do a close-out audit of the former

grantee, if appropriate.

B.   RECAPTURES:  HUD-DIRECTED GRANTEE TERMINATION AND

DOLLAR RECAPTURE:

1.   First-Year Recapture:

If a grantee does not comply with the grant

agreement or fails to offer supportive

services to program participants within 365

days of the execution of the CHSP grant,

HUD/FmHA may pursue a range of sanctions

pursuant to 24 CFR 700.415 or 1944.415,

including the termination of the grant and

the recapture of grant funds.

HUD State-Area Office/FmHA Actions:

At the end of the 12th month without the

grantee's implementation of service delivery,

if termination of the grant is deemed

appropriate, the HUD/FmHA GTR must complete

the following procedures for grant

termination and fund recapture:

14

_____________________________________________________________________

a.   Verify that grantee has incurred no

expenditures for service delivery and

send a letter advising the grantee that

the grant is being recommended for

termination and recapture of funds

subject to Section 700.415 or 1944.282

of the Final Common Rule.

b.   Prepare a grant termination package to

go to the Grant Officer which includes

an unsigned HUD-718 to dereserve the

funds for recapture (or can be prepared

after the settlement of all accounts

since it cannot be signed until after

the Grant Officer has executed the HUD-1044),

a HUD-1044 to terminate the grant

and a memorandum to the Grant Officer

recommending the termination of the

grant and the recapture of the funds.

The memorandum must include:

-    Name and address of grantee (and

project(s) if different);

-    Grant number

-    Recommendation for grant

termination and the recapture of

funds, including reasons for so

doing (also state extenuating

circumstances, if any).

-    Amount of funds initially

obligated, amount of administrative

funds reimbursed to date (if any);

and, amount of funds remaining for

recapture.

The grant termination package is sent to the

Grant Officer.  A copy of the memorandum is

sent to the grantee, the HUD/FmHA GTR and

FmHA Headquarters, if appropriate.

c.   The Grant Officer will issue the grantee

a letter of termination and instruct the

FAD to recapture the funds remaining in

the grant after the grant is terminated.

d.   When the grant is terminated, the Grant

Officer may request the Inspector

General to do a closeout audit of the

former grantee.

15

_____________________________________________________________________

2.   Other Terminations and Recaptures

Recaptures other than for lack of first year

start-up will usually result from major grantee

problems which are not correctable, resulting in

either termination or withdrawal from CHSP (see

Section prior).  Terminations and recaptures must

comply with the CHSP regulations at 24 CFR 700.415

or 1944.415.

VII.  THE GRANT CLOSEOUT PROCESS:

A.   GENERAL:

Closeout is the process by which HUD determines

that all applicable administrative and project requirements have

been completed by the recipient and HUD.  Each grant document

must be closed out at the end of its performance period.

Closing the grant requires the completion of all

required audits, property disposition, settlement of costs,

reconciliation of payment records, closeout reports and

completion of the GTR Performance Assessment (see Section VII C

and Appendix 4 for instruction on completion of GTR Performance

Assessment Form HUD-24016).  Other requirements may also be

specified by the Grant Officer.

Requirements for the closing of grant documents

for state, local and Indian Tribal Government grantees are

contained in HUD regulations at 24 CFR Part 85, "Administrative

Requirements for Grants and Cooperative Agreements to State,

Local and Federally Recognized Indian Tribal Governments" in

Subpart D, titled "After-The-Grant Requirements".

Requirements for the closing of grant documents

for nonprofit grantees may be found in the Office of Management

and Budget (OMB) Circular A-110 which was published as a Final

Rule in the Federal Register on November 29, 1993.  Provisions in

this circular will soon be codified as 24 CFR Part 84 (see

Subpart D, "After-The-Award-Requirements."

B.   GRANTEE ACTIONS:

The grantee must comply fully with all closeout

requirements within 90 days after the expiration or termination

of the grant as specified in the following regulations or

documents:

-    The specific and general clauses contained in

the CHSP grant agreement (HUD-1044);

16

_____________________________________________________________________

-    any HUD/FmHA requirements specified in a

letter or grant amendment from the Grant

Officer; and,

-    requirements contained in 24 CFR Parts 84 or

85, as applicable, Subparts D which prescribe

uniform close-out requirements for all

Federal grantees.

Pursuant to the above referenced requirements, the

grantee must submit the Final Financial Report, SF-269 (see

Appendix 3) and the Post-Grant Report which reflects completion

of all program activities required under the grant and is

submitted as prescribed in the Grant Officer's closeout letter.

C.   HUD AREA/STATE OFFICE/FmHA STATE OFFICE ACTIONS:

1.   The HUD/FmHA GTR must complete a form HUD-24016,

"Final GTR Performance Assessment for

Assistance Agreements" (see Appendix 4).

The GTR shall indicate on the form:

-    Whether the recipient has completed all

performance requirements;

-    the acceptability of performance by

major objectives or task;

-    whether any patentable items were

developed;

-    whether property was furnished to or

acquired by the recipient; and,

-    a qualitative rating of the recipient

which should objectively address the

recipient's expertise, ability to keep

actual costs and completion times in

line with those originally estimated,

and other aspects of their performance.

The HUD/FmHA GTR must complete this form and

forward to the Grant Officer.

2.   The HUD/FmHA GTR must review the Final

Financial Report, SF-269, and the grantee's

Final Performance Report as follows:

17

_____________________________________________________________________

-    Assure that all financial, programmatic

and administrative activities necessary

to closeout the grant are completed.

-    That the grantee is reimbursed for any

eligible outstanding costs (see Section

VII E on final payment under LOCCS/VRS).

-    That the grantee remits any grant funds

owed to HUD/FmHA.  If appropriate, the

grantee must be notified in writing to

remit the excess funds to HUD by wire if

$2000 or more, or by check for lesser

amounts, made payable to HUD.

The check would then be forwarded to FAD

for processing, except for interest on

advances which must be remitted to HUD

for state, local or Indian tribal

government grantees as required in 24

CFR Part 85.21 (i) and to the Department

of Health and Human Services for

non-profit grantees as required in 24 CFR

Part 84.22 (e).

At the time a Final GTR Performance

Assessment, HUD-24016, is sent to the Grant

Officer by the GTR; the Grant Officer shall

initiate the necessary actions to close out

the award, which may include audit

resolution, financial settlement, payment

approval and execution of closeout

agreements.

NOTE:     Closeout of a grant is a step-by-step

process.  The number of steps

in the process may vary by project.

Grantees and GTRs/GTMs should

familiarize themselves with

requirements at 24 CFR Part 85

which sets forth the policies and

procedures for closing out Federal

grants made to State, local or

Indian Tribal Governments; and, 24

CFR Part 84 which sets forth these

provisions for nonprofit

organizations.

D.   GRANTEE NOTIFICATION:

Upon completion of all administrative actions for

final closeout, the Grant Officer shall notify the grantee of the

18

_____________________________________________________________________

terms and conditions of closeout in the form of a letter or an

amendment to the grant indicating that the grant program is

closed out.

The letter may include, but not be limited to:

1.   Final financial settlement;

2.   provision for submission of audit reports and

due dates;

3.   record retention requirements; and,

4.   if closeout is made without full audit

coverage, a statement that HUD/FmHA reserves

the right to recover disallowed costs or take

other appropriate action if HUD/FmHA

determines that information provided by the

grantee is false or erroneous; or if the

subsequent audits or adjustments result in

amounts owed to HUD.

E.   FINAL PAYMENT THROUGH LOCCS:

1.   Grantee Action:

The grantee must submit the Financial Status

Report, SF-269, and a final LOCCS/VRS CHSP

Payment Voucher, HUD-90198, to the GTR no

later than 90 days after the grant closeout

date or other timeframe specified by the

Grant Officer.

2.   HUD State/Area Office/FmHA State Office

Actions:

The final payment of a HUD/FmHA grantee under

LOCCS/VRS shall be processed by the HUD GTR

(for both HUD and FmHA grants) pursuant to

the instructions below and those contained in

Notice H 94-41, "Instructions for Use of the

Line of Credit Control System/Voice Response

System for the Congregate Housing Services

Program (CHSP)."

For FmHA grants, the FmHA GTR is responsible

for reviewing the SF-269 and HUD-90198 forms

referenced below for accuracy and

acceptability before forwarding to the HUD

GTR for execution of the LOCCS/VRS closeout

as referenced below.

19

_____________________________________________________________________

To assure proper financial closure under the

LOCCS/VRS, the following steps MUST be

completed:

-    At date of grant closeout, the HUD GTR

must execute the MO1 function which

suspends payment to deny the grantee any

access to additional automatic payment.

-    HUD GTR should execute the QO5 function

to determine the amount of the

undisbursed balance in the grant.

-    HUD/FmHA GTR requests the final SF-269

and a HUD-90198 from the grantee for

final payment due (if he has not already

done so) for receipt no later than 90

days after the grant expiration/closeout

date.

-    HUD/FmHA GTR reviews the SF-269 and the

HUD-90198 for accuracy, acceptability

and consistency with the LOCCS balance

and the grantee's approved budget.

-    HUD/FmHA GTR forwards the SF-269, HUD-90198,

a HUD-1044 to closeout the grant

and deobligate any surplus funds

remaining after the grantee's final

payment, if appropriate, an unsigned

HUD-718 for funds dereservation with a

memorandum to the Grant Officer

indicating grant closeout or

termination, requesting payment approval

and deobligation of any grant balance.

-    Grant Officer executes the HUD-1044,

approves the SF-269 and returns it to

the GTR; sends a request to FAD to

recapture all excess balance above the

amount due for final grantee payment, if

appropriate; and, notifies grantee that

final payment may be requested under

LOCCS/VRS.

-    HUD GTR executes the FO1 function to

update the budget line items (BLIs) to

reflect the exact amount of payment due

for each budget line item.

-    HUD GTR executes the MO1 to lift the

funds suspension so that grantee can

20

_____________________________________________________________________

drawdown final payment.  This should

leave a zero (0) balance in the grant

account.

If any items remain outstanding, the Grant

Officer will discuss the matter with the GTR.

F.   AUDIT:

CHSP nonprofit grant recipients/subrecipients are

subject to audit requirements at 24 CFR Part 45 titled "Non-Federal

Audit Requirements for Institutions of Higher Education

and Other Nonprofit Institutions" (implements OMB Circular A-133

titled "Audit of Institutions of Higher Learning and Other

Nonprofit Organizations").

CHSP recipients/subrecipients that are State,

local or Indian tribal governments are subject to audit

requirements at 24 CFR Part 44 titled "Non-Federal Audit

Requirements for State and Local Government" (implements OMB

Circular A-128 titled "Audits of State and Local Governments").

The grant dollar thresholds and conditions which

trigger audit requirements are similar for all grantees and are

set forth in the regulations cited above.

In the closure of grants, for the performance of

final cost audits, the HUD Office of Inspector General (OIG) is

normally not requested to perform audits on grants under $100,000

or over $100,000 where sufficient audit information is already

available pursuant to OMB Audits A-133 or A-128 requirements.

G.   FILE RETENTION:

The official CHSP grant case files are

unscheduled, but a HUD records disposition schedule is being

developed to provide disposition instructions for the files (see

Appendix 5 for HUD Records Disposition Schedule 3).  After grant

closeout, these files Cannot be retired to a Federal Records

Center until the National Archives and Records Administration

(NARA) has approved that schedule.

CHSP grant files that are maintained by HUD State

or Area Offices are covered by item 17 of HUD Records Disposition

Schedule 3 which requires that they be destroyed 6 years after

the grant is formally closed out.  Once the CHSP Records

Disposition Schedule is approved, HUD offices can retire the

files to the Federal Records Center any time after grant closeout

that volume warrants.

21

_____________________________________________________________________

FmHA State Offices should follow the disposition

instructions in FmHA's records disposition schedules for the CHSP

files which they maintain.

Questions regarding the material in this Notice

should be directed to the Services Branch at 202-708-3291.

_____________________________________

Assistant Secretary for Housing

- Federal Housing Commissioner

Attachments

22

_____________________________________________________________________

LIST OF APPENDICES

1A.  *HUD-718, Funds Reservation and Contract Authority

(sample form)

1B.  HUD-718,  Instructions for completion

2A.  *HUD-1044,  Assistance Award/Amendment (sample form)

2B.  HUD-1044, Instructions for completion

3.   SF-269, Financial Status Report

4.   *HUD-24016, Final GTR Performance Assessment for

Assistance Agreements

5.   Records Disposition Schedule 3

*    Forms are available in their electronic format on the LAN:

see LAN Main Menu; Office Systems, item E "HUD FORMS"

_____________________________________________________________________

APPENDIX 1A

___________________________________________________________________________

FUNDS RESERVATION & CONTRACT AUTHORITY

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

___________________________________________________________________________

HUD-718 (3-76)

_____________________________________________________________________

___________________________________________________________________________

PREPARATION INSTRUCTIONS FOR FORM HUD-718

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

___________________________________________________________________________

_____________________________________________________________________

APPENDIX 1B

COMPLETION OF THE FUNDS RESERVATION AND CONTRACT AUTHORITY FORMAT

The Funds Reservation and Contract Authority (HUD-718) is

completed by the GTR.  The following blanks must be filled in:

item 1A - full name and address of grantee with

the TIN and EIN number underneath the

address, clearly labeled.

item 1B - grant number

item 2  - self explanatory

item 3  - put in Field Office reservation sequence

number.  Will include "CHS-94" as part

of whatever system used; Field Office

establishes reservation number

item 4  - insert name of GTR

item 5A - insert "Congregate Housing Services" and

appropriation number as appropriate.

The appropriation number is stated on

the HUD-185.

For HUD grants, also insert "NCH" which

indicates grantees will receive

reimbursement under LOCCS/VRS.

For FmHA grants, also insert "CFH" which

indicates grantees will receive

reimbursement under LOCCS/VRS.

item 5B/C - leave blank

item 5D - leave blank

item 5E/F -    put in amount of amendment request

both in upper space and in totals

line.

item 6B - check-off and fill in amendment number.

item 7A - insert "To provide support services to

elderly and non-elderly disabled

residents of eligible housing for the

elderly."

APPENDIX 1B (cont'd)

_____________________________________________________________________

item 8A/B - self explanatory

item 9A - GTR's supervisor

item 9B - fill in name and put title "Director of

Housing" or "Director of Housing

Management", as appropriate.

item 9C  - self explanatory

item 9D  - for "Director of Management"

item 9E  - self explanatory

item 10  - signed by RAD official

_____________________________________________________________________

APPENDIX 2A

___________________________________________________________________________

Assistance Award/

Amendment

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

___________________________________________________________________________

form HUD-1044 (8/90)

_____________________________________________________________________

APPENDIX 2B

COMPLETION OF THE GRANT ASSISTANCE AWARD/AMENDMENT FORMAT:

The grant award/amendment (HUD-1044) is written up by the GTR.

The following blanks must be filled in:

item 1 -  check-off "grant"

item 2 -  check-off "amendment"

item 3 -  insert the grant number

item 4 -  insert sequential amendment number

item 5 -  insert day executed by the Grant Officer

item 6 -  insert FO designated number, if any

item 7 -  insert full name and address of grantee.

Below the address list the grantee's TIN

or EIN number, clearly labeled.

item 8 -  insert FO Housing Management/FmHA State

Office address

item 8A - List Grant Officer

item 8B - List Grant Officer's telephone number

and TDD number

item 9 -  List name and telephone number of the

GTR, and TDD telephone number for the

hearing impaired, plus Field Office code

if applicable (secure Field Office code

list from OFA).

Use the HUD codes also for the FmHA

grantees, as they will also draw down

their funds through the HUD LOCCS/VRS.

If there is insufficient space state

"continued in Item 16" and list there.

item 10 - list name and telephone number of

grantee contact person.

item 11 - check-off "cost reimbursement" and "cost

sharing"

_____________________________________________________________________

APPENDIX 2B (cont'd)

item 12 - check-off "automated clearinghouse"

item 13 - insert "see Paragraph 3 of the schedule

of terms and conditions (LOCCS/VRS)

item 14 - insert "Previous HUD Amount," insert

total obligation figure from prior

years.  For HUD amount this Action"

insert current amount requested.

For "total HUD amount," combine two

prior figures.  For recipient amount,

insert total of match and fees.

For "total instrument amount", insert

total of prior figures.

item 15A  -    insert appropriation code from 718.

item 15B  -    insert reservation number (from FO)

-    "Obligation by this action" and

"total obligation" is same as

"total HUD amount" from No. 14.

item 16 - State purpose of the amendment and that

all of the programmatic elements of the

prior grant instrument, HG ------  and

amendment documents as submitted, are

incorporated herein.

item 17 - check-off

item 18 - leave blank

item 19 - insert name of grantee official

item 20 - insert name of Grant Officer

_____________________________________________________________________

APPENDIX 3

___________________________________________________________________________

FINANCIAL STATUS REPORT

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

___________________________________________________________________________

_____________________________________________________________________

APPENDIX 3

(Continued)

___________________________________________________________________________

FINANCIAL STATUS REPORT

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

___________________________________________________________________________

_____________________________________________________________________

APPENDIX 4

___________________________________________________________________________

Final GTR Performance

Assessment

for Assistance Agreements

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

___________________________________________________________________________

_____________________________________________________________________

APPENDIX 4

(Continued)

___________________________________________________________________________

********************************************************************

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*       GRAPHICS  MATERIAL  IN  ORIGINAL  DOCUMENT  OMITTED        *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

*                                                                  *

********************************************************************

___________________________________________________________________________

_____________________________________________________________________

APPENDIX 5

2225.6 REV-1 CHG-4

APPENDIX 3

___________________________________________________________________________

RECORDS DISPOSITION SCHEDULE 3

ADMINISTRATIVE RECORDS

Item

No.         Description of Records               Disposition

_____        ______________________               ___________

c.   Printouts, output reports.         Destroy when superseded,

complete or no longer needed

for reference.  (NARA Job

NC1-207-80-5, item 14c)

15.  IDEAS Case Files.

a.   Rejected.                          Destroy 2 years after

rejection.  (NARA Job

N1-207-89-1, item 15a)

b.   Adopted.                           Retain for 2 years from date

of adoption, then retire to

Federal Records Center.

Destroy 5 years after date of

adoption.  (NARA Job

N1-207-89-1, item 15b)

Contracts, Grants, Supplies

16.  Records related to contracts and

grants and to obtaining supplies.

*    a.   Program contract/grant records.    Use the appropriate HUD

records disposition schedule

covering the program's

records.  (NARA Job

N1-207-91-1, item 16a)

b.   All other records.                 Use General Records Schedule

(GRS) 3 and items 17 through

19 of this schedule.  (NARA

Job N1-207-91-1, item 16b)

17. Government Technical Representative     Destroy 6 years after contract

(GTR) case files.  The GTR is the       or grant is formally closed

program person responsible for the      out.  (NARA Job N1-207-91-1,

technical direction and evaluation of   item 17)

contractor/grantee performance.  GTR

case files consist of copies of the

request for services, Request for

Proposals (RFP) and amendments,                                      *

___________________________________________________________________________

9/92

11

_____________________________________________________________________

APPENDIX 5 (cont'd)

2225.6 REV-1 CHG-4

APPENDIX 3

___________________________________________________________________________

RECORDS DISPOSITION SCHEDULE 3

ADMINISTRATIVE RECORDS

Item

No.         Description of Records               Disposition

_____        ______________________               ___________

*       technical and cost proposals and

modifications submitted by the

contractor/grantee, conformed copy

of contract/copy of grant agreement and

modifications, contractor's/grantee's

management reports to GTR, GTR reports

and memoranda, contractor's/grantee's

interim and final technical reports,

GTR evaluation reports, distribution

list for final report, statement of

final contract/grant status and any

related correspondence or other

documents.

17-1.  Government Technical Monitor (GTM)   Transfer files to the GTR when

files.  The content of GTM files     contract/grant is closed out.

varies depending on what authority   The GTR screens the GTM files

the GTR has delegated to the GTM.    to eliminate any duplicate

GTM files have the same kinds of     records and adds the remaining

documentation as GTR files.          files to the GTR case file.

Use the disposition in item 17

for the combined files.  (NARA

Job N1-207-91-1, item 17-1)

18.    Extra copies of contractor's/        Destroy when superseded,

grantee's final report.              obsolete, or no longer needed

for reference.  (NARA Job

N1-207-91-1, item 18)        *

19.    Office of Procurement and Contracts

(OPC) Management Information System.

This ADP system will provide a

systematic procedure and reporting

structure to monitor procurement

actions in both pre-award and

post-award phases of a contract.  It

will report contract status for each

___________________________________________________________________________

9/92                               12