Legal Opinion: GCH-0045

Index:  2.810

Subject:  Cancellation of Section 202/8 Fund Reservation

February 24, 1992

MEMORANDUM FOR:  Robert W. Wilden, Director, Assisted

Elderly and Handicapped Housing Division, HMEE

FROM:  Robert S. Kenison, Associate General Counsel

Office of Assisted Housing and Community Development, GC

SUBJECT:  Cancellation of Section 202/8 Fund Reservation

Torrington VOA Elderly Housing, Inc.

This responds to your February 5, 1992, memorandum

requesting advice as to whether it would be legally permissible

to reinstate reservations of Section 202 loan authority and

Section 8 contract and budget authority (referred to hereinafter

as "section 8 funds") terminated in the period between October 1

and October 7, 1991.  The Section 202 loan and Section 8 contract

and budget authority were reserved in Fiscal Year 1986 and the

Denver Office processed the forms deobligating the funds on

October 4, 1991.

The Office of Housing issued a Book Memorandum to HUD Field

Offices on September 12, 1991, advising that no further

deobligations of funds should occur until October 1, 1991, but

that these offices "may proceed with deobligation of Section 202

and Section 8 funds beginning October 1, 1991, unless you are

notified to the contrary."  On October 7, 1991, a similar

memorandum directed that no further reservations shall be

cancelled pending approval of the Fiscal Year 1992 Appropriations

Act and determination of its effect.  The Appropriations Act

provided that no project not making satisfactory progress shall

have its loan reservation terminated before January 1, 1992.  We

understand that the subject project was the only one whose

funding was terminated during this one-week time period.

Since the Section 8 reservation was terminated in Fiscal

Year 1992, the contract and budget authority recaptured were

rescinded, pursuant to the Fiscal Year 1992 HUD Appropriations

Act, and are therefore not available to restore the Section 8

funding that was terminated.  The Fiscal Year 1986 HUD

Appropriations Act authorized loans to be made in the amount of

$631,033,000 in the year 1986.  The effect of terminating the

reservation of Section 202 loan funds made in Fiscal Year 1986

was to cause this authority to lapse.  Action to restore this

funding would be a Fiscal Year 1992 obligation which could not be

2

made from funds available for obligation only in Fiscal Year 1986.

Since the reservations of Section 202 loan authority and

Section 8 contract and budget authority which were terminated

cannot be reinstated, the further question is raised as to

whether the circumstances of the termination are such as to

afford a legally acceptable basis to provide currently available

funding for this project outside the competitive process.  We do

not believe that Section 102 of the HUD Reform Act contains

authority to provide current year's funding outside the

competitive process because of inequities or mistakes in

processing involving prior year's funding.

In any event, we do not find such a justification in the

circumstances of the Torrington VOA project.  As already pointed

out, the Denver Office complied with instructions received from

the Office of Housing in regard to the termination of funding.

In reviewing the processing history of this project we find that

the Sponsor selected a succession of new sites which resulted in

processing delays and otherwise failed to meet the deadlines

established in successive time extensions.  The maximum three-

year time period from fund reservation to start of construction

provided in 24 CFR section 885.230 would have ended for this

project in September 1989.  In September 1990 the Sponsor was

afforded a 90-day extension to submit an acceptable conditional

commitment application, which it failed to do.  Notwithstanding

this failure, the Denver Office recommended and Central Office

approved an extension to July 30, 1991, with the understanding

that the project would be under construction by September 30,

1991 or the fund reservation would be terminated.  Although the

Denver Office indicated that, if a firm commitment application

was received by September 9, 1991, the loan could be closed by

September 30, 1991; the Sponsor failed to meet this deadline,

with the result that the fund reservation was terminated.

Although it has been indicated that this project was the

only one terminated in the period October 1-7, 1991, we

understand that more than 50 Fiscal Year 1986 and 1987 fund

reservations were terminated during Fiscal Year 1991.  In any

event, the history of this project does not support the

conclusion that termination of the funding was erroneous or

improper.  If the Sponsor still desires funding for this project,

it will need to apply under the Fiscal Year 1992 Notice of Fund

Availability for the Section 202 Program.