## Instructions
Project Tailoring Agreement PPM V2.0
Column | Instructions For Completing This Document
Complete the Project Name, Project Phase, Project Type fields
B | Artifact: This is a pre-populated locked field that lists all of the artifacts that could be initiated, updated, or finalized in each phase.
C | Tailoring: This is an unlocked field used by project teams to propose a tailoring agreement for each artifact. Each possible tailoring agreement is defined below. By default, all artifacts are required. «Required: Use this when the artifact is required and must be created and use the comment column in the PTA to describe the level of detail associated with the artifact (e.g. initiative level, project level, sub-project level). «May be Applicable: This is a TEMPORARY selection to denote if the project is not necessarily required for the project type. As the project develops their Project Tailoring Agreement, any artifacts with this designation as the default should be changed to one of the other 5 choices. «Combine: Use this when you will address the requirements associated with the artifact in question as a section within a larger document rather than as a stand-alone artifact. Combining component management plans (e.g. risk, communication, staffing) into a single, comprehensive Project Management Plan is sometimes more efficient than managing several distinct artifacts; however, it’s not desirable to combine so much content into a single document as to make the document difficult to maintain. «Omit: Use this when a project team determines that the requirements associated with a particular artifact are not applicable to the project. A project must justify its choice to omit an artifact. For example, a project may “omit” the Concept of Operations (CONOPS) artifact if the project is small enough that stakeholders can get a clear picture of the solution based on the descriptions of scope and requirements contained in other artifacts. Also, if the Initial Privacy Assessment (IPA) does not identify and privacy concerns, a project may “omit” the System of Records Notice (SORN) .Use the comment column in the PTA to document the rationale for excluding the artifact. «Refer: Use this when a pre-existing document or system record fully satisfies the requirements associated with the artifact in question and the current project does not cause a need for an update. The “refer” option is most frequently used in connection with security artifacts for projects that are modifications to existing systems. For example, a project that is executing a modification to an existing system may “refer” the Certification and Accreditation memo to a pre-existing record in CSAM that is complete and up-to-date. «Defer: Use this when you will address the requirements associated with the artifact during a future PPM Life Cycle phase rather than during the current Life Cycle phase. Deferring artifacts to future phases is most frequently used when the necessary requirements will be unknown until the activities of the current phase are complete. For example, a project might “Defer” the Solution Architecture document from the Definition Phase to the Design Phase as the completed and approved Risk Adjusted Cost Benefit Analysis of Alternatives (CBA) may be needed to develop the solution architecture on the selected alternative.
D | Category: This is an unlocked field that categorizes the project artifact. The following categories are acceptable: Project Business System N/A (Primarily for Control Gate Reviews)
E | Comments: This is an unlocked field that is used by different groups for different purposes: The IPT uses the comment column to qualify proposed tailoring agreements to refer, combine, or omit artifacts. The PMO uses the comment column to provide additional context and descriptions for ratings given to artifact completeness.
Column | Instructions For Changing the Contents of Drop-Down Menus
Any | Highlight the cell of which you wish to change the content of the drop down menu. From the file menu click "Data" -> "Validation" and change the content of the source field
Column | Instructions For Filtering Data
Any | Highlight the header of the cell you wish to filter data on From the file menu click "Date" -> "Filter" ->"Auto Filter" Then select your filter criteria from the drop down menu that appears on your header cell

## PTA - Mods Enhancements
Project Information
Name:
PPM Life Cycle Phase:
Project Type: | Modifications/Enhancements
Artifact | Tailoring | Category | Comments
Initiation - Project Validation Review
Project Initiation Form (PIF) | Required | Project
Project Charter | Required | Project
Project Schedule (WBS) | Required | Project
Procurement Management Plan | May be Applicable | Project
TRC Control Gate Decision | Required | N/A
Planning - Project Baseline Review
Project Tailoring Agreement (PTA) | Required | Project
Project Management Plan (PMP) | May be Applicable | Project
Concept of Operations (CONOPS) | May be Applicable | Project and Business
Requirements Definition Document | May be Applicable | Project and Business
Requirements Management Plan | May be Applicable | Project
Requirements Traceability Matrix (RTM) | Required | Project and System
Risk Management Log | May be Applicable | Project
Independent Verification & Validation Plan (IV&V) | May be Applicable | Project
Solution Architecture Document | May be Applicable | Project and System
Security & Privacy Artifacts (FIPS 199, IPA, SORN, PIA) | May be Applicable | System | Work with your security and privacy IPT members to determine the required documents for your project
TRC Control Gate Decision | Required | N/A
Execution & Control - Operational Readiness Review and As Needed Reviews
Technical Design Document (TDD) | May be Applicable | Project and System
Interface Control Document (ICD) | May be Applicable | Project and System
Change Management Log | May be Applicable | Project
Implementation Plan | May be Applicable | Project and System
Test Plan & Test Reports | May be Applicable | Project and System
Data Conversion Plan | May be Applicable | Project and System
User Manual | May be Applicable | Business
Operations and Maintenance (O&M) Manual | May be Applicable | System
Security Assessment and Authorization to Operate (ATO) Request | Required | System | Work with your security IPT member to determine the required documents for your project
TRC Control Gate Decision (#1) | Required | N/A | One control gate must consist be an Operational Readiness Review
TRC Control Gate Decision (#2) | Required | N/A | Work with the TRC to determine the number of control gates for this phase
Close Out - Project Close Out Review
Project Completion Report | Required | Project
TRC Control Gate Decision | Required | N/A